## PRJ Groups Main Info
PRJ Groups Main Information
PRJ Code | PRJ Name | PRJ Status | PRJ Commissioning Year First | PRJ Commissioning Year Last | PRJ Group Description | Code of individual projects | Project Name | Project Promoter | Project Host Country
PRJ-G-001 | Physical Reverse Flow at Moffat interconnection point (IE/UK) | Less-Advanced | 2020 | 2020 | Physical Reverse Flow at the Moffat interconnection point, which is currently uni-directional, suppo | TRA-N-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | GNI (UK) Limited | UK
PRJ-G-001 | Physical Reverse Flow at Moffat interconnection point (IE/UK) | Less-Advanced | 2020 | 2020 | Physical Reverse Flow at the Moffat interconnection point, which is currently uni-directional, suppo | TRA-N-1064 | Moffat Physical Reverse Flow | National Grid Gas plc | UK
PRJ-G-002 | Bidirectional Austrian - Czech Interconnection (BACI) | Advanced | 2021 | 2021 | The project of the Bidirectional Austrian - Czech Interconnection (BACI) is a planned pipeline to en | TRA-N-21 | Bidirectional Austrian-Czech Interconnector (BACI) | GAS CONNECT AUSTRIA GmbH | AT
PRJ-G-002 | Bidirectional Austrian - Czech Interconnection (BACI) | Advanced | 2021 | 2021 | The project of the Bidirectional Austrian - Czech Interconnection (BACI) is a planned pipeline to en | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | NET4GAS, s.r.o. | CZ
PRJ-G-003 | Interconnection Slovenia-Croatia (Gas pipeline Lučko-Zabok-Rogatec) | Less-Advanced | 2021 | 2022 | New pipeline which will upgrade the existing interconnection Croatia/Slovenia. Along with the existi | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd | HR
PRJ-G-003 | Interconnection Slovenia-Croatia (Gas pipeline Lučko-Zabok-Rogatec) | Less-Advanced | 2021 | 2022 | New pipeline which will upgrade the existing interconnection Croatia/Slovenia. Along with the existi | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. | SI
PRJ-G-004 | Krk LNG terminal with connecting and evacuation pipelines towards Hungary and beyond | Advanced | 2019 | 2023 | Project which includes the construction of the LNG terminal on the island of Krk and the gas pipelin | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | HR
PRJ-G-004 | Krk LNG terminal with connecting and evacuation pipelines towards Hungary and beyond | Advanced | 2019 | 2023 | Project which includes the construction of the LNG terminal on the island of Krk and the gas pipelin | LNG-N-82 | LNG terminal Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | HR
PRJ-G-004 | Krk LNG terminal with connecting and evacuation pipelines towards Hungary and beyond | Advanced | 2019 | 2023 | Project which includes the construction of the LNG terminal on the island of Krk and the gas pipelin | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd | HR
PRJ-G-004 | Krk LNG terminal with connecting and evacuation pipelines towards Hungary and beyond | Advanced | 2019 | 2023 | Project which includes the construction of the LNG terminal on the island of Krk and the gas pipelin | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd | HR
PRJ-G-005 | CZ/SK Capacity4Gas Project - Capacity increase at IP Lanžhot | FID | 2019 | 2020 | The objective of the CZ/SK Capacity4Gas Project - Capacity increase at IP Lanžhot Project, carried o | TRA-F-902 | Capacity increase at IP Lanžhot entry | eustream,a.s. (a joint-stock company) | SK
PRJ-G-005 | CZ/SK Capacity4Gas Project - Capacity increase at IP Lanžhot | FID | 2019 | 2020 | The objective of the CZ/SK Capacity4Gas Project - Capacity increase at IP Lanžhot Project, carried o | TRA-F-918 | Capacity4Gas – CZ/SK | NET4GAS, s.r.o. | CZ
PRJ-G-008 | Poland – Slovakia Gas Interconnection | FID | 2021 | 2021 | The main goal of the PL-SK Interconnection is to create the first bi-directional cross-border pipeli | TRA-F-190 | Poland - Slovakia interconnection | eustream,a.s. (a joint-stock company) | SK
PRJ-G-008 | Poland – Slovakia Gas Interconnection | FID | 2021 | 2021 | The main goal of the PL-SK Interconnection is to create the first bi-directional cross-border pipeli | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | PL
PRJ-G-010 | Latvia - Lithuania interconnection | Less-Advanced | 2020 | 2021 | The project aims at enhancing the capacity of the gas systems between Latvia and Lithuania. | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | JSC "Conexus Baltic Grid" | LV
PRJ-G-010 | Latvia - Lithuania interconnection | Less-Advanced | 2020 | 2021 | The project aims at enhancing the capacity of the gas systems between Latvia and Lithuania. | TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | AB Amber Grid | LT
PRJ-G-011 | Interconnection Estonia – Finland | FID | 2019 | 2019 | New bidirectional offshore pipeline ﴾Inkoo‐Paldiski, DN500, 80 bar﴿ of 80 km, plus 55 km onshore pip | TRA-F-895 | Balticconnector | Elering AS | EE
PRJ-G-011 | Interconnection Estonia – Finland | FID | 2019 | 2019 | New bidirectional offshore pipeline ﴾Inkoo‐Paldiski, DN500, 80 bar﴿ of 80 km, plus 55 km onshore pip | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FI
PRJ-G-012 | Bidirectional flows between Italy and Germany and France through Switzerland | FID | 2018 | 2018 | The Group aims at creating Reverse Flow capacity along the South-North route in the priority Corrido | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | GRTgaz | FR
PRJ-G-012 | Bidirectional flows between Italy and Germany and France through Switzerland | FID | 2018 | 2018 | The Group aims at creating Reverse Flow capacity along the South-North route in the priority Corrido | TRA-F-208 | Reverse Flow TENP Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | DE
PRJ-G-012 | Bidirectional flows between Italy and Germany and France through Switzerland | FID | 2018 | 2018 | The Group aims at creating Reverse Flow capacity along the South-North route in the priority Corrido | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. | IT
PRJ-G-012 | Bidirectional flows between Italy and Germany and France through Switzerland | FID | 2018 | 2018 | The Group aims at creating Reverse Flow capacity along the South-North route in the priority Corrido | TRA-F-230 | Reverse Flow Transitgas Switzerland | FluxSwiss | CH
PRJ-G-013 | North Interconnection of BiH and Croatia | Less-Advanced | 2020 | 2023 | Interconnection gaspipeline Slobodnica - Brod - Zenica should be connected to the existing high-pres | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | HR
PRJ-G-013 | North Interconnection of BiH and Croatia | Less-Advanced | 2020 | 2023 | Interconnection gaspipeline Slobodnica - Brod - Zenica should be connected to the existing high-pres | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. | BA
PRJ-G-014 | South Interconnection of BiH and Croatia | Less-Advanced | 2021 | 2023 | Southern Interconnection pipeline BIH-CRO by the route Zagvozd-Posusje-Travnik with main branch to M | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | HR
PRJ-G-014 | South Interconnection of BiH and Croatia | Less-Advanced | 2021 | 2023 | Southern Interconnection pipeline BIH-CRO by the route Zagvozd-Posusje-Travnik with main branch to M | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. | BA
PRJ-G-015 | West Interconnection of BiH and Croatia | Less-Advanced | 2026 | 2027 | West Interconnection Pipeline Licka Jesenica (CRO) -Trzac (BiH)- Bosanska Krupa with branches to Bih | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | HR
PRJ-G-015 | West Interconnection of BiH and Croatia | Less-Advanced | 2026 | 2027 | West Interconnection Pipeline Licka Jesenica (CRO) -Trzac (BiH)- Bosanska Krupa with branches to Bih | TRA-N-910 | West Interconnection BiH/CRO | BH-Gas d.o.o. | BA
PRJ-G-017 | Gas Interconnection Poland-Lithuania (GIPL) | FID | 2021 | 2021 | Gas Interconnection Poland-Lithuania (GIPL) is implemented by two project promoters - GAZ-SYSTEM S.A. and AB Amber Grid. | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | PL
PRJ-G-017 | Gas Interconnection Poland-Lithuania (GIPL) | FID | 2021 | 2021 | Gas Interconnection Poland-Lithuania (GIPL) is implemented by two project promoters - GAZ-SYSTEM S.A. and AB Amber Grid. | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | AB Amber Grid | LT
PRJ-G-018 | Additional capacity at Oude Statenzijl from Germany to the Netherlands | Less-Advanced | 2025 | 2025 | Additional capacity at Oude Statenzijl from Germany to the Netherlands | TRA-N-808 | Transport of gas volumes to the Netherlands | Gasunie Deutschland Transport Services GmbH | DE
PRJ-G-018 | Additional capacity at Oude Statenzijl from Germany to the Netherlands | Less-Advanced | 2025 | 2025 | Additional capacity at Oude Statenzijl from Germany to the Netherlands | TRA-N-873 | Additional capacity at OSZ from Germany to the Netherlands | Gasunie Transport Services B.V. | NL
PRJ-G-021 | Baltic Pipe Project | Advanced | 2022 | 2022 | The projects in the project group aim at connecting the gas transmission systems in Poland, Denmark | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | PL
PRJ-G-021 | Baltic Pipe Project | Advanced | 2022 | 2022 | The projects in the project group aim at connecting the gas transmission systems in Poland, Denmark | TRA-N-780 | Baltic Pipe project – onshore section in Denmark | Energinet.dk | DK
PRJ-G-021 | Baltic Pipe Project | Advanced | 2022 | 2022 | The projects in the project group aim at connecting the gas transmission systems in Poland, Denmark | TRA-N-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | PL
PRJ-G-022 | Poland - Czech Republic Interconnection | Advanced | 2022 | 2022 | The planned Poland - Czech Republic Interconnection project consists of: a) the construction of a p | TRA-N-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | CZ
PRJ-G-022 | Poland - Czech Republic Interconnection | Advanced | 2022 | 2022 | The planned Poland - Czech Republic Interconnection project consists of: a) the construction of a p | TRA-N-273 | Poland - Czech Republic Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | PL
PRJ-G-023 | PRJ LNG Terminal Brunsbuettel | Less-Advanced | 2021 | 2021 | Integration of the LNG Terminal Brunsbuettel (Area Hamburg) into the German Gas Infrastructure | LNG-N-1198 | LNG Terminal Brunsbuettel | Gasunie Deutschland Transport Service GmbH | DE
PRJ-G-023 | PRJ LNG Terminal Brunsbuettel | Less-Advanced | 2021 | 2021 | Integration of the LNG Terminal Brunsbuettel (Area Hamburg) into the German Gas Infrastructure | TRA-N-1199 | LNG Terminal Brunsbuettel - Grid Integration | Gasunie Deutschland Transport Service GmbH | DE
PRJ-G-028 | Poland - Ukraine Gas Interconnection | Advanced | 2020 | 2020 | The objective of the project is to create a large transportation corridor between Poland and Ukraine | TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | PJSC UKRTRANSGAZ | UA
PRJ-G-028 | Poland - Ukraine Gas Interconnection | Advanced | 2020 | 2020 | The objective of the project is to create a large transportation corridor between Poland and Ukraine | TRA-N-621 | Poland - Ukraine Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | PL
PRJ-G-030 | Decline of L-gas export | Less-Advanced | 2018 | 2030 | Due to the decline of production from the Groningen field, export capacity of L-gas x-border station | TRA-N-845 | Decline of L-gas export capacity | Gasunie Transport Services B.V. | NL
PRJ-G-030 | Transferring L-gas infrastructure to H-gas | Less-Advanced | 2018 | 2030 | Due to the of production of the Groningen field, L-gas export from the Netherlands to Germany is red | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Gasunie Transport Services B.V. | NL
PRJ-G-030 | Transferring L-gas infrastructure to H-gas | Less-Advanced | 2018 | 2030 | Due to the of production of the Groningen field, L-gas export from the Netherlands to Germany is red | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | DE
PRJ-G-030 | Transferring L-gas infrastructure to H-gas | Less-Advanced | 2018 | 2030 | Due to the of production of the Groningen field, L-gas export from the Netherlands to Germany is red | TRA-N-951 | Embedding CS Folmhusen in H-Gas | Gasunie Deutschland Transport Services GmbH | DE
PRJ-G-030 | Transferring L-gas infrastructure to H-gas | Less-Advanced | 2018 | 2030 | Due to the of production of the Groningen field, L-gas export from the Netherlands to Germany is red | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | DE
PRJ-G-034 | More capacity – DE/CZ Capacity4Gas Project | Advanced | 2019 | 2021 | The objective of the More capacity – DE/CZ Capacity4Gas Project is to satisfy market demand that was | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | DE
PRJ-G-034 | More capacity – DE/CZ Capacity4Gas Project | Advanced | 2019 | 2021 | The objective of the More capacity – DE/CZ Capacity4Gas Project is to satisfy market demand that was | TRA-N-809 | Additional East-West transport | Gasunie Deutschland Transport Services GmbH | DE
PRJ-G-034 | More capacity – DE/CZ Capacity4Gas Project | Advanced | 2019 | 2021 | The objective of the More capacity – DE/CZ Capacity4Gas Project is to satisfy market demand that was | TRA-N-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | ONTRAS Gastransport GmbH | DE
PRJ-G-034 | More capacity – DE/CZ Capacity4Gas Project | Advanced | 2019 | 2021 | The objective of the More capacity – DE/CZ Capacity4Gas Project is to satisfy market demand that was | TRA-F-752 | Capacity4Gas – DE/CZ | NET4GAS, s.r.o. | CZ
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | 2024 | 2028 | The 3rd Interconnection between Portugal and Spain is developed in 2 phases: - The 1st phase cons | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | PT
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | 2024 | 2028 | The 3rd Interconnection between Portugal and Spain is developed in 2 phases: - The 1st phase cons | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. | ES
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | 2024 | 2028 | The 3rd Interconnection between Portugal and Spain is developed in 2 phases: - The 1st phase cons | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | REN-Gasodutos, S.A. | PT
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | 2024 | 2028 | The 3rd Interconnection between Portugal and Spain is developed in 2 phases: - The 1st phase cons | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | REN-Gasodutos, S.A. | PT
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | 2024 | 2028 | The 3rd Interconnection between Portugal and Spain is developed in 2 phases: - The 1st phase cons | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. | ES
PRJ-G-039 | STEP (South Transit East Pyrenees) | Advanced | 2022 | 2022 | STEP project consist in the third interconnection between France and Spain on the eastern part of | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. | ES
PRJ-G-039 | STEP (South Transit East Pyrenees) | Advanced | 2022 | 2022 | STEP project consist in the third interconnection between France and Spain on the eastern part of | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | TIGF | FR
PRJ-G-041 | Pipeline system from Bulgaria via Romania and Hungary to Slovakia [currently known as "Eastring“ | Less-Advanced | 2023 | 2028 | Project Eastring is a new concept of a pan-EU bi-directional transmission pipeline. Technically it w | TRA-N-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | SK
PRJ-G-041 | Pipeline system from Bulgaria via Romania and Hungary to Slovakia [currently known as "Eastring“ | Less-Advanced | 2023 | 2028 | Project Eastring is a new concept of a pan-EU bi-directional transmission pipeline. Technically it w | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | BG
PRJ-G-041 | Pipeline system from Bulgaria via Romania and Hungary to Slovakia [currently known as "Eastring“ | Less-Advanced | 2023 | 2028 | Project Eastring is a new concept of a pan-EU bi-directional transmission pipeline. Technically it w | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA | RO
PRJ-G-041 | Pipeline system from Bulgaria via Romania and Hungary to Slovakia [currently known as "Eastring“ | Less-Advanced | 2023 | 2028 | Project Eastring is a new concept of a pan-EU bi-directional transmission pipeline. Technically it w | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | HU
PRJ-G-044 | MidCat (Iberian-French corridor, Eastern Axis – MidCat project) | Advanced | 2024 | 2024 | MidCat aims to develop the interconnection capacity between France and Spain. This project creates t | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | FR
PRJ-G-044 | MidCat (Iberian-French corridor, Eastern Axis – MidCat project) | Advanced | 2024 | 2024 | MidCat aims to develop the interconnection capacity between France and Spain. This project creates t | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. | ES
PRJ-G-045 | Enhancement of the capacity at SK-HU interconnector | Less-Advanced | 2022 | 2022 | The purpose of the project is to expand the capacity of the border crossing point at Balassagyarmat/ | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | HU
PRJ-G-045 | Enhancement of the capacity at SK-HU interconnector | Less-Advanced | 2022 | 2022 | The purpose of the project is to expand the capacity of the border crossing point at Balassagyarmat/ | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | HU
PRJ-G-045 | Enhancement of the capacity at SK-HU interconnector | Less-Advanced | 2022 | 2022 | The purpose of the project is to expand the capacity of the border crossing point at Balassagyarmat/ | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | eustream,a.s. (a joint-stock company) | SK
PRJ-G-046 | Creation of a single gas market area in France | FID | 2018 | 2018 | The project aims to create a single gas market area in France, consistent with the European gas mark | TRA-F-43 | Val de Saône project | GRTgaz | FR
PRJ-G-046 | Creation of a single gas market area in France | FID | 2018 | 2018 | The project aims to create a single gas market area in France, consistent with the European gas mark | TRA-F-331 | Gascogne Midi | TIGF - GRTgaz | FR
PRJ-G-047 | RO-HU Transmission Corridor | Advanced | 2019 | 2022 | The transmission Corridor ensures bidirectional capacity between Romania and Hungary. | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. | HU
PRJ-G-047 | RO-HU Transmission Corridor | Advanced | 2019 | 2022 | The transmission Corridor ensures bidirectional capacity between Romania and Hungary. | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ Ltd. | HU
PRJ-G-049 | Fos Cavaou LNG Terminal Expansion | Less-Advanced | 2021 | 2023 | The project aims to expand the LNG terminal capacity from 8.25 bcm/y up to 16.5 bcm/y, with intermed | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | Fosmax LNG | FR
PRJ-G-049 | Fos Cavaou LNG Terminal Expansion | Less-Advanced | 2021 | 2023 | The project aims to expand the LNG terminal capacity from 8.25 bcm/y up to 16.5 bcm/y, with intermed | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | FR
PRJ-G-050 | Montoir LNG Terminal Expansion | Less-Advanced | 2021 | 2023 | The project aims to expand the Montoir de Bretagne LNG terminal capacity by 2.5 bcm/y, from 10 bcm/y | LNG-N-225 | Montoir LNG Terminal Expansion | Elengy | FR
PRJ-G-050 | Montoir LNG Terminal Expansion | Less-Advanced | 2021 | 2023 | The project aims to expand the Montoir de Bretagne LNG terminal capacity by 2.5 bcm/y, from 10 bcm/y | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | FR
PRJ-G-054 | LNG | Less-Advanced | 2020 | 2020 | Gate expansion | LNG-N-50 | Gate terminal phase 3 | Gate | NL
PRJ-G-054 | LNG | Less-Advanced | 2020 | 2020 | Gate expansion | TRA-N-192 | Entry capacity expansion GATE terminal | Gasunie Transport Services B.V. | NL
PRJ-G-055 | LNG terminal in northern Greece / Alexandroupolis | Advanced | 2020 | 2020 | The project consists of an LNG offshore Floating Storage Regasification Unit, a Mooring & a Pipeline | LNG-N-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Gastrade S.A. | GR
PRJ-G-055 | LNG terminal in northern Greece / Alexandroupolis | Advanced | 2020 | 2020 | The project consists of an LNG offshore Floating Storage Regasification Unit, a Mooring & a Pipeline | TRA-N-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. | GR
PRJ-G-056 | New UGS in Cornegliano Laudense (IT) | FID | 2018 | 2018 | The Group aims at creating a new UGS facility in northern Italy and the relative connection to the n | UGS-F-242 | Cornegliano UGS | ITAL Gas Storage | IT
PRJ-G-056 | New UGS in Cornegliano Laudense (IT) | FID | 2018 | 2018 | The Group aims at creating a new UGS facility in northern Italy and the relative connection to the n | TRA-F-1228 | Interconnection with UGS in Cornegliano Laudense | Snam Rete Gas S.p.A. | IT
PRJ-G-060 | Hungary – Slovenia interconnection | Less-Advanced | 2022 | 2023 | Interconnector between the Hungarian and Slovenian transmission systems on the route Nagykanizsa - T | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | HU
PRJ-G-060 | Hungary – Slovenia interconnection | Less-Advanced | 2022 | 2023 | Interconnector between the Hungarian and Slovenian transmission systems on the route Nagykanizsa - T | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | SI

## Investment Project Main Info
Investment Project Main Information
PRJ Code | PRJ Name | PRJ Status | Code | Project Name | Country | Promoter | Maturity Status | PCI 3rd List | PCI 3rd List Code | PCI Priority Corridors | Intention to apply to 4th PCI List | Project Commissioning Year First | Project Commissioning Year Last | Project CAPEX Confidential | Project OPEX Confidential | Project Website | Is Part of a NDP | NDP Number
PRJ-G-001 | Physical Reverse Flow at Moffat interconnection point (IE/UK) | Less-Advanced | TRA-N-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | United Kingdom | GNI (UK) Limited | Advanced | Yes | 5.1.1 (2018) | NSIW | Yes | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | Yes | PCI 5.1.1
PRJ-G-001 | Physical Reverse Flow at Moffat interconnection point (IE/UK) | Less-Advanced | TRA-N-1064 | Moffat Physical Reverse Flow | United Kingdom | National Grid Gas plc | Less-Advanced | Yes | 5.1.1 (2018) | NSIW | Yes | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-002 | Bidirectional Austrian - Czech Interconnection (BACI) | Advanced | TRA-N-21 | Bidirectional Austrian-Czech Interconnector (BACI) | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | Yes | 6.04 (2018) | NSIE | Yes | 2021 | 2021 | Non-Confidential | Non-Confidential | URL | Yes | GCA 2015/01a
PRJ-G-002 | Bidirectional Austrian - Czech Interconnection (BACI) | Advanced | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | Czechia | NET4GAS, s.r.o. | Advanced | Yes | 6.04 (2018) | NSIE | Yes | 2021 | 2021 | Non-Confidential | Non-Confidential | URL | Yes | TRA-N-133
PRJ-G-003 | Interconnection Slovenia-Croatia (Gas pipeline Lučko-Zabok-Rogatec) | Less-Advanced | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Croatia | Plinacro Ltd | Advanced | Yes | 6.26.1.1 (2018) | NSIE | Yes | 2021 | 2021 | Confidential | Confidential | URL | Yes | 1.9, 1.10, 1.11
PRJ-G-003 | Interconnection Slovenia-Croatia (Gas pipeline Lučko-Zabok-Rogatec) | Less-Advanced | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.6 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | C12
PRJ-G-004 | Krk LNG terminal with connecting and evacuation pipelines towards Hungary and beyond | Advanced | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Croatia | Plinacro Ltd | Advanced | Yes | 6.5.6 (2018) | NSIE | Yes | 2020 | 2020 | Confidential | Confidential | URL | Yes | 1.19, 1.20, 1.21
PRJ-G-004 | Krk LNG terminal with connecting and evacuation pipelines towards Hungary and beyond | Advanced | LNG-N-82 | LNG terminal Krk | Croatia | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | Advanced | Yes | 6.5.1 (2018) | NSIE | Yes | 2019 | 2023 | Non-Confidential | Non-Confidential | URL | Yes | LNG terminal on the island of Krk
PRJ-G-004 | Krk LNG terminal with connecting and evacuation pipelines towards Hungary and beyond | Advanced | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Croatia | Plinacro Ltd | Advanced | Yes | 6.5.1 (2018) | NSIE | Yes | 2019 | 2019 | Confidential | Confidential | URL | Yes | 1.18
PRJ-G-004 | Krk LNG terminal with connecting and evacuation pipelines towards Hungary and beyond | Advanced | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Croatia | Plinacro Ltd | Advanced | Yes | 6.5.6 (2018) | NSIE | Yes | 2023 | 2023 | Confidential | Confidential | URL | Yes | 1.32
PRJ-G-005 | CZ/SK Capacity4Gas Project - Capacity increase at IP Lanžhot | FID | TRA-F-918 | Capacity4Gas – CZ/SK | Czechia | NET4GAS, s.r.o. | FID | No |  |  | No | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | Yes | TRA-F-918
PRJ-G-005 | CZ/SK Capacity4Gas Project - Capacity increase at IP Lanžhot | FID | TRA-F-902 | Capacity increase at IP Lanžhot entry | Slovakia | eustream,a.s. (a joint-stock company) | FID | No |  |  | No | 2019 | 2019 | Confidential | Confidential | URL | Yes | 4.1.1.3. Lanžhot
PRJ-G-008 | Poland – Slovakia Gas Interconnection | FID | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | FID | Yes | 6.2.1 (2018) | NSIE | Yes | 2021 | 2021 | Confidential | Confidential | URL | Yes | N/A
PRJ-G-008 | Poland – Slovakia Gas Interconnection | FID | TRA-F-190 | Poland - Slovakia interconnection | Slovakia | eustream,a.s. (a joint-stock company) | FID | Yes | 6.2.1 (2018) | NSIE | Yes | 2021 | 2021 | Confidential | Confidential | URL | Yes | 4.1.1.3.-PL-SK
PRJ-G-010 | Latvia - Lithuania interconnection | Less-Advanced | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | Latvia | JSC "Conexus Baltic Grid" | Advanced | Yes | 8.2.1 (2018) | BEMIP | Yes | 2021 | 2021 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-010 | Latvia - Lithuania interconnection | Less-Advanced | TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | Lithuania | AB Amber Grid | Less-Advanced | Yes | 8.2.1 (2018) | BEMIP | Yes | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | Yes | n/a
PRJ-G-011 | Interconnection Estonia – Finland | FID | TRA-F-895 | Balticconnector | Estonia | Elering AS | FID | Yes | 8.1.1 (2018) | BEMIP | Yes | 2019 | 2019 | Non-Confidential | Non-Confidential | URL | Yes | paragraph 3.3
PRJ-G-011 | Interconnection Estonia – Finland | FID | TRA-F-928 | Balticconnector Finnish part | Finland | Baltic Connector Oy | FID | Yes | 8.1.1 (2018) | BEMIP | Yes | 2019 | 2019 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-012 | Bidirectional flows between Italy and Germany and France through Switzerland | FID | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | France | GRTgaz | FID | No |  |  | No | 2018 | 2018 | Non-Confidential | Non-Confidential | URL | Yes | Création de capacités d’entrée à partir de la Suisse
PRJ-G-012 | Bidirectional flows between Italy and Germany and France through Switzerland | FID | TRA-F-208 | Reverse Flow TENP Germany | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | Yes | 5.01 (2018) | NSIW | No | 2018 | 2018 | Confidential | Confidential | URL | Yes | 305-02
PRJ-G-012 | Bidirectional flows between Italy and Germany and France through Switzerland | FID | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Italy | Snam Rete Gas S.p.A. | FID | Yes | 5.11 (2018) | NSIW | No | 2018 | 2018 | Confidential | Confidential | URL | Yes | RN_01
PRJ-G-012 | Bidirectional flows between Italy and Germany and France through Switzerland | FID | TRA-F-230 | Reverse Flow Transitgas Switzerland | Switzerland | FluxSwiss | FID | No |  |  | No | 2018 | 2018 | Confidential | Confidential | URL | No | N/A
PRJ-G-013 | North Interconnection of BiH and Croatia | Less-Advanced | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Croatia | Plinacro Ltd | Advanced | No |  |  | No | 2020 | 2020 | Confidential | Confidential | URL | Yes | 1.15
PRJ-G-013 | North Interconnection of BiH and Croatia | Less-Advanced | TRA-N-224 | Gaspipeline Brod - Zenica | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | No |  |  | Yes | 2023 | 2023 | Non-Confidential | Non-Confidential | URL | Yes | PTG1
PRJ-G-014 | South Interconnection of BiH and Croatia | Less-Advanced | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Croatia | Plinacro Ltd | Advanced | No |  |  | Yes | 2021 | 2021 | Confidential | Confidential | URL | Yes | 1.13
PRJ-G-014 | South Interconnection of BiH and Croatia | Less-Advanced | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | Bosnia Herzegovina | BH-GAS d.o.o. | Less-Advanced | No |  |  | No | 2023 | 2023 | Non-Confidential | Non-Confidential | URL | Yes | PTG2
PRJ-G-015 | West Interconnection of BiH and Croatia | Less-Advanced | TRA-N-910 | West Interconnection BiH/CRO | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | No |  |  | No | 2026 | 2026 | Non-Confidential | Non-Confidential | URL | Yes | PTG4
PRJ-G-015 | West Interconnection of BiH and Croatia | Less-Advanced | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Croatia | Plinacro Ltd | Less-Advanced | No |  |  | No | 2027 | 2027 | Confidential | Confidential | URL | Yes | 1.35 and 1.36
PRJ-G-017 | Gas Interconnection Poland-Lithuania (GIPL) | FID | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | Lithuania | AB Amber Grid | FID | Yes | 8.05 (2018) | BEMIP | Yes | 2021 | 2021 | Non-Confidential | Non-Confidential | URL | Yes | n/a
PRJ-G-017 | Gas Interconnection Poland-Lithuania (GIPL) | FID | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | Poland | GAZ-SYSTEM S.A. | FID | Yes | 8.05 (2018) | BEMIP | Yes | 2021 | 2021 | Confidential | Confidential | URL | Yes | N/A
PRJ-G-018 | Additional capacity at Oude Statenzijl from Germany to the Netherlands | Less-Advanced | TRA-N-808 | Transport of gas volumes to the Netherlands | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  |  | No | 2025 | 2025 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-018 | Additional capacity at Oude Statenzijl from Germany to the Netherlands | Less-Advanced | TRA-N-873 | Additional capacity at OSZ from Germany to the Netherlands | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  |  | No | 2025 | 2025 | Non-Confidential | Non-Confidential | URL | Yes | 6.5.4.
PRJ-G-021 | Baltic Pipe Project | Advanced | TRA-N-780 | Baltic Pipe project – onshore section in Denmark | Denmark | Energinet.dk | Advanced | Yes | 8.3.1 (2018) | BEMIP | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-021 | Baltic Pipe Project | Advanced | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 8.3.2 (2018) | BEMIP | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | N/A
PRJ-G-021 | Baltic Pipe Project | Advanced | TRA-N-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 8.3.2 (2018) | BEMIP | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | N/A
PRJ-G-022 | Poland - Czech Republic Interconnection | Advanced | TRA-N-136 | Czech-Polish Gas Interconnector (CPI) | Czechia | NET4GAS, s.r.o. | Advanced | Yes | 6.2.10 (2018) 6.2.12 (2018) | NSIE | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | TRA-N-136
PRJ-G-022 | Poland - Czech Republic Interconnection | Advanced | TRA-N-273 | Poland - Czech Republic Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 6.2.10 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | N/A
PRJ-G-023 | PRJ LNG Terminal Brunsbuettel | Less-Advanced | LNG-N-1198 | LNG Terminal Brunsbuettel | Germany | Gasunie Deutschland Transport Service GmbH | Less-Advanced | No |  |  | No | 2021 | 2021 | Confidential | Confidential | URL | No | N/A
PRJ-G-023 | PRJ LNG Terminal Brunsbuettel | Less-Advanced | TRA-N-1199 | LNG Terminal Brunsbuettel - Grid Integration | Germany | Gasunie Deutschland Transport Service GmbH | Less-Advanced | No |  |  | No | 2021 | 2021 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-028 | Poland - Ukraine Gas Interconnection | Advanced | TRA-N-621 | Poland - Ukraine Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced | No |  |  | No | 2020 | 2020 | Confidential | Confidential | URL | Yes | N/A
PRJ-G-028 | Poland - Ukraine Gas Interconnection | Advanced | TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | Ukraine | PJSC UKRTRANSGAZ | Advanced | No |  |  | No | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-030 | Transferring L-gas infrastructure to H-gas | Less-Advanced | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Germany | Gastransport Nord GmbH | Less-Advanced | No |  |  | No | 2024 | 2027 | Confidential | Confidential | URL | Yes | 432-01
PRJ-G-030 | Transferring L-gas infrastructure to H-gas | Less-Advanced | TRA-N-951 | Embedding CS Folmhusen in H-Gas | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  |  | No | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | Yes | ID 300-02
PRJ-G-030 | Transferring L-gas infrastructure to H-gas | Less-Advanced | TRA-N-955 | GUD: Complete conversion to H-gas | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  |  | No | 2018 | 2030 | Non-Confidential | Non-Confidential | URL | Yes | ID 221-01 ID; ID 222-02; ID 223-01
PRJ-G-030 | Transferring L-gas infrastructure to H-gas | Less-Advanced | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  |  | No | 2020 | 2030 | Non-Confidential | Non-Confidential | URL | Yes | 6.5.1
PRJ-G-034 | More capacity – DE/CZ Capacity4Gas Project | Advanced | TRA-F-752 | Capacity4Gas – DE/CZ | Czechia | NET4GAS, s.r.o. | FID | No |  |  | No | 2019 | 2021 | Non-Confidential | Non-Confidential | URL | Yes | TRA-F-752
PRJ-G-034 | More capacity – DE/CZ Capacity4Gas Project | Advanced | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | Germany | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | Advanced | No |  |  | No | 2019 | 2020 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-034 | More capacity – DE/CZ Capacity4Gas Project | Advanced | TRA-N-809 | Additional East-West transport | Germany | Gasunie Deutschland Transport Services GmbH | Advanced | No |  |  | No | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-034 | More capacity – DE/CZ Capacity4Gas Project | Advanced | TRA-N-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | Germany | ONTRAS Gastransport GmbH | Advanced | No |  |  | No | 2019 | 2019 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | Portugal | REN-Gasodutos, S.A. | Advanced | Yes | 5.4.1 (2018) | NSIW | Yes | 2024 | 2024 | Non-Confidential | Non-Confidential | URL | Yes | -
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | Portugal | REN-Gasodutos, S.A. | Less-Advanced | Yes | 5.4.2. (2018) | NSIW | Yes | 2028 | 2028 | Non-Confidential | Non-Confidential | URL | Yes | -
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | Portugal | REN-Gasodutos, S.A. | Less-Advanced | Yes | 5.4.2. (2018) | NSIW | Yes | 2028 | 2028 | Non-Confidential | Non-Confidential | URL | Yes | -
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Spain | Enagás Transporte, S.A.U. | Less-Advanced | Yes | 5.4.1 (2018) | NSIW | Yes | 2024 | 2024 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-036 | Interconnection ES-PT (3rd interconnection) | Less-Advanced | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Spain | Enagás Transporte, S.A.U. | Less-Advanced | Yes | 5.4.2. (2018) | NSIW | Yes | 2028 | 2028 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-039 | STEP (South Transit East Pyrenees) | Advanced | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | France | TIGF | Advanced | Yes | 5.5.1 (2018) | NSIW | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | No number
PRJ-G-039 | STEP (South Transit East Pyrenees) | Advanced | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Spain | Enagás Transporte, S.A.U. | Advanced | Yes | 5.5.1 (2018) | NSIW | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | No code in the NDP
PRJ-G-041 | Pipeline system from Bulgaria via Romania and Hungary to Slovakia [currently known as "Eastring“ | Less-Advanced | TRA-N-628 | Eastring - Slovakia | Slovakia | eustream, a.s. (a joint stock company) | Advanced | Yes | 6.25.1 (2018) | NSIE | Yes | 2023 | 2028 | Confidential | Confidential | URL | Yes | 4.1.1.3. Eastring
PRJ-G-041 | Pipeline system from Bulgaria via Romania and Hungary to Slovakia [currently known as "Eastring“ | Less-Advanced | TRA-N-654 | Eastring - Bulgaria | Bulgaria | Bulgartransgaz EAD | Less-Advanced | Yes | 6.25.1 (2018) | NSIE | Yes | 2023 | 2028 | Confidential | Confidential | URL | Yes | Section 5.1(5.1,2)
PRJ-G-041 | Pipeline system from Bulgaria via Romania and Hungary to Slovakia [currently known as "Eastring“ | Less-Advanced | TRA-N-656 | Eastring - Hungary | Hungary | FGSZ Ltd. | Less-Advanced | Yes | 6.25.1 (2018) | NSIE | Yes | 2023 | 2028 | Confidential | Confidential | URL | Yes | 12.13.
PRJ-G-041 | Pipeline system from Bulgaria via Romania and Hungary to Slovakia [currently known as "Eastring“ | Less-Advanced | TRA-N-655 | Eastring - Romania | Romania | SNTGN Transgaz SA | Less-Advanced | Yes | 6.25.1 (2018) | NSIE | Yes | 2023 | 2028 | Confidential | Confidential | URL | No | N/A
PRJ-G-044 | MidCat (Iberian-French corridor, Eastern Axis – MidCat project) | Advanced | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | France | GRTgaz and TIGF | Advanced | Yes | 5.5.2 (2018) | NSIW | Yes | 2024 | 2024 | Non-Confidential | Confidential | URL | Yes | Augmentation des capacités d’interconnexion entre la France et l’Espagne
PRJ-G-044 | MidCat (Iberian-French corridor, Eastern Axis – MidCat project) | Advanced | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Spain | Enagás Transporte, S.A.U. | Advanced | Yes | 5.5.2 (2018) | NSIW | Yes | 2024 | 2024 | Non-Confidential | Non-Confidential | URL | Yes | No code in the NDP
PRJ-G-045 | Enhancement of the capacity at SK-HU interconnector | Less-Advanced | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Hungary | Magyar Gáz Tranzit Zrt. | Less-Advanced | Yes | 6.2.13 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | TRA-N-524 (new nr will be received once project is approved)
PRJ-G-045 | Enhancement of the capacity at SK-HU interconnector | Less-Advanced | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Hungary | Magyar Gáz Tranzit Zrt. | Less-Advanced | Yes | 6.2.13 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | TRA-N-636
PRJ-G-045 | Enhancement of the capacity at SK-HU interconnector | Less-Advanced | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | Slovakia | eustream,a.s. (a joint-stock company) | Less-Advanced | No |  |  | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | 4.1.1.3 Firm transmission capacity increase at the IP Veľké Zlievce
PRJ-G-046 | Creation of a single gas market area in France | FID | TRA-F-43 | Val de Saône project | France | GRTgaz | FID | No |  |  | No | 2018 | 2018 | Non-Confidential | Non-Confidential | URL | Yes | Fusion des zones
PRJ-G-046 | Creation of a single gas market area in France | FID | TRA-F-331 | Gascogne Midi | France | TIGF - GRTgaz | FID | No |  |  | No | 2018 | 2018 | Confidential | Confidential | URL | Yes | No number
PRJ-G-047 | RO-HU Transmission Corridor | Advanced | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | Hungary | FGSZ Ltd. | FID | Yes | 6.24.1.1 (2018) | NSIE | Yes | 2019 | 2019 | Confidential | Confidential | URL | Yes | 12.1.
PRJ-G-047 | RO-HU Transmission Corridor | Advanced | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | Hungary | FGSZ Ltd. | Advanced | Yes | 6.24.4.6 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | 12.1.
PRJ-G-049 | Fos Cavaou LNG Terminal Expansion | Less-Advanced | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | France | Fosmax LNG | Less-Advanced | No |  |  | No | 2021 | 2023 | Confidential | Confidential | URL | Yes | Fos Cavaou Extension
PRJ-G-049 | Fos Cavaou LNG Terminal Expansion | Less-Advanced | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | France | GRTgaz | Less-Advanced | No |  |  | No | 2023 | 2023 | Non-Confidential | Confidential | URL | Yes | Extension du terminal de Fos Cavaou à 16,5 Gm³/an
PRJ-G-050 | Montoir LNG Terminal Expansion | Less-Advanced | LNG-N-225 | Montoir LNG Terminal Expansion | France | Elengy | Less-Advanced | No |  |  | No | 2021 | 2021 | Confidential | Confidential | URL | Yes | Montoir Extension
PRJ-G-050 | Montoir LNG Terminal Expansion | Less-Advanced | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | France | GRTgaz | Less-Advanced | No |  |  | No | 2023 | 2023 | Non-Confidential | Non-Confidential | URL | Yes | Augmentation des capacités d’entrée à partir du terminal de Montoir de 10 à 12,5 Gm³/an
PRJ-G-054 | LNG | Less-Advanced | LNG-N-50 | Gate terminal phase 3 | Netherlands | Gate | Less-Advanced | No |  |  | No | 2020 | 2020 | Confidential | Confidential | URL | Yes | unknown see GTS
PRJ-G-054 | LNG | Less-Advanced | TRA-N-192 | Entry capacity expansion GATE terminal | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  |  | No | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | Yes | 6.5.2
PRJ-G-055 | LNG terminal in northern Greece / Alexandroupolis | Advanced | LNG-N-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Greece | Gastrade S.A. | Advanced | Yes | 6.9.1 (2018) | NSIE | Yes | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-055 | LNG terminal in northern Greece / Alexandroupolis | Advanced | TRA-N-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Greece | Gastrade S.A. | Advanced | Yes | 6.9.1 (2018) | NSIE | Yes | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | No | N/A
PRJ-G-056 | New UGS in Cornegliano Laudense (IT) | FID | UGS-F-242 | Cornegliano UGS | Italy | ITAL Gas Storage | FID | No |  |  | Yes | 2018 | 2018 | Confidential | Confidential | URL | Yes | RN_10
PRJ-G-056 | New UGS in Cornegliano Laudense (IT) | FID | TRA-F-1228 | Interconnection with UGS in Cornegliano Laudense | Italy | Snam Rete Gas S.p.A. | FID | No |  |  | No | 2018 | 2018 | Confidential | Confidential | URL | Yes | RN_10
PRJ-G-060 | Hungary – Slovenia interconnection | Less-Advanced | TRA-N-325 | Slovenian-Hungarian interconnector | Hungary | FGSZ Ltd. | Advanced | Yes | 6.23 (2018) | NSIE | Yes | 2022 | 2023 | Confidential | Confidential | URL | Yes | 12.12.
PRJ-G-060 | Hungary – Slovenia interconnection | Less-Advanced | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.23 (2018) | NSIE | Yes | 2022 | 2023 | Confidential | Confidential | URL | Yes | C3
|  |  | TRA-F-1028 | Albania - Kosovo Gas Pipeline | Albania | Min. of Infrastructure and Energy AL & Min. of Economic Development KO | FID | No |  |  | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | Map no. 3.27, page 145
|  |  | TRA-F-954 | TAG Reverse Flow | Austria | Trans Austria Gasleitung GmbH | FID | No |  |  | No | 2019 | 2019 | Confidential | Confidential | URL | Yes | TAG 2016-01
|  |  | TRA-F-1138 | South Caucasus Pipeline - (Future) Expansion - SCP-(F)X | Azerbaijan | SOCAR Midstream Operations LLC | FID | Yes | 7.1.1 (2018) | SGC | Yes | 2018 | 2018 | Confidential | Confidential | URL | No | N/A
|  |  | LNG-F-229 | Zeebrugge LNG Terminal - 5th Tank | Belgium | Fluxys LNG | FID | No |  |  | No | 2019 | 2019 | Confidential | Confidential | URL | Yes | Zeebrugge LNG Terminal - 5th Tank
|  |  | TRA-F-137 | Interconnection Bulgaria - Serbia | Bulgaria | Ministry of Energy | FID | Yes | 6.10 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | Sectin 5.2 (5.2.3)
|  |  | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgaria | Bulgartransgaz EAD | FID | Yes | 6.8.2 (2018) | NSIE | Yes | 2021 | 2024 | Non-Confidential | Confidential | URL | Yes | Section 5.5.
|  |  | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | Bulgaria | ICGB a.d. | FID | Yes | 6.8.1 (2018) | NSIE | Yes | 2020 | 2025 | Non-Confidential | Non-Confidential | URL | Yes | not applicable
|  |  | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Croatia | Plinacro Ltd | FID | Yes | 6.5.5 (2018) | NSIE | Yes | 2019 | 2019 | Confidential | Confidential | URL | Yes | 5.1
|  |  | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Estonia | Elering AS | FID | Yes | 8.2.2 (2018) | BEMIP | Yes | 2019 | 2019 | Non-Confidential | Non-Confidential | URL | Yes | paragraph 3.3
|  |  | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | Germany | bayernets GmbH | FID | No |  |  | No | 2018 | 2018 | Non-Confidential | Confidential | URL | Yes | 030-02a, 030-02b
|  |  | TRA-F-329 | ZEELINK | Germany | Open Grid Europe GmbH and Thyssengas GmbH | FID | No |  |  | No | 2023 | 2023 | Non-Confidential | Confidential | URL | Yes | 204-02a, 205-02a, 416/02,
|  |  | TRA-F-340 | CS Wertingen | Germany | bayernets GmbH | FID | No |  |  | No | 2019 | 2019 | Non-Confidential | Confidential | URL | Yes | 036-04
|  |  | TRA-F-937 | Nord Stream 2 | Germany | Nord Stream 2 AG | FID | No |  |  | No | 2019 | 2019 | Non-Confidential | Confidential | URL | No | N/A
|  |  | TRA-F-1271 | Compressor Station Krummhoern | Germany | Open Grid Europe GmbH | FID | No |  |  | No | 2022 | 2022 | Non-Confidential | Confidential | URL | Yes | 414-01 an 415-01
|  |  | TRA-F-51 | Trans Adriatic Pipeline | Greece | Trans Adriatic Pipeline AG | FID | Yes | 7.1.3 (2018) | SGC | Yes | 2019 | 2019 | Confidential | Confidential | URL | No | N/A
|  |  | LNG-F-147 | Revythoussa (2nd upgrade) | Greece | DESFA S.A. | FID | No |  |  | No | 2018 | 2018 | Non-Confidential | Non-Confidential | URL | Yes | 2.2.1.7
|  |  | TRA-F-941 | Metering and Regulating station at Nea Messimvria | Greece | DESFA S.A. | FID | Yes | 7.1.3 (2018) | SGC | Yes | 2019 | 2019 | Non-Confidential | Confidential | URL | Yes | 2.2.1.5
|  |  | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Italy | STOGIT | FID | No |  |  | No | 2027 | 2027 | Confidential | Confidential | URL | Yes | NA
|  |  | UGS-F-1045 | Bordolano Second phase | Italy | STOGIT S.p.A. | FID | No |  |  | No | 2020 | 2020 | Confidential | Confidential | URL | Yes | NA
|  |  | TRA-F-1241 | Interconnection with production in Gela | Italy | Snam Rete Gas S.p.A. | FID | No |  |  | No | 2020 | 2020 | Confidential | Confidential | URL | No | N/A
|  |  | TRA-F-247 | North - South Gas Corridor in Western Poland | Poland | GAZ-SYSTEM S.A. | FID | Yes | 6.2.11 (2018) | NSIE | Yes | 2020 | 2020 | Confidential | Confidential | URL | Yes | N/A
|  |  | LNG-F-272 | Upgrade of LNG terminal in Świnoujście | Poland | GAZ-SYSTEM S.A. | FID | Yes | 8.07 (2018) | BEMIP | Yes | 2023 | 2023 | Confidential | Confidential | URL | Yes | N/A
|  |  | LNG-F-163 | Gran Canaria LNG Terminal | Spain | Gascan | FID | No |  |  | No | 2027 | 2027 | Non-Confidential | Non-Confidential | URL | Yes | No code in the NDP
|  |  | LNG-F-178 | Musel LNG terminal | Spain | Enagás Transporte, S.A.U. | FID | No |  |  | No | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | Yes | No code in the NDP
|  |  | LNG-F-183 | Tenerife LNG Terminal | Spain | Gascan | FID | No |  |  | No | 2021 | 2021 | Non-Confidential | Non-Confidential | URL | Yes | No code in the NDP
|  |  | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | Turkey | SOCAR (The State Oil Company of the Azerbaijan Republic) | FID | Yes | 7.1.1 (2018) | SGC | Yes | 2018 | 2019 | Non-Confidential | Confidential | URL | No | N/A
|  |  | UGS-N-1229 | Underground Natural Gas Storage in Dumrea Area (UGS Dumrea) | Albania | Ministry of Infrastructure and Energy of Albania and Albgaz sh.a. | Advanced | No |  |  | Yes | 2024 | 2024 | Confidential | Confidential | URL | Yes | Map no. 3.27; page no. 145
|  |  | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | Yes | 6.26.1.4 (2018) | NSIE | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | GCA 2015/08
|  |  | TRA-N-423 | GCA Mosonmagyaróvár | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | Yes | 6.24.1.3 (2018) | NSIE | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | GCA 2015/05
|  |  | TRA-N-500 | L/H Conversion Belgium | Belgium | Fluxys Belgium | Advanced | Yes | 5.21 (2018) | NSIW | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | L/H Conversion
|  |  | UGS-N-138 | UGS Chiren Expansion | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.20.2 (2018) | NSIE | Yes | 2024 | 2024 | Non-Confidential | Confidential | URL | Yes | Section 5.3 (5.3.1)
|  |  | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.25.4 (2018) | NSIE | Yes | 2022 | 2022 | Non-Confidential | Confidential | URL | Yes | Section 5.1. (5.1.1)
|  |  | TRA-N-593 | Varna-Oryahovo gas pipeline | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.25.4 (2018) | NSIE | Yes | 2022 | 2022 | Non-Confidential | Confidential | URL | Yes | Section 5.1. (5.1.1)
|  |  | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.25.4 (2018) | NSIE | Yes | 2022 | 2022 | Non-Confidential | Confidential | URL | Yes | Section 5.1. (5.1.1)
|  |  | TRA-N-68 | Ionian Adriatic Pipeline | Croatia | Plinacro Ltd | Advanced | No |  |  | Yes | 2022 | 2023 | Confidential | Confidential | URL | Yes | 1.12, 1.25-1.27, 5.5
|  |  | TRA-N-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Croatia | Plinacro Ltd | Advanced | No |  |  | No | 2023 | 2023 | Confidential | Confidential | URL | Yes | 1.30, 1.31
|  |  | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Croatia | Plinacro Ltd | Advanced | Yes | 6.26.1.3 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | 5.3 and 5.4
|  |  | LNG-N-1146 | Cyprus Gas2EU | Cyprus | Ministry of Energy, Commerce, Industry and Tourism | Advanced | Yes | 7.05 (2018) | SGC | Yes | 2020 | 2020 | Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-394 | Norwegian tie-in to Danish upstream system | Denmark | Energinet.dk | Advanced | No |  |  | No | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | No | N/A
|  |  | LNG-N-962 | Tallinn LNG | Estonia | Vopak E.O.S. AS / Vopak LNG Holdings B.V/ Port of Tallinn AS | Advanced | No |  |  | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | Paragraph 3 point 7
|  |  | TRA-N-291 | NOWAL - Nord West Anbindungsleitung | Germany | GASCADE Gastransport GmbH | Advanced | No |  |  | No | 2018 | 2020 | Non-Confidential | Non-Confidential | URL | Yes | (already completed: 083-07, 409-01), 410-01 (older version compared to current draft NDP)
|  |  | TRA-N-1267 | Upgrade Sülstorf station | Germany | NGT GmbH / GUD GmbH & Co. KG / Fluxys D GmbH / ONTRAS GmbH | Advanced | No |  |  | No | 2019 | 2019 | Non-Confidential | Non-Confidential | URL | No | N/A
|  |  | TRA-N-10 | Poseidon Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | Yes | 7.3.3 (2018) | SGC | Yes | 2022 | 2025 | Non-Confidential | Non-Confidential | URL | Yes | n.a.
|  |  | TRA-N-123 | Városföld CS | Hungary | FGSZ Ltd. | Advanced | Yes | 6.24.4.3 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | 12.2.
|  |  | LNG-N-30 | Shannon LNG Terminal and Connecting Pipeline | Ireland | Shannon LNG Ltd | Advanced | Yes | 5.03 (2018) | NSIW | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | 3.3
|  |  | TRA-N-12 | GALSI Pipeline Project | Italy | Galsi S.p.A. | Advanced | No |  |  | Yes | 2019 | 2019 | Confidential | Confidential | URL | Yes | n.a.
|  |  | LNG-N-198 | Porto Empedocle LNG | Italy | Nuove Energie S.r.l. | Advanced | No |  |  | Yes | 2021 | 2021 | Confidential | Confidential | URL | Yes | RN_12
|  |  | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Italy | Società Gasdotti Italia | Advanced | No |  |  | No | 2022 | 2022 | Non-Confidential | Confidential | URL | Yes | Dorsale Larino Recanati
|  |  | TRA-N-975 | Sardinia Gas Transportation Network | Italy | Società Gasdotti Italia | Advanced | No |  |  | No | 2020 | 2021 | Non-Confidential | Confidential | URL | Yes | Metanizzazione della regione Sardegna
|  |  | UGS-N-374 | Enhancement of Incukalns UGS | Latvia | JSC "Conexus Baltic Grid" | Advanced | Yes | 8.2.4 (2018) | BEMIP | Yes | 2020 | 2024 | Non-Confidential | Non-Confidential | URL | No | N/A
|  |  | TRA-N-31 | Connection of Malta to the European Gas Network - Pipelines | Malta | Ministry For Energy & Water Management - Malta | Advanced | Yes | 5.19 (2018) | NSIW | Yes | 2024 | 2024 | Non-Confidential | Non-Confidential | URL | Yes | Section 4.3.2
|  |  | TRA-N-320 | Carregado Compressor Station | Portugal | REN-Gasodutos, S.A. | Advanced | No |  |  | No | 2024 | 2024 | Non-Confidential | Non-Confidential | URL | Yes | -
|  |  | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.24.10.1 (2018) | NSIE | Yes | 2019 | 2019 | Non-Confidential | Non-Confidential | URL | Yes | 7.3
|  |  | UGS-N-233 | Depomures | Romania | Engie Romania SA | Advanced | Yes | 6.20.4 (2018) | NSIE | Yes | 2020 | 2023 | Non-Confidential | Non-Confidential | URL | No | N/A
|  |  | TRA-N-357 | NTS developments in North-East Romania | Romania | SNTGN Transgaz SA | Advanced | No |  |  | No | 2019 | 2019 | Non-Confidential | Non-Confidential | URL | Yes | 7.4
|  |  | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.24.4.5 (2018) | NSIE | Yes | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | Yes | 7.2
|  |  | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.24.10.3 (2018) | NSIE | No | 2019 | 2019 | Non-Confidential | Non-Confidential | URL | Yes | 7.6
|  |  | TRA-N-1268 | Romania-Serbia Interconnection | Romania | SNTGN Tranzgaz SA | Advanced | No |  |  | No | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | Yes | 7.7
|  |  | TRA-N-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | Romania | SNTGN Transgaz SA | Advanced | No |  |  | No | 2019 | 2019 | Non-Confidential | Non-Confidential | URL | Yes | 7.8
|  |  | UGS-N-356 | Underground Gas Storage Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | Advanced | No |  |  | Yes | 2023 | 2023 | Non-Confidential | Non-Confidential | URL | Yes | chapter 3.3
|  |  | LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | Spain | Reganosa | Advanced | No |  |  | No | 2020 | 2020 | Confidential | Confidential | URL | No | N/A
|  |  | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Spain | Reganosa | Advanced | No |  |  | No | 2022 | 2022 | Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-950 | Guitiriz - Lugo - Zamora pipeline | Spain | Reganosa | Advanced | No |  |  | Yes | 2020 | 2020 | Non-Confidential | Non-Confidential | URL | Yes | N/A.
|  |  | LNG-N-32 | Project GO4LNG LNG terminal Gothenburg | Sweden | Swedegas AB | Advanced | Yes | 8.06 (2018) | BEMIP | Yes | 2020 | 2020 | Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-339 | Trans-Caspian | Turkmenistan | W-Stream Caspian Pipeline Company Ltd | Advanced | Yes | 7.1.1 (2018) | SGC | Yes | 2021 | 2022 | Non-Confidential | Non-Confidential | URL | No | N/A
|  |  | UGS-N-294 | Islandmagee Gas Storage Facility | United Kingdom | Islandmagee Storage Limited | Advanced | Yes | 5.1.3 (2018) | NSIW | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | n.a.
|  |  | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | Romania | SNTGN Transgaz S.A. | FID* | Yes | 6.24.1.2 (2018) | NSIE | Yes | 2020 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | 7.1
|  |  | TRA-F-1193 | TAP interconnection | Italy | Snam Rete Gas S.p.A. | FID** | No |  |  | Yes | 2019 | 2019 | Non-Confidential | Non-Confidential | URL | Yes | RN_02
|  |  | TRA-N-1303 | IAEF - Vlora ccgt | Albania | Albgaz Sha | Less-Advanced | No |  |  | Yes | 2020 | 2020 | Confidential | Confidential | URL | Yes | PiP1
|  |  | LNG-N-742 | Zeebrugge LNG Terminal - 3rd Jetty | Belgium | Fluxys LNG | Less-Advanced | No |  |  | No | 2023 | 2023 | Confidential | Confidential | URL | Yes | Zeebrugge LNG Terminal - 3rd Jetty
|  |  | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgaria | Bulgartransgaz EAD | Less-Advanced | No |  |  | Yes | 2022 | 2022 | Non-Confidential | Confidential | URL | Yes | ITB
|  |  | TRA-N-1197 | Expansion of the gas infrastructure between BG-TR and BG-RS borders | Bulgaria | Bulgartransgaz EAD | Less-Advanced | No |  |  | Yes | 2020 | 2022 | Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Croatia | Plinacro Ltd | Less-Advanced | No |  |  | No | 2027 | 2027 | Confidential | Confidential | URL | Yes | 1.37
|  |  | LNG-N-79 | Paldiski LNG Terminal | Estonia | Balti Gaas plc | Less-Advanced | No |  |  | Yes | 2025 | 2025 | Non-Confidential | Non-Confidential | URL | Yes | -
|  |  | TRA-N-965 | Interconnection Macedonia-Serbia | former Yugoslav Republic of Macedonia | MER JSC Skopje | Less-Advanced | No |  |  | No | 2021 | 2021 | Confidential | Confidential | URL | Yes | N/A
|  |  | TRA-N-976 | Interconnection Macedonia-Bulgaria | former Yugoslav Republic of Macedonia | MER JSC Skopje | Less-Advanced | No |  |  | No | 2021 | 2021 | Confidential | Confidential | URL | Yes | N/A
|  |  | TRA-N-980 | Interconnection Macedonia-Greece | former Yugoslav Republic of Macedonia | MER JSC Skopje | Less-Advanced | No |  |  | No | 2020 | 2020 | Confidential | Confidential | URL | Yes | N/A
|  |  | TRA-N-47 | Reverse capacity from France to Germany at Obergailbach | France | GRTgaz | Less-Advanced | No |  |  | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | na
|  |  | TRA-N-429 | Adaptation L- gas - H-gas | France | GRTgaz and Storengy | Less-Advanced | Yes | 5.21 (2018) | NSIW | Yes | 2025 | 2025 | Non-Confidential | Non-Confidential | URL | Yes | Plan de conversion du gaz B en gaz H
|  |  | TRA-N-53 | White Stream | Georgia | White Stream Ltd | Less-Advanced | No |  |  | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | No | N/A
|  |  | TRA-N-755 | CS Rimpar | Germany | GRTgaz Deutschland GmbH | Less-Advanced | No |  |  | No | 2023 | 2023 | Non-Confidential | Confidential | URL | Yes | 312-01
|  |  | TRA-N-1200 | Expansion MS Hetlingen | Germany | Gasunie Deutschland Transport Service GmbH | Less-Advanced | No |  |  | No | 2019 | 2022 | Non-Confidential | Non-Confidential | URL | No | N/A
|  |  | TRA-N-1254 | CS Elten | Germany | Open Grid Europe GmbH and Thyssengas GmbH | Less-Advanced | No |  |  | No | 2022 | 2022 | Non-Confidential | Confidential | URL | Yes | 422/01
|  |  | TRA-N-14 | Komotini-Thesprotia pipeline | Greece | DESFA S.A. | Less-Advanced | No |  |  | Yes | 2024 | 2024 | Non-Confidential | Confidential | URL | Yes | 2.2.1.6
|  |  | TRA-N-128 | Compressor Station Kipi | Greece | DESFA S.A. | Less-Advanced | Yes | 6.8.1 (2018) | NSIE | Yes | 2020 | 2020 | Non-Confidential | Confidential | URL | Yes | 2.2.1.3
|  |  | TRA-N-330 | EastMed Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced | Yes | 7.3.1 (2018) | SGC | Yes | 2025 | 2025 | Non-Confidential | Non-Confidential | URL | No | N/A
|  |  | UGS-N-385 | South Kavala Underground Gas Storage facility | Greece | Hellenic Republic Asset anagement Fund | Less-Advanced | No |  |  | Yes | 2023 | 2023 | Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-967 | Nea-Messimvria to FYRoM pipeline | Greece | DESFA S.A. | Less-Advanced | No |  |  | Yes | 2021 | 2021 | Non-Confidential | Confidential | URL | Yes | 2.1.2.2
|  |  | TRA-N-971 | Compressor station at Nea Messimvria | Greece | DESFA S.A. | Less-Advanced | Yes | 7.1.3 (2018) | SGC | Yes | 2022 | 2022 | Non-Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | Greece | DESFA S.A. | Less-Advanced | Yes | 6.9.1 | NSIE | Yes | 2020 | 2020 | Non-Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-1091 | Metering and Regulating station at Megalopoli | Greece | DESFA S.A. | Less-Advanced | Yes | 7.3.1 (2018) | SGC | Yes | 2025 | 2025 | Non-Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | Greece | DESFA S.A. | Less-Advanced | Yes | 6.20.3 (2018) | NSIE | Yes | 2023 | 2023 | Non-Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-1129 | Compressor Station Kipi Increment | Greece | DESFA S.A. | Less-Advanced | No |  |  | Yes | 2024 | 2024 | Non-Confidential | Non-Confidential | URL | Yes | 2.2.1.3
|  |  | TRA-N-1276 | Compressor station at Nea Messimvria (3rd unit) | Greece | DESFA S.A. | Less-Advanced | No |  |  | Yes | 2021 | 2021 | Non-Confidential | Non-Confidential | URL | Yes | 2.1.2.9
|  |  | TRA-N-1278 | Compressor station at Ambelia | Greece | DESFA S.A. | Less-Advanced | No |  |  | Yes | 2022 | 2022 | Non-Confidential | Non-Confidential | URL | Yes | 2.1.2.3
|  |  | TRA-N-831 | Vecsés-Városföld gas transit pipeline | Hungary | Magyar Gáz Tranzit Zrt. | Less-Advanced | Yes | 6.2.14 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | TRA-N-831
|  |  | TRA-N-71 | Physical Reverse Flow on South North Pipeline | Ireland | Gas Networks Ireland | Less-Advanced | No |  |  | Yes | 2023 | 2023 | Non-Confidential | Non-Confidential | URL | Yes | N/A
|  |  | LNG-N-1231 | Inisfree LNG | Ireland | NextDecade LNG | Less-Advanced | No |  |  | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | CER17278
|  |  | TRA-N-7 | Development for new import from the South (Adriatica Line) | Italy | Snam Rete Gas S.p.A. | Less-Advanced | Yes | 7.3.4 (2018) | SGC | Yes | 2025 | 2025 | Non-Confidential | Non-Confidential | URL | Yes | RN_04
|  |  | TRA-N-8 | Import developments from North-East | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | No | 2034 | 2034 | Confidential | Confidential | URL | Yes | RN_06
|  |  | TRA-N-9 | Additional Southern developments | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | No | 2034 | 2034 | Confidential | Confidential | URL | Yes | RN_07
|  |  | TRA-N-354 | Interconnection with Slovenia | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | No | 2023 | 2023 | Confidential | Confidential | URL | Yes | RN_03
|  |  | TRA-N-1194 | Sardinia Methanization | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | No | 2020 | 2025 | Confidential | Confidential | URL | Yes | RN_09
|  |  | TRA-N-1195 | Matagiola - Massafra pipeline | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | Yes | 2025 | 2025 | Non-Confidential | Non-Confidential | URL | Yes | RN_05
|  |  | TRA-N-1227 | Gorizia plant upgrade | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | Yes | 2022 | 2022 | Non-Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-1246 | Greece - Italy interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | No | 2025 | 2025 | Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-1265 | Biomethane productions interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | No | 2022 | 2022 | Confidential | Confidential | URL | No | N/A
|  |  | LNG-N-912 | Skulte LNG | Latvia | AS Skulte LNG Terminal | Less-Advanced | No |  |  | Yes | 2021 | 2021 | Non-Confidential | Non-Confidential | URL | No | N/A
|  |  | LNG-N-824 | LNG Terminal in Klaipeda | Lithuania | AB Klaipėdos Nafta | Less-Advanced | No |  |  | Yes | 2024 | 2024 | Confidential | Non-Confidential | URL | No | N/A
|  |  | TRA-N-1253 | Trans-Balkan Bi-directional Flow (Moldavia phase) | Moldavia | Moldovatransgaz LLC | Less-Advanced | No |  |  | Yes | 2019 | 2019 | Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-245 | North - South Gas Corridor in Eastern Poland | Poland | GAZ-SYSTEM S.A. | Less-Advanced | Yes | 6.2.2 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | N/A
|  |  | UGS-N-914 | UGS Damasławek | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  |  | No | 2026 | 2026 | Confidential | Confidential | URL | Yes | N/A
|  |  | LNG-N-947 | FSRU Polish Baltic Sea Coast | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  |  | No | 2022 | 2022 | Confidential | Confidential | URL | Yes | N/A
|  |  | TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  |  | No | 2022 | 2022 | Confidential | Confidential | URL | No | N/A
|  |  | UGS-N-371 | Sarmasel undeground gas storage in Romania | Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced | Yes | 6.20.6 (2018) | NSIE | Yes | 2024 | 2024 | Confidential | Confidential | URL | No | N/A
|  |  | LNG-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | Romania | AGRI LNG Project Company SRL (RO) | Less-Advanced | No |  |  | Yes | 2026 | 2026 | Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | Romania | SNTGN Transgaz SA | Less-Advanced | Yes | 6.24.10.2 (2018) | NSIE | Yes | 2023 | 2023 | Non-Confidential | Non-Confidential | URL | Yes | 7.5
|  |  | TRA-N-17 | System Enhancements - Eustream | Slovakia | eustream, a.s. | Less-Advanced | No |  |  | No | 2027 | 2027 | Confidential | Confidential | URL | Yes | 4.2.1
|  |  | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | No |  |  | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | C1
|  |  | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.1.2 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | C5
|  |  | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Slovenia | Plinovodi d.o.o. | Less-Advanced | No |  |  | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | C2
|  |  | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.1.5 (2018) | NSIE | Yes | 2022 | 2022 | Confidential | Confidential | URL | Yes | C4
|  |  | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Spain | Reganosa | Less-Advanced | No |  |  | No | 2023 | 2023 | Confidential | Confidential | URL | Yes | No Number- Name: Ampliación Planta de Reganosa. Ampliación de Emisión a 825,600 Nm3/h
|  |  | TRA-N-645 | HU-UA reverse flow (Ukrainian section) | Ukraine | PJSC Ukrtransgaz | Less-Advanced | No |  |  | No | 2017 | 2017 | Non-Confidential | Non-Confidential | URL | No | N/A
|  |  | TRA-N-1169 | Trans-Balkan Bi-directional Flow | Ukraine | PJSC "UKRTRANSGAZ" | Less-Advanced | No |  |  | No | 2019 | 2019 | Confidential | Confidential | URL | No | N/A
|  |  | TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | United Kingdom | Premier Transmission Limited | Less-Advanced | Yes | 5.1.2 (2018) | NSIW | Yes | 2021 | 2021 | Non-Confidential | Non-Confidential | URL | Yes | n.a.
* The current submission includes phase 1 and phase 2 of the project under the same investment item. To supoort modelling the project phases may be considered under two different investment items and the project list amended accordingly.
** Open Season procedure still ongoing

## Transmission Projects
Pipelines including Compressor Stations
Type | Code | Project Name | Promoter | Maturity Status | Section | Length (km) | Diameter (mm) | Compressor Power (MW)
Pipeline including CS | TRA-F-43 | Val de Saône project | GRTgaz | FID | Etrez CS |  |  | 9
Pipeline including CS | TRA-F-43 | Val de Saône project | GRTgaz | FID | Voisines CS |  |  | 0
Pipeline including CS | TRA-F-43 | Val de Saône project | GRTgaz | FID | Palleau CS |  |  | 0
Pipeline including CS | TRA-F-43 | Val de Saône project | GRTgaz | FID | Bourgogne | 189 | 1200
Pipeline including CS | TRA-F-43 | Val de Saône project | GRTgaz | FID | looping of Bourgogne pipeline | 190 | 1200 | 9
Pipeline including CS | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. | FID | Section 2 | 19 | 1200 | 0
Pipeline including CS | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. | FID |  | 80 | 1200 | 95
Pipeline including CS | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. | FID | Section 3 | 0 | 0 | 82
Pipeline including CS | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Snam Rete Gas S.p.A. | FID | Section 1 | 62 | 1400 | 0
Pipeline including CS | TRA-F-230 | Reverse Flow Transitgas Switzerland | FluxSwiss | FID
Pipeline including CS | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH | FID | Burghausen-Finsing | 87 | 1200
Pipeline including CS | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | bayernets GmbH | FID | Burghausen-Finsing | 90 | 1200
Pipeline including CS | TRA-F-208 | Reverse Flow TENP Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID
Pipeline including CS | TRA-F-331 | Gascogne Midi | TIGF - GRTgaz | FID | Pipeline Lussagnet - Barran + CS in Barbaira | 60 | 900 | 6
Pipeline including CS | TRA-F-331 | Gascogne Midi | TIGF - GRTgaz | FID | Additional compression at Barbaira | 0 | 0 | 0
Pipeline including CS | TRA-F-1228 | Interconnection with UGS in Cornegliano Laudense | Snam Rete Gas S.p.A. | FID | Interconnection with UGS in Cornegliano Laudense | 10 | 1050
Pipeline including CS | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | GRTgaz | FID | Morelmaison CS |  |  | 0
Pipeline including CS | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | GRTgaz | FID
Pipeline including CS | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | GRTgaz | FID | Oltingue interconnection station |  |  | 0
Pipeline including CS | TRA-F-1138 | South Caucasus Pipeline - (Future) Expansion - SCP-(F)X | SOCAR Midstream Operations LLC | FID | South-Caucasus Pipeline | 691 | 1067 | 6
Pipeline including CS | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | SOCAR (The State Oil Company of the Azerbaijan Republic) | FID | Georgia/Turkey border- Eskishehir | 1333 | 56
Pipeline including CS | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | SOCAR (The State Oil Company of the Azerbaijan Republic) | FID | Georgia/Turkey border- Eskishehir | 1347 | 1442 | 46
Pipeline including CS | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | SOCAR (The State Oil Company of the Azerbaijan Republic) | FID | Eskishehir (Turkey)-Greece Border | 460 | 1219 | 46
Pipeline including CS | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ Ltd. | FID | Csanadpalota |  |  | 9
Pipeline including CS | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | FGSZ Ltd. | FID | Csanádpalota |  |  | 9
Pipeline including CS | TRA-F-752 | Capacity4Gas – DE/CZ | NET4GAS, s.r.o. | FID | HSK-Přimda |  |  | 25
Pipeline including CS | TRA-F-752 | Capacity4Gas – DE/CZ | NET4GAS, s.r.o. | FID | HSK-Přimda | 152 | 1400
Pipeline including CS | TRA-F-941 | Metering and Regulating station at Nea Messimvria | DESFA S.A. | FID | Nea-Messivria to TAP | 1
Pipeline including CS | TRA-F-340 | CS Wertingen | bayernets GmbH | FID
Pipeline including CS | TRA-F-937 | Nord Stream 2 | Nord Stream 2 AG | FID | Nord Stream 2 | 1200 | 1153
Pipeline including CS | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Elering AS | FID | Karksi GMS, Puiatu CS |  |  | 10
Pipeline including CS | TRA-F-954 | TAG Reverse Flow | Trans Austria Gasleitung GmbH | FID
Pipeline including CS | TRA-F-1193 | TAP interconnection | Snam Rete Gas S.p.A. | Less-Advanced | Tap Interconnection | 55 | 1400
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Plinacro Ltd | FID | CS 1 |  |  | 4
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Plinacro Ltd | FID | Compressor stations at the Croatian transmission system - first compressor |  |  | 6
Pipeline including CS | TRA-F-902 | Capacity increase at IP Lanžhot entry | eustream,a.s. (a joint-stock company) | FID | Capacity increase at IP Lanžhot entry |  |  | 46
Pipeline including CS | TRA-F-895 | Balticconnector | Elering AS | FID | FI Onshore | 20 | 500 | 10
Pipeline including CS | TRA-F-895 | Balticconnector | Elering AS | FID | Offshore | 80 | 500
Pipeline including CS | TRA-F-895 | Balticconnector | Elering AS | FID | EE Onshore | 55 | 700 | 10
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Offshore section | 105 | 900
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Main onshore section | 773 | 1200 | 90
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | FID | Trans-Adriatic Pipeline | 14 | 900 | 90
Pipeline including CS | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | EE Onshore | 50 | 700 | 10
Pipeline including CS | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | FI Onshore | 20 | 500 | 10
Pipeline including CS | TRA-F-928 | Balticconnector Finnish part | Baltic Connector Oy | FID | Offshore | 80 | 500
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | CS Kędzierzyn |  |  | 30
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | Tworóg-Kędzierzyn Koźle pipeline | 43 | 1000
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | Tworóg-Tworzeń pipeline | 56 | 1000
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | Kędzierzyn Node
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | Zdzieszowice-Kędzierzyn Koźle | 19 | 1000
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | CS Odolanów |  |  | 34
Pipeline including CS | TRA-F-918 | Capacity4Gas – CZ/SK | NET4GAS, s.r.o. | FID | Capacity4Gas - CZ/SK
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. | FID | Podisor-Horia | 545 | 800 | 50
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. | FID | Phase II: Recas-Horia | 50 | 800 | 14
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. | FID | Podisor - Horia | 528 | 813 | 50
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | FID | IGB | 182 | 813 | 12
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. | FID | Podisor - Horia | 528 | 813 | 50
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. | FID | Phase I: Podisor-Recas | 479 | 800 | 28
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | SNTGN Transgaz S.A. | FID | Podisor - Horia | 528 | 813 | 50
Pipeline including CS | TRA-F-1241 | Interconnection with production in Gela | Snam Rete Gas S.p.A. | FID | all the project | 1 | 500 | 0
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | GAZ-SYSTEM S.A. | FID | Zdzieszowice - Wrocław pipeline | 130 | 1000
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | Advanced | CS Hołowczyce - modernization
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | Advanced | GIPL - Polish section | 357 | 700 | 6
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | Advanced | GIPL - Polish section | 357 | 700
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | GAZ-SYSTEM S.A. | Advanced | CS Gustorzyn |  |  | 30
Pipeline including CS | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | AB Amber Grid | Advanced | Board of POland - Jauniunai (LT) | 177 | 700
Pipeline including CS | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | AB Amber Grid | Advanced | Border PL/LT - Jauniunai | 165 | 700
Pipeline including CS | TRA-F-190 | Poland - Slovakia interconnection | eustream,a.s. (a joint-stock company) | Advanced
Pipeline including CS | TRA-F-190 | Poland - Slovakia interconnection | eustream,a.s. (a joint-stock company) | Advanced | Slovak section | 106 | 1000 | 0
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | Pogórka Wola - Tworzeń pipeline | 160 | 1000
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | PL-SK Interconnection - Polish section | 58 | 1000
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | CS Strachocina |  |  | 30
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | Tworóg - Tworzeń pipeline | 56 | 1000
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | Strachocina - Pogórska Wola pipeline | 98 | 1000
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | The Polish section | 164 | 1000 | 29
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD | FID | PF Beglej - VA Dermantsi - VA Batultsi - VA Kalugerovo | 58 | 700
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD | FID | Gorni Bogrov - Novi Iskar | 19 | 700 | 20
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD | FID | Valchi Dol - Preselka | 23 | 700
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgartransgaz EAD | FID | Lozenets-Nedyalsko | 20 | 1000
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy | FID | Bulgarian territory | 62 | 700
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy | FID | Bulgarian territory | 62 | 700
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy | FID | Serbian territory | 108 | 700
Pipeline including CS | TRA-F-1271 | Compressor Station Krummhoern | Open Grid Europe GmbH | FID | CS Krummhoern extension step 2 |  |  | 13
Pipeline including CS | TRA-F-1271 | Compressor Station Krummhoern | Open Grid Europe GmbH | FID | CS Krummhoern extension step 1 |  |  | 13
Pipeline including CS | TRA-F-1028 | Albania - Kosovo Gas Pipeline | Min. of Infrastructure and Energy AL & Min. of Economic Development KO | FID | Section 1 | 175 | 610 | 2
Pipeline including CS | TRA-F-329 | ZEELINK | Open Grid Europe GmbH and Thyssengas GmbH | FID | CS Legden |  |  | 26
Pipeline including CS | TRA-F-329 | ZEELINK | Open Grid Europe GmbH and Thyssengas GmbH | FID | ZEELINK 1 | 112 | 1000
Pipeline including CS | TRA-F-329 | ZEELINK | Open Grid Europe GmbH and Thyssengas GmbH | FID | CS Würselen |  |  | 39
Pipeline including CS | TRA-F-329 | ZEELINK | Open Grid Europe GmbH and Thyssengas GmbH | FID | ZEELINK 2 | 115 | 1000
Pipeline including CS | TRA-N-291 | NOWAL - Nord West Anbindungsleitung | GASCADE Gastransport GmbH | Advanced | Rehden-Drohne | 26 | 600
Pipeline including CS | TRA-N-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | GALSI Italian Section 2 sealine Sardinia - Tuscany | 288 | 812 | 52
Pipeline including CS | TRA-N-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | GALSI International Section | 288 | 660 | 99
Pipeline including CS | TRA-N-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | GALSI Italian Section 1 onshore pipeline crossing Sardinia | 285 | 1219
Pipeline including CS | TRA-N-12 | GALSI Pipeline Project | Galsi S.p.A. | Advanced | GALSI Italian Section 1 onshore pipeline crossing Sardinia | 285 | 1219
Pipeline including CS | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd | Advanced | Omišalj-Zlobin | 18 | 1000
Pipeline including CS | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Plinacro Ltd | Advanced | Omišalj-Zlobin | 18 | 1000
Pipeline including CS | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | SNTGN Transgaz SA | Advanced
Pipeline including CS | TRA-N-1169 | Trans-Balkan Bi-directional Flow | PJSC "UKRTRANSGAZ" | Less-Advanced | Phase 1 | 320 | 1200 | 0
Pipeline including CS | TRA-N-1267 | Upgrade Sülstorf station | NGT GmbH / GUD GmbH & Co. KG / Fluxys D GmbH / ONTRAS GmbH | Advanced
Pipeline including CS | TRA-N-357 | NTS developments in North-East Romania | SNTGN Transgaz SA | Advanced | Onesti - Gheraesti - Letcani | 165 | 711 | 18
Pipeline including CS | TRA-N-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | SNTGN Transgaz SA | Advanced | A
Pipeline including CS | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | Advanced | AL NEL | 1 | 1000
Pipeline including CS | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | Advanced | EUGAL | 484 | 1400 | 75
Pipeline including CS | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | SNTGN Transgaz SA | Advanced | Vadu-Gradina | 25 | 508
Pipeline including CS | TRA-N-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. | Advanced | Alexandroupolis FSRU - M/R Amfitriti (new) | 28 | 762
Pipeline including CS | TRA-N-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Gastrade S.A. | Advanced | Alexandroupolis LNG terminal - M/R Amfitriti | 28 | 762 | 0
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Advanced | Slobodnica - Bosanski Brod | 6 | 700
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Advanced | Slobodnica - Bosanski Brod | 6 | 700
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Advanced | Bosiljevo - Sisak | 102 | 1000
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Advanced | Kozarac - Sisak | 20 | 800
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Advanced | Bosiljevo - Sisak | 102 | 800
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Plinacro Ltd | Advanced | Zlobin - Bosiljevo | 58 | 800
Pipeline including CS | TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | PJSC UKRTRANSGAZ | Advanced | Drozdovychi - Bilche Volytsya | 99 | 1000 | 0
Pipeline including CS | TRA-N-950 | Guitiriz - Lugo - Zamora pipeline | Reganosa | Advanced | Guitiriz-Lugo | 30 | 750 | 0
Pipeline including CS | TRA-N-950 | Guitiriz - Lugo - Zamora pipeline | Reganosa | Advanced | Lugo-Zamora | 288 | 750 | 0
Pipeline including CS | TRA-N-1303 | IAEF - Vlora ccgt | Albgaz Sha | Less-Advanced | IAEF - Vlora CCGT | 40 | 400
Pipeline including CS | TRA-N-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | GNI (UK) Limited | Advanced | interconnector 1 & 2 | 100 | 914 | 40
Pipeline including CS | TRA-N-975 | Sardinia Gas Transportation Network | Società Gasdotti Italia | Advanced | Regional Network | 200 | 250
Pipeline including CS | TRA-N-975 | Sardinia Gas Transportation Network | Società Gasdotti Italia | Advanced | National Network backbone | 400 | 400
Pipeline including CS | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | SNTGN Transgaz SA | Advanced | Black Sea shore - Podișor | 308 | 1200
Pipeline including CS | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | SNTGN Transgaz SA | Advanced | Black Sea shore - Podisor | 247 | 800
Pipeline including CS | TRA-N-621 | Poland - Ukraine Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | Hermanowice Node - PL/UA border pipeline | 2 | 1000
Pipeline including CS | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd | Advanced | Bosiljevo-Karlovac-Lučko-Zabok-Rogatec | 148 | 700
Pipeline including CS | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd | Advanced | Lučko-Zabok | 33 | 700
Pipeline including CS | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd | Advanced | Zabok-Rogatec | 36 | 700
Pipeline including CS | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | NET4GAS, s.r.o. | Advanced | Břeclav-Reintal-Baumgarten
Pipeline including CS | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | NET4GAS, s.r.o. | Advanced | Břeclav (CZ) - Poštorná/Reintal (CZ/AT) | 12 | 800
Pipeline including CS | TRA-N-21 | Bidirectional Austrian-Czech Interconnector (BACI) | GAS CONNECT AUSTRIA GmbH | Advanced | Austrian Side | 49 | 800
Pipeline including CS | TRA-N-21 | Bidirectional Austrian-Czech Interconnector (BACI) | GAS CONNECT AUSTRIA GmbH | Advanced | Czech Side | 12 | 800
Pipeline including CS | TRA-N-21 | Bidirectional Austrian-Czech Interconnector (BACI) | GAS CONNECT AUSTRIA GmbH | Advanced | Austrian Side | 46 | 800 | 24
Pipeline including CS | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | Advanced | Zagvozd-Imotski-Posušje | 22 | 500
Pipeline including CS | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | Advanced | Zagvozd-Imotski-Posušje | 22 | 500
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | IAP - Croatian part | 250 | 800
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | IAP - Croatian part | 250 | 800 | 1
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | IAP- Albanian part | 180 | 800
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Advanced | IAP- Montenego part | 110 | 800
Pipeline including CS | TRA-N-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Advanced | Tvrdonice-Hať-Kedzierzyn | 267 | 1000
Pipeline including CS | TRA-N-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Advanced | Tvrdonice (CZ) - Hať (CZ/PL) | 207 | 1000 | 24
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. | Advanced | Pipeline Figueras - French Border | 25 | 892
Pipeline including CS | TRA-N-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | Poseidon offshore section | 210 | 915 | 75
Pipeline including CS | TRA-N-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | Poseidon onshore section | 770 | 1220 | 75
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Less-Advanced | R15/1 Pince - Lendava - Kidričevo | 73 | 500 | 6
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Less-Advanced | R15/1 Lendava - Kidričevo | 70 | 500
Pipeline including CS | TRA-N-123 | Városföld CS | FGSZ Ltd. | Advanced | Városföld CS |  |  | 6
Pipeline including CS | TRA-N-123 | Városföld CS | FGSZ Ltd. | Advanced | Városföld CS |  |  | 6
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. | Advanced | Hostalrich - Figueras | 79 | 900
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. | Advanced | Pipeline Figueras - French Border | 28 | 900
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. | Advanced | CS Martorell |  |  | 36
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | Advanced | Onshore pipeline connecting offshore pipeline with the national grid | 40 | 1000
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | Advanced | Baltic Pipe (offshore section) | 280 | 600
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | Advanced | Baltic Pipe (offshore section) | 280 | 900
Pipeline including CS | TRA-N-273 | Poland - Czech Republic Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | PL-CZ Interconnection - Polish section | 54 | 1000
Pipeline including CS | TRA-N-273 | Poland - Czech Republic Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Advanced | PL-CZ interconnection - Polish section | 60 | 1000 | 16
Pipeline including CS | TRA-N-423 | GCA Mosonmagyaróvár | GAS CONNECT AUSTRIA GmbH | Advanced | Mosonmagyarovar
Pipeline including CS | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | GAS CONNECT AUSTRIA GmbH | Advanced | Murfeld
Pipeline including CS | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | GAS CONNECT AUSTRIA GmbH | Advanced | Murfeld
Pipeline including CS | TRA-N-423 | GCA Mosonmagyaróvár | GAS CONNECT AUSTRIA GmbH | Advanced | Mosonmagyarovar
Pipeline including CS | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | Bulgartransgaz EAD | Advanced | CS Valchi dol - line valve Novi Iskar | 383 | 700
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia | Advanced | Chieti-Cellino | 55 | 500
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia | Advanced | Cellino-San Marco | 90 | 500
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia | Advanced | Larino - Chieti | 113 | 600
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Società Gasdotti Italia | Advanced | San Marco-Recanati | 35 | 600 | 3
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Advanced | Nagykanizsa-Tornyiszentmiklós | 41 | 600
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Advanced | Nagykanizsa-Tornyiszentmiklós | 150 | 600 | 12
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | FGSZ Ltd. | Advanced | Nagykanizsa-Tornyiszentmiklós | 41 | 500 | 8
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | GAZ-SYSTEM S.A. | Advanced | Onshore receiving terminal in Poland
Pipeline including CS | TRA-N-780 | Baltic Pipe project – onshore section in Denmark | Energinet.dk | Advanced
Pipeline including CS | TRA-N-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | Advanced | CS Odolanów |  |  | 14
Pipeline including CS | TRA-N-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | Advanced | CS Gustorzyn |  |  | 15
Pipeline including CS | TRA-N-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | Advanced | Goleniów – Lwówek pipeline | 188 | 1000
Pipeline including CS | TRA-N-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | GAZ-SYSTEM S.A. | Advanced | CS Goleniów |  |  | 12
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Plinovodi d.o.o. | Less-Advanced | Upgrade of Murfeld/Ceršak interconnection | 0 | 800
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Plinovodi d.o.o. | Less-Advanced | Upgrade of Murfeld/Ceršak interconnection | 0 | 800
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. | Less-Advanced | Upgrade of Rogatec interconnection |  | 800
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Plinovodi d.o.o. | Less-Advanced | Upgrade of Rogatec interconnection | 4 | 800
Pipeline including CS | TRA-N-593 | Varna-Oryahovo gas pipeline | Bulgartransgaz EAD | Advanced | Varna-Oryahovo gas pipeline | 844 | 1200 | 265
Pipeline including CS | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | TIGF | Advanced | Pipeline Spanish Border-Barbaira + CS Barbaira | 120 | 800 | 10
Pipeline including CS | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | TIGF | Advanced | Pipeline Spanish Border-Barbaira | 120 | 900
Pipeline including CS | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. | Advanced | Csanádpalota |  |  | 4
Pipeline including CS | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | FGSZ Ltd. | Advanced | Csanádpalota |  |  | 4
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Plinovodi d.o.o. | Less-Advanced | CS Kidričevo, 2nd phase of upgrade |  |  | 30
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Plinovodi d.o.o. | Less-Advanced | CS Kidričevo, 2nd phase of upgrade |  |  | 30
Pipeline including CS | TRA-N-394 | Norwegian tie-in to Danish upstream system | Energinet.dk | Advanced
Pipeline including CS | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgartransgaz EAD | Advanced | CS Strandja – a new IP with Turkey. | 20 | 1000
Pipeline including CS | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgartransgaz EAD | Advanced | Looping CS Provadia – Rupcha village | 50 | 1200 | 10
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Plinacro Ltd | Advanced
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Plinacro Ltd | Advanced | Kozarac-Slobodnica | 128 | 800
Pipeline including CS | TRA-N-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Advanced | Slobodnica - Sotin | 97 | 800
Pipeline including CS | TRA-N-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Advanced | Sotin- Bačko Novo Selo | 5 | 800
Pipeline including CS | TRA-N-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Plinacro Ltd | Advanced | Slobodnica - Sotin | 97 | 800
Pipeline including CS | TRA-N-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Advanced | Eastring - SK-2 | 19 | 1400 | 52
Pipeline including CS | TRA-N-31 | Connection of Malta to the European Gas Network - Pipelines | Ministry For Energy & Water Management - Malta | Advanced | FSRU (Malta) to Delimara (Malta) | 12 | 457
Pipeline including CS | TRA-N-31 | Connection of Malta to the European Gas Network - Pipelines | Ministry For Energy & Water Management - Malta | Advanced | Delimara (Malta) to Gela (Sicily) Italy | 159 | 560 | 0
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | Montpellier and Saint Martin de Crau compressor stations |  |  | 30
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | Midi pipeline (TIGF section) | 40 | 1050
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | Midi pipeline (GRTgaz section) | 200 | 1050
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | Barbaira CS (TIGF section) |  |  | 7
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | Eridan (GRTgaz section) | 220 | 1200
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | Palleau CS (GRTgaz section) |  |  | 50
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | Barbaira - Border (TIGF section) | 120 | 900
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | St-Martin de Crau CS |  |  | 30
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | Arc Lyonnais (GRTgaz section) | 150 | 1200
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | St-Avit CS (GRTgaz section) |  |  | 15
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Advanced | Perche (GRTgaz section) | 63 | 900
Pipeline including CS | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | Advanced | Celorico-Spanish border | 162 | 700
Pipeline including CS | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | Advanced | Pipeline Spanish Border-Celorico | 158 | 700
Pipeline including CS | TRA-N-320 | Carregado Compressor Station | REN-Gasodutos, S.A. | Advanced | Setubal - Leiria (Lote 1) |  |  | 14
Pipeline including CS | TRA-N-320 | Carregado Compressor Station | REN-Gasodutos, S.A. | Advanced | Setubal - Leiria (Lote 1) |  |  | 14
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. | Advanced | CS Martorell |  |  | 36
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. | Advanced | Loop Tivissa – Arbós + CS Tivissa filters + CS Arbós (increment) | 114 | 740 | 21
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. | Advanced | Loop Castelnou – Villar de Arnedo + CS Zaragoza (increment) | 214 | 640 | 5
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. | Advanced | Hostalrich - Figueras | 79 | 900
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. | Advanced | Pipeline Figueras - French Border | 28 | 900
Pipeline including CS | TRA-N-645 | HU-UA reverse flow (Ukrainian section) | PJSC Ukrtransgaz | Less-Advanced
Pipeline including CS | TRA-N-955 | GUD: Complete conversion to H-gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced
Pipeline including CS | TRA-N-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | ONTRAS Gastransport GmbH | Advanced | Connection Kienbaum-EUGAL |  | 700
Pipeline including CS | TRA-N-1200 | Expansion MS Hetlingen | Gasunie Deutschland Transport Service GmbH | Less-Advanced
Pipeline including CS | TRA-N-1253 | Trans-Balkan Bi-directional Flow (Moldavia phase) | Moldovatransgaz LLC | Less-Advanced | Phase 1 | 320 | 1200
Pipeline including CS | TRA-N-192 | Entry capacity expansion GATE terminal | Gasunie Transport Services B.V. | Less-Advanced | Maasvlakte - Wijngaarden | 25 | 1200
Pipeline including CS | TRA-N-192 | Entry capacity expansion GATE terminal | Gasunie Transport Services B.V. | Less-Advanced | Maasvlakte - Wijngaarden | 25 | 1200
Pipeline including CS | TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | AB Amber Grid | Less-Advanced | Enhancement of Latvia-Lithuania interconnection (Lithuanian part)
Pipeline including CS | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Gasunie Transport Services B.V. | Less-Advanced
Pipeline including CS | TRA-N-809 | Additional East-West transport | Gasunie Deutschland Transport Services GmbH | Advanced | Reversion Holtum
Pipeline including CS | TRA-N-980 | Interconnection Macedonia-Greece | MER JSC Skopje | Less-Advanced | Stip-Hamzali-Stojakovo (border with Greece)
Pipeline including CS | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | DESFA S.A. | Less-Advanced
Pipeline including CS | TRA-N-1197 | Expansion of the gas infrastructure between BG-TR and BG-RS borders | Bulgartransgaz EAD | Less-Advanced | New gas pipeline from CS Provadia to the Bulgarian-Serbian border | 484 | 1200 | 64
Pipeline including CS | TRA-N-1197 | Expansion of the gas infrastructure between BG-TR and BG-RS borders | Bulgartransgaz EAD | Less-Advanced | CS Strandja through CS Lozenets to CS Provadia
Pipeline including CS | TRA-N-1197 | Expansion of the gas infrastructure between BG-TR and BG-RS borders | Bulgartransgaz EAD | Less-Advanced | New gas pipeline from the Bulgarian-Turkish border to CS Strandja | 93 | 1200 | 64
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 4 | 1 | 150
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 5 | 26 | 150
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 6 | 17 | 200
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 7 | 105 | 400
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 1 | 17 | 250
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 2 | 29 | 150
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 3 | 50 | 650
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 4 | 77 | 650
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 6 | 6 | 150
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 1 | 43 | 400
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 2 | 75 | 650
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 5 | 8 | 250
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 7 | 26 | 150
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 1 | 32 | 650
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 3 | 54 | 400
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Snam Rete Gas S.p.A. | Less-Advanced | phase 4 | 7 | 200
Pipeline including CS | TRA-N-951 | Embedding CS Folmhusen in H-Gas | Gasunie Deutschland Transport Services GmbH | Less-Advanced
Pipeline including CS | TRA-N-1268 | Romania-Serbia Interconnection | SNTGN Tranzgaz SA | Less-Advanced | PETROVASELO-COMLOȘU MARE | 85 | 600
Pipeline including CS | TRA-N-128 | Compressor Station Kipi | DESFA S.A. | Less-Advanced | Kipi | 0 | 0 | 9
Pipeline including CS | TRA-N-128 | Compressor Station Kipi | DESFA S.A. | Less-Advanced | Kipi | 0 | 0 | 9
Pipeline including CS | TRA-N-1064 | Moffat Physical Reverse Flow | National Grid Gas plc | Less-Advanced
Pipeline including CS | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | JSC "Conexus Baltic Grid" | Less-Advanced | Riga-Iecava-Lithuanian border | 93 | 700
Pipeline including CS | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | JSC "Conexus Baltic Grid" | Less-Advanced | Riga-Iecava-Lithuanian border | 42 | 700
Pipeline including CS | TRA-N-967 | Nea-Messimvria to FYRoM pipeline | DESFA S.A. | Less-Advanced | Nea-Messimvria to Pontoiraklia/Stojakovo | 50 | 700
Pipeline including CS | TRA-N-339 | Trans-Caspian | W-Stream Caspian Pipeline Company Ltd | Advanced | sub-sea (string 1) | 300 | 812 | 175
Pipeline including CS | TRA-N-339 | Trans-Caspian | W-Stream Caspian Pipeline Company Ltd | Advanced | sub-sea (string 2) | 300 | 812 | 175
Pipeline including CS | TRA-N-965 | Interconnection Macedonia-Serbia | MER JSC Skopje | Less-Advanced | Main gas pipeline section Klechovce-Sopot (border with Serbia) | 23 | 500
Pipeline including CS | TRA-N-976 | Interconnection Macedonia-Bulgaria | MER JSC Skopje | Less-Advanced | Main gas pipeline section Hamzali – Novo Selo (border with Bulgaria) | 25 | 700
Pipeline including CS | TRA-N-1276 | Compressor station at Nea Messimvria (3rd unit) | DESFA S.A. | Less-Advanced
Pipeline including CS | TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | Premier Transmission Limited | Less-Advanced | SNIP-Scotland to Northern Ireland |  | 600 | 10
Pipeline including CS | TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | Premier Transmission Limited | Less-Advanced | SNIP-Scotland to Northern Ireland |  | 600 | 10
Pipeline including CS | TRA-N-1199 | LNG Terminal Brunsbuettel - Grid Integration | Gasunie Deutschland Transport Service GmbH | Less-Advanced | Brunsbuettel-Hetlingen | 50 | 800
Pipeline including CS | TRA-N-47 | Reverse capacity from France to Germany at Obergailbach | GRTgaz | Less-Advanced | Morelmaison - Laneuvelotte | 60 | 1050 | 42
Pipeline including CS | TRA-N-47 | Reverse capacity from France to Germany at Obergailbach | GRTgaz | Less-Advanced | Obergailbach interconnection station
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Plinovodi d.o.o. | Less-Advanced | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | 12 | 500
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Plinovodi d.o.o. | Less-Advanced | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | 31 | 500
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD | Less-Advanced |  | 130
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD | Less-Advanced | ITB Bulgarian Section | 76 | 700 | 13
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD | Less-Advanced | ITB Turkish Section | 130
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | Less-Advanced | Hungarian section | 92 | 800
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | Less-Advanced | Slovak section | 18 | 800
Pipeline including CS | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | eustream,a.s. (a joint-stock company) | Less-Advanced
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | Less-Advanced | Hungarian section | 92 | 800
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | Less-Advanced | Slovak | 18 | 800
Pipeline including CS | TRA-N-971 | Compressor station at Nea Messimvria | DESFA S.A. | Less-Advanced | Nea Messimvria to TAP |  |  | 27
Pipeline including CS | TRA-N-1254 | CS Elten | Open Grid Europe GmbH and Thyssengas GmbH | Less-Advanced | CS Elten |  |  | 11
Pipeline including CS | TRA-N-1265 | Biomethane productions interconnection | Snam Rete Gas S.p.A. | Less-Advanced | All the project | 21 | 100
Pipeline including CS | TRA-N-1227 | Gorizia plant upgrade | Snam Rete Gas S.p.A. | Less-Advanced
Pipeline including CS | TRA-N-1278 | Compressor station at Ambelia | DESFA S.A. | Less-Advanced
Pipeline including CS | TRA-N-500 | L/H Conversion Belgium | Fluxys Belgium | Advanced
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Jarosław - Rozwadów pipeline | 60 | 700
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Rembelszczyzna-Wronów pipeline | 135 | 1000
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Rozwadow-Konskowola-Wronow pipeline | 103 | 700
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Hermanowice-Strachocina pipeline | 72 | 700
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Hermanowice-Jarosław pipeline | 39 | 700
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Gustorzyn-Wronów pipeline | 316 | 1000
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | GAZ-SYSTEM S.A. | Less-Advanced | Rozwadów-Końskowola-Wronów pipeline | 103 | 700
Pipeline including CS | TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | GAZ-SYSTEM S.A. | Less-Advanced | Kiełczów node - modernisation
Pipeline including CS | TRA-N-831 | Vecsés-Városföld gas transit pipeline | Magyar Gáz Tranzit Zrt. | Less-Advanced | Vecsés-Városföld | 80 | 800
Pipeline including CS | TRA-N-53 | White Stream | White Stream Ltd | Less-Advanced | Supsa to Constanta | 1115 | 726 | 375
Pipeline including CS | TRA-N-53 | White Stream | White Stream Ltd | Less-Advanced | Supsa to Constanta | 1115 | 726
Pipeline including CS | TRA-N-53 | White Stream | White Stream Ltd | Less-Advanced | Vale to Supsa | 135 | 1039
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Plinovodi d.o.o. | Less-Advanced | CS Ajdovščina, 1st phase of upgrade |  |  | 5
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Plinovodi d.o.o. | Less-Advanced | CS Ajdovščina, 1st phase of upgrade |  |  | 5
Pipeline including CS | TRA-N-71 | Physical Reverse Flow on South North Pipeline | Gas Networks Ireland | Less-Advanced
Pipeline including CS | TRA-N-71 | Physical Reverse Flow on South North Pipeline | Gas Networks Ireland | Less-Advanced
Pipeline including CS | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. | Less-Advanced | Zenica - Brod | 130 | 500
Pipeline including CS | TRA-N-224 | Gaspipeline Brod - Zenica | BH-Gas d.o.o. | Less-Advanced | Brod-Zenica (section through FBiH and RS) | 140 | 500 | 0
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | Perche | 63 | 900
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | Palleau CS |  |  | 50
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | Eridan | 220 | 1200
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | St-Martin de Crau CS |  |  | 30
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | Arc Lyonnais | 150 | 1200
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | GRTgaz | Less-Advanced | St-Avit CS |  |  | 15
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | Less-Advanced | Artère du Maine | 200 | 1050
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | Less-Advanced | Auvers-le-Hamon CS |  |  | 0
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | Less-Advanced | Maine pipeline looping | 200 | 1050
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | GRTgaz | Less-Advanced | Artère du Perche | 63 | 900
Pipeline including CS | TRA-N-354 | Interconnection with Slovenia | Snam Rete Gas S.p.A. | Less-Advanced | all the project | 6 | 250 | 0
Pipeline including CS | TRA-N-354 | Interconnection with Slovenia | Snam Rete Gas S.p.A. | Less-Advanced | All the pipe | 6 | 250 | 0
Pipeline including CS | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Less-Advanced | Eastring-BG-2 | 257 | 1400 | 88
Pipeline including CS | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Less-Advanced | Eastring-HU-1/2 | 112 | 1400 | 0
Pipeline including CS | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | SNTGN Transgaz SA | Less-Advanced | Onesti - Nadlac | 843 | 813 | 82
Pipeline including CS | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | DESFA S.A. | Less-Advanced
Pipeline including CS | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | BH-GAS d.o.o. | Less-Advanced | Posusje-Travnik with branch to Mostar | 165 | 500 | 0
Pipeline including CS | TRA-N-655 | Eastring - Romania | SNTGN Transgaz SA | Less-Advanced | Eastring-RO-2 | 651 | 1400
Pipeline including CS | TRA-N-755 | CS Rimpar | GRTgaz Deutschland GmbH | Less-Advanced | CS Rimpar / MEGAL | 0 | 0 | 39
Pipeline including CS | TRA-N-14 | Komotini-Thesprotia pipeline | DESFA S.A. | Less-Advanced | Komotini-Thesprotia | 613 | 1067 | 58
Pipeline including CS | TRA-N-14 | Komotini-Thesprotia pipeline | DESFA S.A. | Less-Advanced | Komotini-Thesprotia | 613 | 1067 | 58
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. | Less-Advanced | Zamora - Portuguese Border | 86 | 700
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. | Less-Advanced | CS Zamora |  |  | 4
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. | Less-Advanced | CS Zamora |  |  | 23
Pipeline including CS | TRA-N-1129 | Compressor Station Kipi Increment | DESFA S.A. | Less-Advanced | 1 |  |  | 20
Pipeline including CS | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | Less-Advanced
Pipeline including CS | TRA-N-7 | Development for new import from the South (Adriatica Line) | Snam Rete Gas S.p.A. | Less-Advanced | Adriatica section | 700 | 1200 | 33
Pipeline including CS | TRA-N-7 | Development for new import from the South (Adriatica Line) | Snam Rete Gas S.p.A. | Less-Advanced | Adriatica Line | 430 | 1200 | 33
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Less-Advanced | Bethune area | 8 | 300
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Less-Advanced | Arleux interconnection station
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Less-Advanced | Connection to H-gas grid
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Less-Advanced | Taisnieres interconnection station
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Less-Advanced | Brouckerque area | 2 | 200
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | GRTgaz and Storengy | Less-Advanced | Interconnection with Gournay UGS
Pipeline including CS | TRA-N-873 | Additional capacity at OSZ from Germany to the Netherlands | Gasunie Transport Services B.V. | Less-Advanced
Pipeline including CS | TRA-N-1246 | Greece - Italy interconnection | Snam Rete Gas S.p.A. | Less-Advanced | All the project
Pipeline including CS | TRA-N-808 | Transport of gas volumes to the Netherlands | Gasunie Deutschland Transport Services GmbH | Less-Advanced
Pipeline including CS | TRA-N-1091 | Metering and Regulating station at Megalopoli | DESFA S.A. | Less-Advanced
Pipeline including CS | TRA-N-1195 | Matagiola - Massafra pipeline | Snam Rete Gas S.p.A. | Less-Advanced | Matagiola - Massafra | 80 | 1400
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced | EastMed pipeline: section from West Greece to Thesprotia | 236 | 1070
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced | EastMed pipeline: section from Crete to Peloponnese | 421 | 660 | 120
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced | EastMed: section from Peloponnese to West Greece | 317 | 1070
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced | EastMed pipeline: section from Cyprus to Crete | 732 | 660 | 100
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced | EastMed pipeline: section from Levantine Basin to Cyprus | 165 | 610
Pipeline including CS | TRA-N-910 | West Interconnection BiH/CRO | BH-Gas d.o.o. | Less-Advanced | Licka Jesenica - Trzac - Bos.Krupa | 35 | 500 | 0
Pipeline including CS | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Plinacro Ltd | Less-Advanced | Umag - Plovanija (HR)- Koper (SI) | 8 | 300
Pipeline including CS | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Plinacro Ltd | Less-Advanced | Umag - Plovanija (HR)- Koper (SI) | 8 | 300
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | Less-Advanced | Rakovica-Bihać | 10 | 500
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | Less-Advanced | Lička Jesenica-Rakovica | 20 | 500
Pipeline including CS | TRA-N-17 | System Enhancements - Eustream | eustream, a.s. | Less-Advanced
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. | Less-Advanced | Guitiriz - Lugo | 28 | 740
Pipeline including CS | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | REN-Gasodutos, S.A. | Less-Advanced | Cantanhede Compressor Station |  |  | 12
Pipeline including CS | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | REN-Gasodutos, S.A. | Less-Advanced | Cantanhede Compressor Station |  |  | 12
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. | Less-Advanced | Castropodame - Zamora | 170 | 600
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. | Less-Advanced | Villafranca del Bierzo - Castropodame | 30 | 740
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. | Less-Advanced | Zamora - La Barbolla - Adradas | 307 | 800
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. | Less-Advanced | Lugo - Villafranca del Bierzo | 90 | 740
Pipeline including CS | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | REN-Gasodutos, S.A. | Less-Advanced | Pipeline Cantanhede-Mangualde | 67 | 700
Pipeline including CS | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | REN-Gasodutos, S.A. | Less-Advanced | Pipeline Cantanhede-Mangualde | 67 | 500
Pipeline including CS | TRA-N-8 | Import developments from North-East | Snam Rete Gas S.p.A. | Less-Advanced | Section 2 | 119 | 1400 | 0
Pipeline including CS | TRA-N-8 | Import developments from North-East | Snam Rete Gas S.p.A. | Less-Advanced | Section 3 | 0 | 0 | 75
Pipeline including CS | TRA-N-8 | Import developments from North-East | Snam Rete Gas S.p.A. | Less-Advanced |  | 120 | 1400 | 100
Pipeline including CS | TRA-N-8 | Import developments from North-East | Snam Rete Gas S.p.A. | Less-Advanced | Section 1 | 15 | 1050 | 0
Pipeline including CS | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Section 1 | 255 | 800 | 0
Pipeline including CS | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Section 1 | 663 | 1200 | 0
Pipeline including CS | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Section 3 | 590 | 1200 | 0
Pipeline including CS | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Section 4 | 0 | 0 | 60
Pipeline including CS | TRA-N-9 | Additional Southern developments | Snam Rete Gas S.p.A. | Less-Advanced | Section 2 | 115 | 1050 | 0

## LNG Terminals
LNG Terminals
Type | Code | Project Name | LNG Facility | Promoter | Maturity Status | Reloading Ability | Project Yearly Volume (bcm/y) | Project Ship Size (m3 LNG) | Project Storage Capacity (m3 LNG)
LNG Terminal | LNG-F-147 | Revythoussa (2nd upgrade) | Revythoussa LNG Terminal | DESFA S.A. | FID
LNG Terminal | LNG-F-229 | Zeebrugge LNG Terminal - 5th Tank | Zeebrugge LNG Terminal | Fluxys LNG | FID | Yes | 0 | 0 | 180000
LNG Terminal | LNG-F-178 | Musel LNG terminal | Musel | Enagás Transporte, S.A.U. | FID
LNG Terminal | LNG-F-183 | Tenerife LNG Terminal | Tenerife LNG Terminal | Gascan | FID |  | 1.3 | 140000 | 150000
LNG Terminal | LNG-F-272 | Upgrade of LNG terminal in Świnoujście | LNG terminal in Świnoujście | GAZ-SYSTEM S.A. | FID
LNG Terminal | LNG-F-163 | Gran Canaria LNG Terminal | Gran Canaria | Gascan | FID |  | 1.3 | 140 | 150000
LNG Terminal | LNG-N-82 | LNG terminal Krk | The import terminal for the liquefied natural gas(LNG) on the Island of Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | Advanced | Yes | 2.6 | 160000 | 160000
LNG Terminal | LNG-N-82 | LNG terminal Krk | The import terminal for the liquefied natural gas(LNG) on the Island of Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | Advanced | Yes | 3.5 | 0 | 0
LNG Terminal | LNG-N-82 | LNG terminal Krk | The import terminal for the liquefied natural gas(LNG) on the Island of Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | Advanced | Yes | 7 | 0 | 0
LNG Terminal | LNG-N-32 | Project GO4LNG LNG terminal Gothenburg | GO4LNG Gothenburg | Swedegas AB | Advanced
LNG Terminal | LNG-N-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | LNG terminal in northern Greece / Alexandroupolis | Gastrade S.A. | Advanced | Yes | 8.3 | 170000 | 170000
LNG Terminal | LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | Mugardos LNG Terminal | Reganosa | Advanced | Yes | 0 | 266000 | 0
LNG Terminal | LNG-N-198 | Porto Empedocle LNG | Porto Empedocle LNG | Nuove Energie S.r.l. | Advanced
LNG Terminal | LNG-N-30 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG Limited | Shannon LNG Ltd | Advanced |  | 2.8 | 265000 | 200000
LNG Terminal | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Mugardos LNG Terminal | Reganosa | Advanced | Yes | 0 | 0 | 190000
LNG Terminal | LNG-N-962 | Tallinn LNG | Tallinn LNG | Vopak E.O.S. AS / Vopak LNG Holdings B.V/ Port of Tallinn AS | Advanced | Yes | 4 | 160000 | 160000
LNG Terminal | LNG-N-50 | Gate terminal phase 3 | Gate terminal Rotterdam | Gate | Less-Advanced
LNG Terminal | LNG-N-1146 | Cyprus Gas2EU | CyprusGas2EU | Ministry of Energy, Commerce, Industry and Tourism | Advanced
LNG Terminal | LNG-N-225 | Montoir LNG Terminal Expansion | Montoir LNG Terminal | Elengy | Less-Advanced
LNG Terminal | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | Fos Cavaou LNG Terminal | Fosmax LNG | Less-Advanced
LNG Terminal | LNG-N-912 | Skulte LNG | FRU | AS Skulte LNG Terminal | Less-Advanced | Yes | 1.5 | 170000 | 700000
LNG Terminal | LNG-N-1198 | LNG Terminal Brunsbuettel | LNG Terminal Brunsbüttel (German LNG) | Gasunie Deutschland Transport Service GmbH | Less-Advanced
LNG Terminal | LNG-N-947 | FSRU Polish Baltic Sea Coast | FSRU Polish Baltic Sea Coast | GAZ-SYSTEM S.A. | Less-Advanced
LNG Terminal | LNG-N-1231 | Inisfree LNG | Inisfree LNG | NextDecade LNG | Less-Advanced
LNG Terminal | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Mugardos LNG Terminal | Reganosa | Less-Advanced | Yes | 3.6 | 0 | 0
LNG Terminal | LNG-N-742 | Zeebrugge LNG Terminal - 3rd Jetty | Zeebrugge LNG Terminal | Fluxys LNG | Less-Advanced | Yes | 0 | 0 | 0
LNG Terminal | LNG-N-824 | LNG Terminal in Klaipeda | FSRU Independence | AB Klaipėdos Nafta | Less-Advanced | Yes | 3.7 | 160000 | 170000
LNG Terminal | LNG-N-79 | Paldiski LNG Terminal | Paldiski LNG Terminal | Balti Gaas plc | Less-Advanced | Yes | 1.2 | 160000 | 160000
LNG Terminal | LNG-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | AGRI - Regazification Terminal | AGRI LNG Project Company SRL (RO) | Less-Advanced |  | 8 | 280000 | 160000

## Underground Storages
Underground Storages
Type | Code | Project Name | UGS Facility | Type | Promoter | Maturity Status | WGV (mcm)
Storage Facility | UGS-F-242 | Cornegliano UGS | Cornegliano UGS | Depleted Field | ITAL Gas Storage | FID | 800
Storage Facility | UGS-F-1045 | Bordolano Second phase | Bordolano | Depleted Field | STOGIT S.p.A. | FID | 757
Storage Facility | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Stogit Enhancements and New Developments | Depleted Field | STOGIT | FID | 588
Storage Facility | UGS-N-233 | Depomures | Targu Mures | Depleted Field | Engie Romania SA | Advanced | 100
Storage Facility | UGS-N-233 | Depomures | Targu Mures | Depleted Field | Engie Romania SA | Advanced | 200
Storage Facility | UGS-N-374 | Enhancement of Incukalns UGS | Incukalns Underground Gas Storage | Aquifer | JSC "Conexus Baltic Grid" | Advanced | 0
Storage Facility | UGS-N-294 | Islandmagee Gas Storage Facility | Islandmagee Storage Facility | Salt Cavern | Islandmagee Storage Limited | Advanced | 420
Storage Facility | UGS-N-356 | Underground Gas Storage Velke Kapusany | Underground Gas Storage Velke Kapusany | Depleted Field | NAFTA a.s. (joint stock company) | Advanced | 340
Storage Facility | UGS-N-138 | UGS Chiren Expansion | UGS Chiren | Depleted Field | Bulgartransgaz EAD | Advanced | 450
Storage Facility | UGS-N-385 | South Kavala Underground Gas Storage facility | South Kavala | Depleted Field | Hellenic Republic Asset anagement Fund | Less-Advanced
Storage Facility | UGS-N-371 | Sarmasel undeground gas storage in Romania | UGS SARMASEL | Depleted Field | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced | 650
Storage Facility | UGS-N-1229 | Underground Natural Gas Storage in Dumrea Area (UGS Dumrea) | UGS Dumrea | Salt Cavern | Ministry of Infrastructure and Energy of Albania and Albgaz sh.a. | Advanced | 1200
Storage Facility | UGS-N-1229 | Underground Natural Gas Storage in Dumrea Area (UGS Dumrea) | UGS Dumrea | Salt Cavern | Ministry of Infrastructure and Energy of Albania and Albgaz sh.a. | Advanced | 300
Storage Facility | UGS-N-914 | UGS Damasławek | UGS Damasławek | Salt Cavern | GAZ-SYSTEM S.A. | Less-Advanced

## Time Schedule
Time Schedule
Type | Code | Project Name | Host Country | Promoter | Maturity Status | FID Ends | Feasibility Starts | Feasibility Ends | FEED Starts | FEED Ends | Permitting Phase Starts | Permitting Phase Ends | Construction Starts | Construction Ends | Commissioning Starts | Commissioning Ends | Grant Obtention Date | Schedule Status | Delay Explanation
Pipeline including CS | TRA-F-1138 | South Caucasus Pipeline - (Future) Expansion - SCP-(F)X | Azerbaijan | SOCAR Midstream Operations LLC | FID | 2013-12-17 | 2010-04-01 | 2013-01-01 | 2011-01-01 | 2012-01-01 | 2010-09-01 | 2014-04-01 | 2014-01-01 | 2018-09-01 | 2018 | 2018 |  | On time
Pipeline including CS | TRA-F-43 | Val de Saône project | France | GRTgaz | FID | 2015-09-07 | 2012-09-01 | 2013-07-31 | 2013-07-31 | 2014-07-31 | 2014-10-01 | 2016-06-30 | 2016-06-30 | 2018-11-01 | 2018 | 2018 | 2015-09-01 | On time
Pipeline including CS | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | France | GRTgaz | FID | 2015-07-24 | 2014-10-14 | 2015-08-31 | 2015-09-01 | 2016-12-31 |  |  | 2017-03-31 | 2018-11-30 | 2018 | 2018 |  | On time
Pipeline including CS | TRA-F-331 | Gascogne Midi | France | TIGF - GRTgaz | FID | 2014-09-15 |  |  | 2015-03-15 | 2016-06-15 | 2016-02-15 | 2017-07-16 | 2017-06-15 | 2018-07-15 | 2018 | 2018
Pipeline including CS | TRA-F-208 | Reverse Flow TENP Germany | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | 2015-01-01 | 2012-10-01 | 2015-01-01 | 2016-07-01 | 2016-12-31 | 2016-12-01 | 2018-01-01 | 2017-06-01 | 2018-06-01 | 2018 | 2018 |  | On time
Pipeline including CS | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | Germany | bayernets GmbH | FID | 2015-04-07 | 2009-03-01 | 2009-05-19 | 2009-08-03 | 2009-12-08 | 2013-11-15 | 2016-02-15 | 2016-10-01 | 2018-10-31 | 2018 | 2018 |  | Delayed | Because of extensive negotiations about the rights of way and the late finalisation of the approval procedure the project is, in comparison to the original planning, delayed. The commissioning will take place in October 2018. This has no impact on the planed capacity offer.
LNG Terminal | LNG-F-147 | Revythoussa (2nd upgrade) | Greece | DESFA S.A. | FID | [8 empty] | 2018-08-31 | 2018 | 2018 |  | Delayed | Delays in the contract award procedure Delays due to the capital controls imposed in Greece in July 2015 Delays due to the need to shut down the terminal in order to perform the tie-ins, in a low demand season.
Pipeline including CS | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Italy | Snam Rete Gas S.p.A. | FID | [9 empty] | 2018 | 2018 |  | On time
Storage Facility | UGS-F-242 | Cornegliano UGS | Italy | ITAL Gas Storage | FID | 2015-11-05 |  |  | 2009-06-11 | 2011-03-14 |  | 2011-03-15 | 2015-12-16 | 2018-11-30 | 2018 | 2018 | 2011-03-15
Pipeline including CS | TRA-F-1228 | Interconnection with UGS in Cornegliano Laudense | Italy | Snam Rete Gas S.p.A. | FID | [9 empty] | 2018 | 2018
Pipeline including CS | TRA-F-230 | Reverse Flow Transitgas Switzerland | Switzerland | FluxSwiss | FID | [9 empty] | 2018 | 2018
Pipeline including CS | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | Turkey | SOCAR (The State Oil Company of the Azerbaijan Republic) | FID | 2013-12-17 | 2013-01-01 | 2013-03-31 | 2012-09-01 | 2014-05-01 | 2014-04-01 | 2014-07-24 | 2014-06-26 | 2019-06-30 | 2018 | 2019 | 2016-03-01 | On time | ​
Pipeline including CS | TRA-F-954 | TAG Reverse Flow | Austria | Trans Austria Gasleitung GmbH | FID | [9 empty] | 2019 | 2019 |  | Delayed
LNG Terminal | LNG-F-229 | Zeebrugge LNG Terminal - 5th Tank | Belgium | Fluxys LNG | FID | [9 empty] | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Croatia | Plinacro Ltd | FID | 2017-12-15 | 2014-11-01 | 2015-03-16 |  |  | 2015-06-16 | 2018-05-31 | 2018-01-01 | 2019-03-31 | 2019 | 2019 |  | Rescheduled
Pipeline including CS | TRA-F-752 | Capacity4Gas – DE/CZ | Czechia | NET4GAS, s.r.o. | FID | 2017-03-07 | 2017-03-08 | 2017-10-31 | 2017-07-01 | 2019-06-13 | 2017-07-20 | 2019-12-31 | 2018-06-01 | 2021-09-30 | 2019 | 2021 |  | On time
Pipeline including CS | TRA-F-895 | Balticconnector | Estonia | Elering AS | FID | 2016-10-26 | 2006-01-01 | 2006-12-31 | 2016-01-01 | 2016-02-29 | 2012-12-02 | 2019-01-01 | 2017-11-30 | 2019-12-27 | 2019 | 2019 | 2016-10-21 | On time
Pipeline including CS | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Estonia | Elering AS | FID | 2016-10-26 | 2015-01-01 | 2016-01-01 | 2015-05-01 | 2016-05-31 | 2015-09-01 | 2019-06-30 | 2018-06-17 | 2019-12-31 | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-928 | Balticconnector Finnish part | Finland | Baltic Connector Oy | FID | 2016-10-26 | 2006-01-01 | 2006-12-31 | 2016-01-01 | 2017-05-01 | 2012-12-02 | 2018-05-01 | 2017-11-30 | 2019-12-27 | 2019 | 2019 | 2016-10-21 | On time
Pipeline including CS | TRA-F-340 | CS Wertingen | Germany | bayernets GmbH | FID | 2016-05-23 | 2015-07-01 | 2015-11-13 |  |  | 2016-04-29 | 2017-04-03 | 2017-09-27 | 2019-12-31 | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-937 | Nord Stream 2 | Germany | Nord Stream 2 AG | FID | 2015-09-04 | 2012-01-30 | 2012-10-08 |  |  | 2013-04-08 | 2018-06-30 | 2018-02-01 | 2019-10-31 | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Greece | Trans Adriatic Pipeline AG | FID | 2013-12-17 |  |  | 2008-01-01 | 2013-03-25 | 2011-09-01 | 2018-05-01 | 2016-05-16 | 2019-12-01 | 2019 | 2019 | 2017-08-02 | On time | N/A
Pipeline including CS | TRA-F-941 | Metering and Regulating station at Nea Messimvria | Greece | DESFA S.A. | FID |  |  |  | 2016-05-04 | 2018-03-31 |  |  |  |  | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | Hungary | FGSZ Ltd. | FID | 2017-06-13 | 2016-09-01 | 2017-07-31 | 2018-07-01 | 2018-10-03 | 2018-07-01 | 2018-09-30 | 2018-10-01 | 2019-12-31 | 2019 | 2019 | 2015-10-14 | On time
Pipeline including CS | TRA-F-1193 | TAP interconnection | Italy | Snam Rete Gas S.p.A. | FID | [9 empty] | 2019 | 2019
Pipeline including CS | TRA-F-902 | Capacity increase at IP Lanžhot entry | Slovakia | eustream,a.s. (a joint-stock company) | FID | 2017-12-12 | 2015-06-30 | 2015-10-31 | 2015-09-01 | 2017-07-31 | 2017-08-01 | 2018-02-28 | 2018-02-01 | 2019-11-30 | 2019 | 2019 |  | On time
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | Bulgaria | ICGB a.d. | FID | 2015-12-10 | 2009-05-01 | 2009-07-31 | 2010-08-01 | 2016-03-31 | 2010-08-01 | 2018-06-30 | 2018-09-02 | 2020-06-30 | 2020 | 2025 |  | Delayed | ​Extension in permitting procedures for authorization of construction and of Exemption Procedure for new gas infrastructure. Requirement by Bulgarian authorities for conducting public procurement procedures for construction phase in accordance with Public Procurement Act (PPA) and received appeals under PPA causing delays.
Pipeline including CS | TRA-F-918 | Capacity4Gas – CZ/SK | Czechia | NET4GAS, s.r.o. | FID | 2017-03-07 |  |  | 2017-04-20 | 2018-06-30 | 2018-03-15 | 2018-08-15 | 2019-05-01 | 2020-09-30 | 2020 | 2020 |  | On time
Storage Facility | UGS-F-1045 | Bordolano Second phase | Italy | STOGIT S.p.A. | FID | [9 empty] | 2020 | 2020
Pipeline including CS | TRA-F-1241 | Interconnection with production in Gela | Italy | Snam Rete Gas S.p.A. | FID | [9 empty] | 2020 | 2020
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | Poland | GAZ-SYSTEM S.A. | FID | 2017-11-05 |  |  | 2013-09-23 | 2017-08-11 | 2014-11-05 | 2017-08-11 |  |  | 2020 | 2020
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | Romania | SNTGN Transgaz S.A. | FID | 2016-11-30 | 2014-01-01 | 2014-12-31 | 2016-01-19 | 2017-06-30 | 2014-01-01 | 2018-02-28 | 2017-12-01 | 2022-09-30 | 2020 | 2022 | 2016-09-09 | Rescheduled | Phase I – on time. FID taken in November 2016. Comissioning in 2019 Phase II – rescheduled to accomodate the result of the Open Season Procedure which took place in December 2017
LNG Terminal | LNG-F-178 | Musel LNG terminal | Spain | Enagás Transporte, S.A.U. | FID | [9 empty] | 2020 | 2020
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgaria | Bulgartransgaz EAD | FID |  | 2008-08-01 | 2017-08-01 |  |  | 2009-09-01 | 2020-02-03 | 2014-09-01 | 2021-06-01 | 2021 | 2024 | 2016-04-27 | Delayed | Fine-tuning the schedule to reflect the degree of project implementation. An update of the Implementation Schedule has been made consequently to the technical and economic analysis of the operation of the new equipment (installed during Stage 1 of the CS modernization) in connection with the second stage of the CS modernisation (Phase 2).
Pipeline including CS | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | Lithuania | AB Amber Grid | FID | 2018-03-31 | 2012-02-01 | 2013-02-01 | 2015-05-01 | 2016-09-15 | 2016-07-01 | 2016-09-27 | 2018-03-31 | 2021-06-30 | 2021 | 2021 | 2015-10-15 | On time
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | Poland | GAZ-SYSTEM S.A. | FID |  |  |  | 2015-06-18 | 2019-10-11 | 2015-12-09 | 2019-10-11 |  |  | 2021 | 2021
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | FID |  |  |  | 2015-04-16 | 2018-08-31 | 2016-08-22 | 2018-08-31 |  |  | 2021 | 2021
Pipeline including CS | TRA-F-190 | Poland - Slovakia interconnection | Slovakia | eustream,a.s. (a joint-stock company) | FID | 2018-03-31 | 2011-05-02 | 2013-07-31 | 2015-10-01 | 2018-04-30 | 2015-08-01 | 2018-09-30 | 2018-05-01 | 2020-11-30 | 2021 | 2021 | 2017-12-18 | Delayed | 1)Unexpected decision of the relevant building authority to merge the localisation proceedings prior to obtainment of the Localisation permit for the pipeline and the compressor station and subsequent obligation to update Zoning Plans of Košice and Prešov Self-governing Regions. 2)Delay in finalization of the cross-border environmental impact assessment by the Slovak and the Polish nature protection authorities.3)Necessity to prolong public procurement proceeding due to the request of tenderers for extension of time period for submission of the initial tender bids. 4)Prolongation of the tendering process caused postponement of submission of documentation by the winning bidder all caused delay of detailed engineering. 5)Request of DG ENVIRO to deliver updated appropriate environmental impact assessment according to the chosen final routing of the pipeline.
LNG Terminal | LNG-F-183 | Tenerife LNG Terminal | Spain | Gascan | FID | [9 empty] | 2021 | 2021 |  | Rescheduled
Pipeline including CS | TRA-F-1028 | Albania - Kosovo Gas Pipeline | Albania | Min. of Infrastructure and Energy AL & Min. of Economic Development KO | FID | 2016-07-12 | 2019-01-01 | 2020-01-01 | [6 empty] | 2022 | 2022 |  | On time | We don't see any delay for this Project.
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Bulgaria | Ministry of Energy | FID | 2012-12-03 | 2011-12-01 | 2012-12-01 |  |  | 2013-06-03 | 2019-12-02 | 2020-03-02 | 2022-03-01 | 2022 | 2022 |  | Delayed | • Large archeological survey and researches along the route. • The Public procurement procedure for selection of a Contractor for the design phase, including apeal to Court, took rather long. • Need for amendment of the Detailed Development Plan. • The implementation of the project on Bulgarian territory, according to the requirements under OPIC 2014-2020 has exclusive conditionality with the Serbian section, namely the start of construction works on Serbian territory is an essential prerequisite to commission the grant under Operational Programme Innovation and Competitiveness for beginning of the construction works on the Bulgarian territory.
Pipeline including CS | TRA-F-1271 | Compressor Station Krummhoern | Germany | Open Grid Europe GmbH | FID | [9 empty] | 2022 | 2022
Pipeline including CS | TRA-F-329 | ZEELINK | Germany | Open Grid Europe GmbH and Thyssengas GmbH | FID | 2018-01-01 | [6 empty] | 2019-04-01 | 2023-03-31 | 2023 | 2023 |  | Rescheduled
LNG Terminal | LNG-F-272 | Upgrade of LNG terminal in Świnoujście | Poland | GAZ-SYSTEM S.A. | FID | 2018-01-01 | 2015-04-01 | 2017-12-01 | 2017-12-01 | 2018-06-01 |  |  | 2018-06-01 | 2023-01-01 | 2023 | 2023
Storage Facility | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Italy | STOGIT | FID | [6 empty] | 2025-01-01 |  |  | 2027 | 2027
LNG Terminal | LNG-F-163 | Gran Canaria LNG Terminal | Spain | Gascan | FID | [9 empty] | 2027 | 2027 |  | Rescheduled
Pipeline including CS | TRA-N-291 | NOWAL - Nord West Anbindungsleitung | Germany | GASCADE Gastransport GmbH | Advanced | [5 empty] | 2014-01-01 | 2016-01-01 |  |  | 2018 | 2020 |  | On time
LNG Terminal | LNG-N-82 | LNG terminal Krk | Croatia | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | Advanced | 2018-06-30 | 2012-07-12 | 2014-01-15 | 2017-03-28 | 2017-12-13 | 2013-10-01 | 2018-05-31 | 2018-06-30 | 2019-11-01 | 2019 | 2023 | 2017-12-18 | Rescheduled | In comparison with last TYNDP, the project is rescheduled with new beginning of operation from year 2019.
Pipeline including CS | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Croatia | Plinacro Ltd | Advanced | 2018-06-29 |  |  |  |  | 2009-07-02 | 2019-12-02 | 2018-07-02 | 2019-12-02 | 2019 | 2019 |  |  | ​This project completely depends on LNG terminal project on island of Krk
Pipeline including CS | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | Germany | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | Advanced | [5 empty] | 2017-01-01 | 2018-01-01 |  |  | 2019 | 2020
Pipeline including CS | TRA-N-1267 | Upgrade Sülstorf station | Germany | NGT GmbH / GUD GmbH & Co. KG / Fluxys D GmbH / ONTRAS GmbH | Advanced |  |  |  | 2017-01-01 | 2019-01-01 |  |  |  |  | 2019 | 2019
Pipeline including CS | TRA-N-12 | GALSI Pipeline Project | Italy | Galsi S.p.A. | Advanced | 2019-11-30 | 2006-01-01 | 2006-12-31 | 2007-01-01 | 2010-12-31 | 2008-07-31 | 2018-11-30 | 2019-12-01 | 2022-12-31 | 2019 | 2019 | 2010-08-13 | On time
Pipeline including CS | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | Romania | SNTGN Transgaz SA | Advanced | 2018-06-01 | 2016-12-12 | 2017-04-28 | 2017-05-01 | 2018-06-22 | 2017-03-19 | 2018-07-31 | 2018-12-18 | 2019-12-31 | 2019 | 2019 |  | On time
Pipeline including CS | TRA-N-357 | NTS developments in North-East Romania | Romania | SNTGN Transgaz SA | Advanced | 2018-04-30 | 2014-02-28 | 2018-01-01 | 2016-01-01 | 2018-01-01 | 2016-01-01 | 2018-01-01 | 2018-06-01 | 2019-10-31 | 2019 | 2019 |  | Delayed | Delays in obtaining the necessary approvals, permits and authorizations
Pipeline including CS | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | Romania | SNTGN Transgaz SA | Advanced |  | 2016-10-24 | 2017-05-31 | 2017-08-01 | 2018-01-31 | 2017-03-01 | 2017-12-30 | 2018-11-01 | 2019-07-30 | 2019 | 2019
Pipeline including CS | TRA-N-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | Romania | SNTGN Transgaz SA | Advanced | 2018-08-31 | 2018-01-01 | 2018-08-31 | 2018-01-01 | 2018-08-31 | 2018-01-01 | 2018-08-31 | 2018-08-31 | 2019-12-31 | 2019 | 2019
Pipeline including CS | TRA-N-1169 | Trans-Balkan Bi-directional Flow | Ukraine | PJSC "UKRTRANSGAZ" | Less-Advanced | [9 empty] | 2019 | 2019
Pipeline including CS | TRA-N-1303 | IAEF - Vlora ccgt | Albania | Albgaz Sha | Less-Advanced | 2019-09-12 | 2017-03-08 | 2018-02-01 | 2018-09-06 | 2018-09-06 | 2018-11-14 | 2019-03-12 | 2019-11-14 | 2020-11-28 | 2020 | 2020 | 2016-01-28 | On time
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Croatia | Plinacro Ltd | Advanced | 2018-11-30 |  |  |  |  | 2011-01-01 | 2019-01-01 | 2019-12-02 | 2020-12-01 | 2020 | 2020
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Croatia | Plinacro Ltd | Advanced | 2018-07-02 | 2015-09-01 | 2016-10-01 |  |  | 2009-07-02 | 2020-01-01 | 2018-10-01 | 2020-01-01 | 2020 | 2020 | 2015-11-24 | On time | The preparatory work will be performed in phases, depending on the development of the LNG project,
LNG Terminal | LNG-N-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Greece | Gastrade S.A. | Advanced | 2018-11-30 | 2014-01-01 | 2014-06-01 | 2017-03-10 | 2017-09-29 | 2010-12-01 | 2015-01-20 | 2018-12-03 | 2020-09-30 | 2020 | 2020 | 2015-04-16 | Delayed | Permitting phase completed 1Q2015 and FEED completed in September 2017. Final negotiations with Bulgarian Energy Holding (BEH) and Public Gas Corporation (DEPA) for acquiring stakes in GASTRADE is estimated to be completed by end of April 2018. GASTRADE plans to initiate a Market Test in May 2018 and critical mass terminal use agreements are anticipated by October 2018. Completion of financing agreements and EPC contract awards (subject to FID) required for FID. FID is planned for November 2018. 24 months required from FID to commercial start-up.
Pipeline including CS | TRA-N-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Greece | Gastrade S.A. | Advanced | 2018-11-30 | 2014-01-01 | 2014-06-01 | 2017-03-10 | 2017-09-29 | 2010-12-01 | 2015-01-20 | 2018-12-03 | 2020-09-30 | 2020 | 2020 | 2015-04-16 | Delayed | Permitting phase completed 1Q2015 and FEED completed in September 2017. Final negotiations with Bulgarian Energy Holding (BEH) and Public Gas Corporation (DEPA) for acquiring stakes in GASTRADE is estimated to be completed by end of April 2018. GASTRADE plans to initiate a Market Test in May 2018 and critical mass terminal use agreements are anticipated by October 2018. Completion of financing agreements and EPC contract awards (subject to FID) required for FID. FID is planned for November 2018. 24 months required from FID to commercial start-up.
Pipeline including CS | TRA-N-975 | Sardinia Gas Transportation Network | Italy | Società Gasdotti Italia | Advanced |  | 2015-07-01 | 2015-07-31 | 2015-08-01 | 2015-12-31 | 2016-03-01 |  |  |  | 2020 | 2021 |  | On time
Storage Facility | UGS-N-374 | Enhancement of Incukalns UGS | Latvia | JSC "Conexus Baltic Grid" | Advanced |  | 2017-02-20 | 2017-11-28 |  |  | 2014-05-01 | 2020-12-31 | 2014-03-01 | 2024-12-31 | 2020 | 2024 | 2017-05-19 | Rescheduled | Lack of financing and change in market conditions.
Pipeline including CS | TRA-N-621 | Poland - Ukraine Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced |  |  |  | 2016-09-01 | 2018-09-28 | 2016-10-11 | 2018-09-28 |  |  | 2020 | 2020
Storage Facility | UGS-N-233 | Depomures | Romania | Engie Romania SA | Advanced | 2018-06-30 | 2008-06-01 | 2009-06-01 | 2011-06-01 | 2012-06-01 | 2012-06-01 | 2017-09-26 | 2015-07-10 | 2023-03-01 | 2020 | 2023 |  | Delayed | The main delay encountered is related to permit granting for part of the investment (i.e. the last sector of the main gathering pipeline). The construction of the main gathering pipeline was essential for the entire project and a pre-requisite for implementing the rest of the project (dehydration and compression station and subsequent expansion to 600 mcm of the capacity). The permit was eventually obtained at the end of 2017.
Pipeline including CS | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | Romania | SNTGN Transgaz SA | Advanced | 2018-06-01 | 2014-07-01 | 2016-01-30 | 2016-06-01 | 2018-02-28 | 2015-01-01 | 2018-05-30 | 2019-01-01 | 2020-10-30 | 2020 | 2020 |  | On time
LNG Terminal | LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | Spain | Reganosa | Advanced | 2018-08-21 | 2015-02-11 | 2015-12-15 | 2016-04-06 | 2017-06-27 | 2017-10-18 | 2018-08-21 | 2018-11-14 | 2020-09-29 | 2020 | 2020 |  | On time
Pipeline including CS | TRA-N-950 | Guitiriz - Lugo - Zamora pipeline | Spain | Reganosa | Advanced | 2019-08-09 | 2017-07-31 | 2017-12-01 | 2017-12-04 | 2018-12-28 | 2018-11-05 | 2019-08-09 | 2019-08-12 | 2020-11-13 | 2020 | 2020 |  | On time
LNG Terminal | LNG-N-32 | Project GO4LNG LNG terminal Gothenburg | Sweden | Swedegas AB | Advanced | 2017-12-31 | 2012-01-01 | 2012-06-01 | 2017-01-01 | 2017-01-01 | 2013-10-01 | 2014-05-01 | 2018-01-01 | 2020-10-31 | 2020 | 2020 |  |  | Slower market development than expected.
Pipeline including CS | TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | Ukraine | PJSC UKRTRANSGAZ | Advanced |  | 2015-01-01 | 2016-12-31 | 2016-12-01 | 2018-07-31 | 2016-12-01 | 2018-09-30 | 2018-08-01 | 2020-03-31 | 2020 | 2020
Pipeline including CS | TRA-N-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | United Kingdom | GNI (UK) Limited | Advanced | 2020-12-31 | 2017-07-22 | 2018-11-28 | 2019-01-01 | 2019-12-31 | 2020-01-01 | 2020-12-31 | 2021-01-01 | 2021-12-31 | 2020 | 2020 | 2017-03-14 | On time
Pipeline including CS | TRA-N-21 | Bidirectional Austrian-Czech Interconnector (BACI) | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | [5 empty] | 2015-10-27 |  |  | 2021-10-01 | 2021 | 2021 | 2015-04-30
Pipeline including CS | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Croatia | Plinacro Ltd | Advanced | 2019-11-01 | 2014-09-01 | 2014-12-01 |  |  | 2015-10-14 | 2021-12-01 | 2019-12-02 | 2021-12-01 | 2021 | 2021 | 2016-04-25
Pipeline including CS | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Croatia | Plinacro Ltd | Advanced | 2019-01-01 |  |  |  |  | 2014-08-25 | 2021-01-01 | 2020-01-01 | 2021-01-01 | 2021 | 2021
Pipeline including CS | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | Czechia | NET4GAS, s.r.o. | Advanced | 2019-08-31 | 2012-03-01 | 2014-02-01 | 2012-03-01 | 2018-06-01 | 2015-05-01 | 2019-11-30 | 2019-12-16 | 2021-09-30 | 2021 | 2021 | 2014-01-01 | Rescheduled | Particular dates have been changed due to the fact that there is a change in permitting process caused by amendment of the Building Act valid as of January 1, 2018.
LNG Terminal | LNG-N-198 | Porto Empedocle LNG | Italy | Nuove Energie S.r.l. | Advanced | 2017-10-01 | 2006-01-01 |  | 2006-03-01 | 2006-09-28 | 2009-01-01 | 2009-10-22 | 2018-12-31 | 2021-12-31 | 2021 | 2021 |  | Delayed | After the issues of the National Energy Strategy (SEN) in October 2017, Nuove Energie is reconsidering and reevaluating the project.
Pipeline including CS | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | [5 empty] | 2015-10-27 | 2019-07-01 |  | 2022-06-01 | 2022 | 2022
Pipeline including CS | TRA-N-423 | GCA Mosonmagyaróvár | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | [5 empty] | 2015-10-27 | 2019-07-01 |  | 2022-05-01 | 2022 | 2022
Pipeline including CS | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | Bulgaria | Bulgartransgaz EAD | Advanced | [8 empty] | 2022-06-01 | 2022 | 2022 | 2017-05-17 | On time
Pipeline including CS | TRA-N-593 | Varna-Oryahovo gas pipeline | Bulgaria | Bulgartransgaz EAD | Advanced | [8 empty] | 2022-06-01 | 2022 | 2022 | 2017-05-17 | On time
Pipeline including CS | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgaria | Bulgartransgaz EAD | Advanced | [8 empty] | 2022-06-01 | 2022 | 2022 | 2017-05-17 | On time
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Croatia | Plinacro Ltd | Advanced | 2019-01-01 | 2012-05-01 | 2014-02-01 |  |  | 2009-07-21 | 2023-01-01 | 2020-01-01 | 2023-01-01 | 2022 | 2023 |  |  | Dynamics of project implementation depends on the dynamics of TAP project implementation.
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Croatia | Plinacro Ltd | Advanced | 2019-10-01 |  |  |  |  | 2018-09-03 | 2020-01-01 | 2020-03-02 | 2022-12-01 | 2022 | 2022 | 2016-04-25 | Rescheduled
Pipeline including CS | TRA-N-136 | Czech-Polish Gas Interconnector (CPI) | Czechia | NET4GAS, s.r.o. | Advanced | 2019-12-31 | 2009-01-01 | 2012-12-31 | 2014-11-01 | 2017-10-31 | 2016-02-01 | 2019-11-01 | 2021-07-01 | 2022-12-31 | 2022 | 2022 | 2018-01-01 | Delayed | Delay was caused by political decisions.
Pipeline including CS | TRA-N-394 | Norwegian tie-in to Danish upstream system | Denmark | Energinet.dk | Advanced | 2018-12-01 | 2015-09-01 | 2016-12-15 | 2018-05-01 | 2022-02-27 | 2018-01-01 | 2019-07-01 | 2020-01-01 | 2022-10-01 | 2022 | 2022 |  | On time
Pipeline including CS | TRA-N-780 | Baltic Pipe project – onshore section in Denmark | Denmark | Energinet.dk | Advanced | 2018-12-01 | 2015-09-01 | 2016-12-15 | 2018-06-11 | 2020-02-27 | 2017-12-21 | 2019-07-01 | 2020-03-10 | 2022-10-01 | 2022 | 2022 |  | On time
LNG Terminal | LNG-N-962 | Tallinn LNG | Estonia | Vopak E.O.S. AS / Vopak LNG Holdings B.V/ Port of Tallinn AS | Advanced |  | 2012-01-01 |  | 2016-01-01 |  | 2012-01-01 | 2018-01-01 |  |  | 2022 | 2022 |  | Delayed | The project is delayed because of the uncertainty and delay in other former LNG Terminal projects in the region, as this affects the project scope, feasibility, FEED and FID.
Pipeline including CS | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | France | TIGF | Advanced | 2019-04-15 | 2016-01-04 | 2017-01-31 | 2016-01-19 | 2019-06-30 | 2019-02-17 | 2020-12-31 | 2020-12-01 | 2022-10-31 | 2022 | 2022 | 2016-01-19
Pipeline including CS | TRA-N-10 | Poseidon Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | 2019-06-01 |  |  | 2017-08-01 | 2019-01-01 | 2017-08-01 | 2019-06-01 | 2019-09-01 | 2022-09-01 | 2022 | 2025 |  | Rescheduled | As a result of project promoter decision to extend Poseidon pipeline up to the Turkish-Greek border, the project development timeline has been rescheduled.
Pipeline including CS | TRA-N-123 | Városföld CS | Hungary | FGSZ Ltd. | Advanced | 2019-03-01 | 2016-09-01 | 2017-07-31 | 2019-01-01 | 2020-01-31 | 2019-10-01 | 2020-04-30 | 2020-05-01 | 2022-10-01 | 2022 | 2022 | 2015-10-14 | On time
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | Hungary | FGSZ Ltd. | Advanced | 2019-07-31 | 2016-05-01 | 2017-12-30 | 2019-12-31 | 2020-12-31 | 2016-11-01 | 2019-12-31 | 2020-01-01 | 2022-10-01 | 2022 | 2023 |  | Delayed | Time schedule in the last TYNDP was estimated according to the data from the pre-feasibility study with lower level of details. Slower progress of project as planned.
Pipeline including CS | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | Hungary | FGSZ Ltd. | Advanced | 2019-03-15 | 2016-09-01 | 2017-07-31 | 2019-01-01 | 2020-01-31 | 2019-10-01 | 2020-04-30 | 2020-05-01 | 2022-12-31 | 2022 | 2022 | 2016-11-08 | On time
LNG Terminal | LNG-N-30 | Shannon LNG Terminal and Connecting Pipeline | Ireland | Shannon LNG Ltd | Advanced | 2018-11-30 | 2006-05-01 | 2007-09-01 | 2017-11-01 | 2018-10-31 | 2007-09-01 | 2010-12-31 | 2018-11-30 | 2022-04-01 | 2022 | 2022 |  | On time | Regulatory uncertainty, Low rate of return and lack of proper transposition of EU regulation.
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Italy | Società Gasdotti Italia | Advanced | 2018-12-31 | 2014-01-01 | 2014-12-31 | 2015-01-01 | 2015-01-31 | 2015-01-01 | 2019-12-31 | 2019-03-01 | 2022-12-31 | 2022 | 2022 |  | On time
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | Poland | GAZ-SYSTEM S.A. | Advanced |  |  |  | 2017-08-03 | [5 empty] | 2022 | 2022
Pipeline including CS | TRA-N-273 | Poland - Czech Republic Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced |  |  |  | 2015-07-28 | 2017-12-29 | 2016-07-19 | 2017-12-29 |  |  | 2022 | 2022
Pipeline including CS | TRA-N-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | Poland | GAZ-SYSTEM S.A. | Advanced |  |  |  | 2017-11-28 | [5 empty] | 2022 | 2022
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | 2019-07-01 |  |  | 2019-07-01 | 2021-07-01 |  |  | 2021-07-01 | 2022-12-31 | 2022 | 2022 |  | Rescheduled
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Slovenia | Plinovodi d.o.o. | Less-Advanced | 2019-07-01 |  |  | 2019-07-01 | 2021-12-01 |  |  | 2020-10-01 | 2023-12-31 | 2022 | 2023 |  | Rescheduled
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Slovenia | Plinovodi d.o.o. | Less-Advanced | 2019-07-01 |  |  | 2019-07-01 | 2021-07-01 |  |  | 2021-07-01 | 2022-12-31 | 2022 | 2022 |  | Rescheduled
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Slovenia | Plinovodi d.o.o. | Less-Advanced | 2019-07-01 |  |  | 2019-07-01 | 2021-07-01 |  |  | 2021-07-01 | 2022-12-31 | 2022 | 2022 |  | Rescheduled
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Spain | Enagás Transporte, S.A.U. | Advanced | 2019-06-01 | 2009-01-01 | 2009-01-01 | 2016-01-01 | 2016-12-31 | 2019-05-01 | 2020-11-01 | 2021-04-01 | 2022-12-01 | 2022 | 2022 | 2018-01-25 | Rescheduled
LNG Terminal | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Spain | Reganosa | Advanced |  | 2015-02-11 | 2015-12-15 | 2016-08-24 | 2017-11-14 | 2018-04-04 | 2019-02-05 | 2019-05-29 | 2021-12-21 | 2022 | 2022 |  | On time
Storage Facility | UGS-N-294 | Islandmagee Gas Storage Facility | United Kingdom | Islandmagee Storage Limited | Advanced | 2019-05-31 |  |  | 2018-01-15 | 2018-12-20 |  |  | 2019-09-02 | 2022-05-03 | 2022 | 2022 | 2016-06-17 | Rescheduled | ​The project has been rescheduled due to the availability of finance and the difficult trading conditions within the UK gas market.
Pipeline including CS | TRA-N-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Croatia | Plinacro Ltd | Advanced | 2021-10-01 |  |  |  |  | 2010-01-12 | 2023-10-02 | 2022-01-01 | 2023-10-02 | 2023 | 2023
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Croatia | Plinacro Ltd | Advanced | 2020-01-01 | 2015-09-01 | 2016-10-01 |  |  | 2014-09-01 | 2023-01-01 | 2021-01-01 | 2023-01-01 | 2023 | 2023 | 2015-11-24 |  | Project depend on LNG project
Storage Facility | UGS-N-356 | Underground Gas Storage Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | Advanced | 2020-01-01 | 2019-04-01 | 2019-09-01 | 2020-02-01 | 2021-04-01 | 2017-11-01 | 2021-04-01 | 2021-06-01 | 2023-06-01 | 2023 | 2023
Pipeline including CS | TRA-N-628 | Eastring - Slovakia | Slovakia | eustream, a.s. (a joint stock company) | Advanced |  | 2017-09-01 | 2018-06-30 | 2018-10-01 | 2020-02-28 | 2020-03-01 | 2020-12-31 | 2021-01-01 | 2023-09-30 | 2023 | 2028 | 2017-05-12 | Delayed | Time schedule in the last TYNDP was estimated according to the data from the pre-feasibility study with lower level of details.
Storage Facility | UGS-N-138 | UGS Chiren Expansion | Bulgaria | Bulgartransgaz EAD | Advanced |  | 2015-03-02 | 2019-10-31 | 2020-08-31 | 2022-11-30 | 2021-04-30 | 2022-12-20 | 2021-06-30 | 2024-06-28 | 2024 | 2024 | 2015-10-23 | Delayed | Commissioning: 2024 The delay of the overall PCI implementation is due to delay in the in the implementation of 3D seismic studies. The reasons are that within the tender procedure, the Selection Decision was appealed by one of the bidders and that hindered its successful completion. In the mean time new standard templates for tender procedures were approved by the Bulgarian Ministry of Finance, which from our side let to delay in the preparation of new tender documentation for the 3D seismic studies tendering, which afterwards needed to be re-launch.
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | France | GRTgaz and TIGF | Advanced |  | 2007-03-01 | 2019-12-31 | 2012-09-01 | 2021-12-31 | 2012-09-01 | 2021-12-31 | 2022-03-01 | 2024-11-30 | 2024 | 2024 | 2016-01-19 | On time
Pipeline including CS | TRA-N-31 | Connection of Malta to the European Gas Network - Pipelines | Malta | Ministry For Energy & Water Management - Malta | Advanced | 2020-07-01 | 2013-04-09 | 2015-04-30 | 2018-11-01 | 2020-03-01 | 2017-11-20 | 2020-07-01 | 2023-03-01 | 2024-05-01 | 2024 | 2024 | 2018-01-25 | Ahead of schedule
Pipeline including CS | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | Portugal | REN-Gasodutos, S.A. | Advanced |  | 2015-01-01 | 2015-03-31 | 2015-07-22 |  |  |  |  | 2022-12-31 | 2024 | 2024 | 2015-07-14 | Delayed | In the last edition of the TYNDP, REN was in the permitting process phase, waiting for the Environmental Impact Declaration to be issued by the Competent Authorities. At this moment, REN already received the declaration with a unfavorable decision. As a consequence,it will be necessary to make an adjustment to the initial route, maintaining the same point of interconnection with Spain. Furthermore, the project of the 3rd Interconnection between Portugal and Spain was rescheduled due to the activities that are being developed in the High Level Group for the development of the interconnections between France, Spain and Portugal. It’s important to notice that the Portuguese project has its decision dependent on the STEP project’s decision.
Pipeline including CS | TRA-N-320 | Carregado Compressor Station | Portugal | REN-Gasodutos, S.A. | Advanced |  | 2008-09-01 | 2010-01-01 | 2010-08-01 | 2010-11-01 |  |  |  | 2022-12-31 | 2024 | 2024 |  | Delayed | Demand forecasts decrease due to the economic and financial context in Portugal and in the EU. Decrease in the demand for the CCGTs due to the low prices of the CO2 emissions.The investment in this infrastructure should be decided by 2018, with the commissioning to occur by the end of 2021.The schedule of this project is aligned and is a enabler of the PCI project 5.4 - 3rd interconnection between Portugal and Spain (TRA-N-283, TRA-N-284, TRA-N-285).
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Spain | Enagás Transporte, S.A.U. | Advanced | 2021-05-01 | 2008-01-01 | 2010-01-01 | 2020-01-01 | 2021-05-01 | 2020-09-01 | 2022-12-01 | 2023-01-01 | 2024-12-01 | 2024 | 2024 | 2016-01-19 | Rescheduled
Pipeline including CS | TRA-N-645 | HU-UA reverse flow (Ukrainian section) | Ukraine | PJSC Ukrtransgaz | Less-Advanced | [9 empty] | 2017 | 2017
Pipeline including CS | TRA-N-955 | GUD: Complete conversion to H-gas | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | [9 empty] | 2018 | 2030
Pipeline including CS | TRA-N-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | Germany | ONTRAS Gastransport GmbH | Advanced |  | 2017-07-01 | 2017-10-01 | 2017-10-01 | 2017-12-31 | 2018-01-01 |  |  |  | 2019 | 2019
Pipeline including CS | TRA-N-1200 | Expansion MS Hetlingen | Germany | Gasunie Deutschland Transport Service GmbH | Less-Advanced | [9 empty] | 2019 | 2022
Pipeline including CS | TRA-N-1253 | Trans-Balkan Bi-directional Flow (Moldavia phase) | Moldavia | Moldovatransgaz LLC | Less-Advanced | [9 empty] | 2019 | 2019
Pipeline including CS | TRA-N-1197 | Expansion of the gas infrastructure between BG-TR and BG-RS borders | Bulgaria | Bulgartransgaz EAD | Less-Advanced | [8 empty] | 2022-03-01 | 2020 | 2022
LNG Terminal | LNG-N-1146 | Cyprus Gas2EU | Cyprus | Ministry of Energy, Commerce, Industry and Tourism | Advanced |  | 2017-04-14 | 2017-10-16 | 2017-05-02 | 2018-12-03 | 2017-08-16 | 2019-06-30 | 2018-12-14 | 2020-11-02 | 2020 | 2020 |  | On time
Pipeline including CS | TRA-N-980 | Interconnection Macedonia-Greece | former Yugoslav Republic of Macedonia | MER JSC Skopje | Less-Advanced | [9 empty] | 2020 | 2020
Pipeline including CS | TRA-N-809 | Additional East-West transport | Germany | Gasunie Deutschland Transport Services GmbH | Advanced | [5 empty] | 2018-01-01 |  |  |  | 2020 | 2020
Pipeline including CS | TRA-N-951 | Embedding CS Folmhusen in H-Gas | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | [9 empty] | 2020 | 2020
Pipeline including CS | TRA-N-128 | Compressor Station Kipi | Greece | DESFA S.A. | Less-Advanced | [9 empty] | 2020 | 2020
Pipeline including CS | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | Greece | DESFA S.A. | Less-Advanced | [9 empty] | 2020 | 2020 |  | On time
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Italy | Snam Rete Gas S.p.A. | Less-Advanced | [9 empty] | 2020 | 2025
Pipeline including CS | TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | Lithuania | AB Amber Grid | Less-Advanced | 2020-01-01 | 2017-10-06 | 2018-09-30 | 2018-09-30 | 2019-04-30 | 2019-05-01 | 2020-01-01 | 2020-01-01 | 2020-12-31 | 2020 | 2020 |  | Rescheduled
LNG Terminal | LNG-N-50 | Gate terminal phase 3 | Netherlands | Gate | Less-Advanced | [9 empty] | 2020 | 2020 | 2007-12-31 | Delayed | more time for the market to develop and finalise commercial discussions.
Pipeline including CS | TRA-N-192 | Entry capacity expansion GATE terminal | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | [9 empty] | 2020 | 2020
Pipeline including CS | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | [9 empty] | 2020 | 2030
Pipeline including CS | TRA-N-1268 | Romania-Serbia Interconnection | Romania | SNTGN Tranzgaz SA | Advanced | 2018-10-01 | 2018-02-28 | 2018-08-31 | 2018-03-31 | 2018-12-31 | 2018-03-31 | 2018-12-31 | 2018-10-02 | 2019-04-30 | 2020 | 2020
Pipeline including CS | TRA-N-1064 | Moffat Physical Reverse Flow | United Kingdom | National Grid Gas plc | Less-Advanced | 2020-12-31 | 2017-07-22 | 2018-11-28 | 2019-01-01 | 2019-12-31 | 2020-01-01 | 2020-12-31 | 2021-01-01 | 2021-12-31 | 2020 | 2020 | 2017-03-14 | On time
Pipeline including CS | TRA-N-965 | Interconnection Macedonia-Serbia | former Yugoslav Republic of Macedonia | MER JSC Skopje | Less-Advanced |  | 2009-04-23 | 2010-07-12 |  | 2010-07-12 |  |  |  |  | 2021 | 2021
Pipeline including CS | TRA-N-976 | Interconnection Macedonia-Bulgaria | former Yugoslav Republic of Macedonia | MER JSC Skopje | Less-Advanced |  | 2009-04-23 | 2010-07-12 |  | 2010-07-12 |  |  |  |  | 2021 | 2021 |  |  | MER JSC Skopje for the first time submits its projects in the TYNDP. The possibility of delay is due to the interstate procedures and financing.
LNG Terminal | LNG-N-225 | Montoir LNG Terminal Expansion | France | Elengy | Less-Advanced | 2019-06-01 | [6 empty] | 2019-06-01 | 2021-06-01 | 2021 | 2021 |  | Rescheduled | market was not yet there
LNG Terminal | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | France | Fosmax LNG | Less-Advanced | 2019-06-01 | [5 empty] | 2019-06-01 | 2019-06-01 | 2023-06-01 | 2021 | 2023 |  |  | market was not yet there
LNG Terminal | LNG-N-1198 | LNG Terminal Brunsbuettel | Germany | Gasunie Deutschland Transport Service GmbH | Less-Advanced | [9 empty] | 2021 | 2021
Pipeline including CS | TRA-N-1199 | LNG Terminal Brunsbuettel - Grid Integration | Germany | Gasunie Deutschland Transport Service GmbH | Less-Advanced | [9 empty] | 2021 | 2021
Pipeline including CS | TRA-N-967 | Nea-Messimvria to FYRoM pipeline | Greece | DESFA S.A. | Less-Advanced | [9 empty] | 2021 | 2021 |  | Rescheduled
Pipeline including CS | TRA-N-1276 | Compressor station at Nea Messimvria (3rd unit) | Greece | DESFA S.A. | Less-Advanced | [9 empty] | 2021 | 2021
Pipeline including CS | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | Latvia | JSC "Conexus Baltic Grid" | Advanced |  | 2017-10-06 | 2018-09-30 | [6 empty] | 2021 | 2021 | 2018-03-30 | Rescheduled
LNG Terminal | LNG-N-912 | Skulte LNG | Latvia | AS Skulte LNG Terminal | Less-Advanced | 2019-03-01 | 2015-03-03 | 2016-05-10 | 2018-06-01 | 2019-02-01 | 2019-01-01 | 2019-03-01 | 2019-03-01 | 2021-09-30 | 2021 | 2021 | 2018-08-01
Pipeline including CS | TRA-N-339 | Trans-Caspian | Turkmenistan | W-Stream Caspian Pipeline Company Ltd | Advanced | 2019-12-01 | 2018-03-01 | 2019-02-01 | 2019-02-01 | 2019-11-01 | 2019-06-01 | 2019-11-01 | 2020-04-01 | 2021-09-01 | 2021 | 2022 | 2018-01-25
Pipeline including CS | TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | United Kingdom | Premier Transmission Limited | Less-Advanced | 2019-12-31 | 2018-10-01 | 2018-10-01 | 2019-01-01 | 2019-01-01 | 2018-10-01 | 2019-09-30 | 2021-01-01 | 2021-09-30 | 2021 | 2021 |  | On time | ​This project is linked to the Islandmagee gas storage project and has been subsequently delayed, in line with the gas storage project being delayed – caused by the absence of competitive transmission tariffs for gas storage.
Pipeline including CS | TRA-N-500 | L/H Conversion Belgium | Belgium | Fluxys Belgium | Advanced |  |  |  | 2015-09-01 | [5 empty] | 2022 | 2022 |  | On time
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgaria | Bulgartransgaz EAD | Less-Advanced |  | 2015-08-02 | 2016-02-01 | [5 empty] | 2022-12-23 | 2022 | 2022 |  | Delayed
Pipeline including CS | TRA-N-47 | Reverse capacity from France to Germany at Obergailbach | France | GRTgaz | Less-Advanced |  | 2013-07-01 | 2017-06-30 | [5 empty] | 2022-11-30 | 2022 | 2022 |  | On time
Pipeline including CS | TRA-N-53 | White Stream | Georgia | White Stream Ltd | Less-Advanced | 2021-01-01 | 2018-09-01 | 2019-09-01 | 2019-10-01 | 2020-09-01 | 2020-01-01 | 2020-12-01 | 2021-06-01 | 2022-12-01 | 2022 | 2022 |  | On time
Pipeline including CS | TRA-N-1254 | CS Elten | Germany | Open Grid Europe GmbH and Thyssengas GmbH | Less-Advanced |  | 2018-10-01 | 2019-06-01 |  |  | 2018-10-01 | 2020-04-01 |  |  | 2022 | 2022
Pipeline including CS | TRA-N-971 | Compressor station at Nea Messimvria | Greece | DESFA S.A. | Less-Advanced | [9 empty] | 2022 | 2022 |  | On time
Pipeline including CS | TRA-N-1278 | Compressor station at Ambelia | Greece | DESFA S.A. | Less-Advanced | [9 empty] | 2022 | 2022
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Hungary | Magyar Gáz Tranzit Zrt. | Less-Advanced | [7 empty] | 2020-03-01 | 2022-03-31 | 2022 | 2022
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Hungary | Magyar Gáz Tranzit Zrt. | Less-Advanced | [7 empty] | 2020-03-01 | 2022-03-31 | 2022 | 2022
Pipeline including CS | TRA-N-831 | Vecsés-Városföld gas transit pipeline | Hungary | Magyar Gáz Tranzit Zrt. | Less-Advanced | [7 empty] | 2020-03-01 | 2022-03-31 | 2022 | 2022
LNG Terminal | LNG-N-1231 | Inisfree LNG | Ireland | NextDecade LNG | Less-Advanced | [9 empty] | 2022 | 2022
Pipeline including CS | TRA-N-1227 | Gorizia plant upgrade | Italy | Snam Rete Gas S.p.A. | Less-Advanced | [9 empty] | 2022 | 2022
Pipeline including CS | TRA-N-1265 | Biomethane productions interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | [9 empty] | 2022 | 2022
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | Poland | GAZ-SYSTEM S.A. | Less-Advanced | [9 empty] | 2022 | 2022
LNG Terminal | LNG-N-947 | FSRU Polish Baltic Sea Coast | Poland | GAZ-SYSTEM S.A. | Less-Advanced | 2019-05-31 | 2017-03-31 | 2018-01-31 | 2018-10-31 | 2019-05-31 | 2018-10-31 | 2019-12-31 | 2020-07-31 | 2022-06-30 | 2022 | 2022 |  | On time
Pipeline including CS | TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | Poland | GAZ-SYSTEM S.A. | Less-Advanced | [9 empty] | 2022 | 2022
Pipeline including CS | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | Slovakia | eustream,a.s. (a joint-stock company) | Less-Advanced | [7 empty] | 2020-10-01 | 2022-06-30 | 2022 | 2022
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | [9 empty] | 2022 | 2022
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Slovenia | Plinovodi d.o.o. | Less-Advanced | [9 empty] | 2022 | 2022
LNG Terminal | LNG-N-742 | Zeebrugge LNG Terminal - 3rd Jetty | Belgium | Fluxys LNG | Less-Advanced | [9 empty] | 2023 | 2023 |  | On time
Pipeline including CS | TRA-N-224 | Gaspipeline Brod - Zenica | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | 2019-11-30 | 2017-11-01 | 2019-04-30 | 2019-12-01 | 2021-04-30 | 2020-01-01 | 2021-05-31 | 2022-06-01 | 2023-09-30 | 2023 | 2023 |  |  | Regarding the fact that the part of this project runs through Republic of Srpska Entity, the main obstacle is lack of political support of the RS official representatives, as well as lack of primary gas legislation at the state level in accordance with the Third Energy Package. Also,existing natural gas market is not able to cover assessed project cost related to preliminary activities.
Pipeline including CS | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | Bosnia Herzegovina | BH-GAS d.o.o. | Less-Advanced | 2018-06-30 | 2017-04-01 | 2018-04-01 | 2018-07-01 | 2019-09-30 | 2018-07-01 | 2019-09-30 | 2020-09-01 | 2021-12-30 | 2023 | 2023
Pipeline including CS | TRA-N-654 | Eastring - Bulgaria | Bulgaria | Bulgartransgaz EAD | Less-Advanced |  | 2017-09-01 | 2018-06-30 | 2018-10-01 | 2020-02-29 | 2020-03-01 | 2020-12-31 | 2021-01-01 | 2023-09-30 | 2023 | 2028 | 2017-05-12 | Delayed | Time schedule in the last TYNDP was estimated according to the data from the pre-feasibility study with lower level of details.
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | France | GRTgaz | Less-Advanced | [8 empty] | 2023-12-31 | 2023 | 2023 |  | Rescheduled | Waiting for terminal promoter decision
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | France | GRTgaz | Less-Advanced |  | 2007-03-01 | [6 empty] | 2023-11-30 | 2023 | 2023 |  | Rescheduled | Waiting for LNG terminal decision
Pipeline including CS | TRA-N-755 | CS Rimpar | Germany | GRTgaz Deutschland GmbH | Less-Advanced | [5 empty] | 2019-01-01 | 2019-12-31 | 2020-01-01 | 2023-12-01 | 2023 | 2023 |  | On time
Storage Facility | UGS-N-385 | South Kavala Underground Gas Storage facility | Greece | Hellenic Republic Asset anagement Fund | Less-Advanced | [9 empty] | 2023 | 2023 |  | Rescheduled | ​Decision on the procedure to select the project promoter and time needed to prepare the relevant tender procedure.
Pipeline including CS | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | Greece | DESFA S.A. | Less-Advanced | [9 empty] | 2023 | 2023 |  | Rescheduled | The project schedule depends on the implementation of the UGS of South Kavala, promoted by others (HRADF). Therefore the completion date is indicative.
Pipeline including CS | TRA-N-656 | Eastring - Hungary | Hungary | FGSZ Ltd. | Less-Advanced |  | 2017-09-01 | 2018-06-30 | 2018-10-01 | 2020-02-29 | 2020-03-01 | 2020-12-31 | 2021-01-01 | 2023-09-30 | 2023 | 2028 | 2017-05-12 | Delayed | Time schedule in the last TYNDP was estimated according to the data from the pre-feasibility study with lower level of details.
Pipeline including CS | TRA-N-71 | Physical Reverse Flow on South North Pipeline | Ireland | Gas Networks Ireland | Less-Advanced |  | 2019-06-01 | 2020-05-31 | 2020-06-01 | 2021-05-31 | 2021-06-01 | 2022-05-31 | 2022-06-01 | 2023-12-31 | 2023 | 2023
Pipeline including CS | TRA-N-354 | Interconnection with Slovenia | Italy | Snam Rete Gas S.p.A. | Less-Advanced | [9 empty] | 2023 | 2023
Pipeline including CS | TRA-N-655 | Eastring - Romania | Romania | SNTGN Transgaz SA | Less-Advanced |  | 2017-09-01 | 2019-06-01 | 2018-10-01 | 2019-02-01 | 2020-03-02 | 2020-12-01 | 2021-01-01 | 2023-09-30 | 2023 | 2028 |  | Delayed | Time schedule in the last TYNDP was estimated according to the data from the pre-feasibility study with lower level of details.
Pipeline including CS | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | Romania | SNTGN Transgaz SA | Less-Advanced | [9 empty] | 2023 | 2023 |  | On time
LNG Terminal | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Spain | Reganosa | Less-Advanced | 2021-02-19 | 2017-04-10 | 2018-02-09 | 2018-08-27 | 2019-11-15 | 2020-03-09 | 2021-02-19 | 2021-06-14 | 2023-09-01 | 2023 | 2023 |  | On time
Storage Facility | UGS-N-1229 | Underground Natural Gas Storage in Dumrea Area (UGS Dumrea) | Albania | Ministry of Infrastructure and Energy of Albania and Albgaz sh.a. | Advanced | 2019-12-30 | 2019-01-01 | 2019-10-30 | 2018-01-01 | 2019-10-30 | 2020-09-01 | 2020-12-30 | 2022-01-01 | 2024-12-31 | 2024 | 2024 |  | On time | This Project was not part of last TYNDP. This Project is in time without any delays.
Pipeline including CS | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Germany | Gastransport Nord GmbH | Less-Advanced | [9 empty] | 2024 | 2027
Pipeline including CS | TRA-N-14 | Komotini-Thesprotia pipeline | Greece | DESFA S.A. | Less-Advanced | [9 empty] | 2024 | 2024 |  |  | Lack of interest from the market
Pipeline including CS | TRA-N-1129 | Compressor Station Kipi Increment | Greece | DESFA S.A. | Less-Advanced | [9 empty] | 2024 | 2024
LNG Terminal | LNG-N-824 | LNG Terminal in Klaipeda | Lithuania | AB Klaipėdos Nafta | Less-Advanced | 2020-12-31 | 2017-11-14 | 2018-03-13 | [6 empty] | 2024 | 2024 |  | On time
Storage Facility | UGS-N-371 | Sarmasel undeground gas storage in Romania | Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced | 2020-10-01 | 2018-05-01 | 2019-05-01 | 2019-08-01 | 2020-06-01 | 2019-06-01 | 2020-08-01 | 2021-02-01 | 2024-10-01 | 2024 | 2024 |  | Rescheduled | The commissioning deadline was changed to 2024. The change occurred due to:(a) the need to correlate the development of storage system with NTS development directions (stages of NTS and interconnections HU, BG and RS, changes in the status of transit lines, clarifications on gas sources for the entire NTS), (b) upcoming monetisation of Black Sea developments , (c) the impact on the financial results generated from the evolution of the gas price on the market which caused a drop in storage services demand..
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Spain | Enagás Transporte, S.A.U. | Less-Advanced | 2020-05-31 | 2019-01-01 | 2020-05-31 | 2019-01-01 | 2020-05-31 | 2019-09-01 | 2021-12-31 | 2022-04-01 | 2023-12-01 | 2024 | 2024 |  | Rescheduled
LNG Terminal | LNG-N-79 | Paldiski LNG Terminal | Estonia | Balti Gaas plc | Less-Advanced | 2022-01-01 | 2012-01-01 | 2016-01-29 | 2013-04-01 | 2014-04-24 | 2008-01-14 | 2017-06-12 | 2022-11-01 | 2025-12-31 | 2025 | 2025 |  | Rescheduled | The project is technically ready for construction, but no FID can be taken before the competing projects and govermental aid issues are solved (political decision regarding regional LNG terminal and potential financial aid to it).
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | France | GRTgaz and Storengy | Less-Advanced | 2021-12-31 | 2014-06-01 | 2016-09-30 | 2015-09-01 | 2020-09-30 | 2016-11-01 | 2026-12-31 | 2017-04-01 | 2026-12-31 | 2025 | 2025 |  | On time
Pipeline including CS | TRA-N-808 | Transport of gas volumes to the Netherlands | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | [9 empty] | 2025 | 2025
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced | 2021-06-01 | 2015-05-01 | 2018-03-31 | 2018-11-01 | 2020-12-31 | 2018-06-01 | 2021-06-01 | 2021-06-01 | 2024-12-31 | 2025 | 2025 | 2018-01-25 | Rescheduled | Thanks to the positive outcomes of the Pre-FEED activities, co-financed by European Commission trough CEF program, the promoter has updated the project schedule increasing the accuracy of the next development activities.
Pipeline including CS | TRA-N-1091 | Metering and Regulating station at Megalopoli | Greece | DESFA S.A. | Less-Advanced | [9 empty] | 2025 | 2025 |  | Rescheduled | Lack of market demand
Pipeline including CS | TRA-N-7 | Development for new import from the South (Adriatica Line) | Italy | Snam Rete Gas S.p.A. | Less-Advanced | [9 empty] | 2025 | 2025
Pipeline including CS | TRA-N-1195 | Matagiola - Massafra pipeline | Italy | Snam Rete Gas S.p.A. | Less-Advanced | [9 empty] | 2025 | 2025
Pipeline including CS | TRA-N-1246 | Greece - Italy interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | [9 empty] | 2025 | 2025
Pipeline including CS | TRA-N-873 | Additional capacity at OSZ from Germany to the Netherlands | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | [9 empty] | 2025 | 2025
Pipeline including CS | TRA-N-910 | West Interconnection BiH/CRO | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | 2024-10-01 | 2018-01-01 | 2019-04-01 | 2019-04-30 | 2024-12-31 | 2025-01-01 | 2025-06-30 | 2025-06-01 | 2026-06-30 | 2026 | 2026
Storage Facility | UGS-N-914 | UGS Damasławek | Poland | GAZ-SYSTEM S.A. | Less-Advanced | [9 empty] | 2026 | 2026
LNG Terminal | LNG-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | Romania | AGRI LNG Project Company SRL (RO) | Less-Advanced | 2020-11-01 | 2012-06-28 | 2015-04-24 | 2019-01-01 | 2020-04-01 | 2018-01-01 | 2019-09-01 | 2022-06-01 | 2026-08-01 | 2026 | 2026 |  | Delayed | longer process for deciding the next steps of the Project
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Croatia | Plinacro Ltd | Less-Advanced | 2025-12-01 |  |  |  |  | 2012-12-05 | 2026-09-01 | 2026-04-01 | 2027-11-01 | 2027 | 2027
Pipeline including CS | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Croatia | Plinacro Ltd | Less-Advanced | [7 empty] | 2027-04-01 | 2027-11-01 | 2027 | 2027
Pipeline including CS | TRA-N-17 | System Enhancements - Eustream | Slovakia | eustream, a.s. | Less-Advanced | [9 empty] | 2027 | 2027 |  | On time
Pipeline including CS | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | Portugal | REN-Gasodutos, S.A. | Less-Advanced | [9 empty] | 2028 | 2028 |  | Delayed | ​This phase of the project is dependent on the 1st phase of the 3rd IP PT-ES (pipeline Celorico-Spanish border).
Pipeline including CS | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | Portugal | REN-Gasodutos, S.A. | Less-Advanced | [9 empty] | 2028 | 2028 |  | Delayed | This phase of the project is dependent on the 1st phase of the 3rd IP PT-ES (pipeline Celorico-Spanish border).
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Spain | Enagás Transporte, S.A.U. | Less-Advanced | [9 empty] | 2028 | 2028 |  | Rescheduled
Pipeline including CS | TRA-N-8 | Import developments from North-East | Italy | Snam Rete Gas S.p.A. | Less-Advanced | [9 empty] | 2034 | 2034
Pipeline including CS | TRA-N-9 | Additional Southern developments | Italy | Snam Rete Gas S.p.A. | Less-Advanced | [9 empty] | 2034 | 2034

## Third-Party Access Exemptions
Projects Having Applied for Third-Party Access Exemptions
Project Type | Code | Project Name | Promoter | Applied For Exemption | Exemption Granted | Exemption Stage Reached | Exempted % Entry | Exempted % Exit | Tariff Regime | TPA Regime Comments
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Magyar Gáz Tranzit Zrt. | Yes | No |  | 0% | 0% | Regulated
LNG Terminal | LNG-N-50 | Gate terminal phase 3 | Gate | Yes | Yes |  | 0% | 100% | Not Applicable | The exemption was applied for in March 2006; the exemption has been granted by the Dutch Minister on 14 July 2007; the EC gave its approval on 2 October 2007. Was not sure what to fill in regulated or negotiated. It is exempted
Pipeline including CS | TRA-N-965 | Interconnection Macedonia-Serbia | MER JSC Skopje | Yes | Not Relevant |  | 0% | 0% | Regulated | The transmission tariff will be regulated according to EU regulations.
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | ICGB a.d. | Yes | Not Yet | Market Test completed with signed ARCAs; Exemption Application being reviewed by Regulators | 90% | 90% | Not Applicable | The Exemption Application has been submitted for obtaining exemption from tariff regulation, TPA obligations and ownership unbundling. Finalization of the Exemption procedure is planned in 1st half 2018.
Pipeline including CS | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | DESFA S.A. | Yes | Yes |  | 0% | 0% | Regulated
Pipeline including CS | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Gastransport Nord GmbH | Yes | Yes |  | 0% | 0% | Regulated
LNG Terminal | LNG-N-198 | Porto Empedocle LNG | Nuove Energie S.r.l. | Yes | Yes | Nuove Energie relinquished the exemption in April 2017 | 0% | 0% | Negotiated | The TPA exemption has been granted as per EC Decision issued on 7.5.2012 and Italian Ministry of Economic Development Decree issued on June 6th, 2012 for 5 years . TPA exemption expired the 7.5.2017.
LNG Terminal | LNG-N-30 | Shannon LNG Terminal and Connecting Pipeline | Shannon LNG Ltd | Yes | Yes |  | 0% | 0% | Negotiated
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | Yes | Yes | Exemption has been granted by the relevant regulatory authorities and the Commission. The start of the Exemption period coincides with the start of commercial operations of TAP | 100% | 100% | Negotiated | The initial capacity is exempted from TPA. Expansion capacity is subject to TPA and will be offered to the market via market tests, from no later than start of operations and subsequently every two years. In this regard, please note enclosed Annexes.
Pipeline including CS | TRA-N-831 | Vecsés-Városföld gas transit pipeline | Magyar Gáz Tranzit Zrt. | Yes | Yes |  | 0% | 0% | Regulated

## Intergovernmental Agreements
Intergovernmental Agreements
Project Type | Code | Project Name | Promoter | Agreement | Signed | Signature Date | Description
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Letter of Itent | Yes | 2018-02-15 | Signed by Plinacro, Montenegro Bonus and Albgaz
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Memorandum of Understanding on cooperation in relation to EastMed Pipeline | Yes | 2017-12-05 | MoU signed by Ministers of the Republic of Cyprus, the Hellenic Republic and the State of Israel and the Ambassador of the Italian Republic to Cyprus
Pipeline including CS | TRA-N-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Memorandum of Understanding | Yes | 2017-10-30 | Memorandum of Understanding
Pipeline including CS | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Memorandum of Understanding | Yes | 2017-10-30 | Memorandum of Understanding
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy | Memorandum of Understanding between Bulgaria and Serbia | Yes | 2017-01-19 | Memorandum of Understanding between Bulgaria and Serbia
Pipeline including CS | TRA-N-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Memorandum of understanding | Yes | 2016-12-12 | On project of expanded interconnection between gas transmission system of Republic of Poland and Czech Republic (STORK II)
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Italiy-Greece-Cyprus-Israel Working Group | Yes | 2016-12-01
Pipeline including CS | TRA-N-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Memorandum of understanding | Yes | 2016-09-06 | On the cooperation in the natural gas sector aimed at implementation of the Czech Republic- Poland Interconnection Project
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Memorandum of Understanding and Cooperation | Yes | 2016-08-26 | signed by the Ministry of Energy and Industry of Republic of Albania, Ministry Foreign Trade and Economic Relations of Bosnia and Herzegovina, Ministry of Economy of the Republic of Croatia and Ministry of Economy of Montenegro
Pipeline including CS | TRA-N-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Memorandum of Understanding | Yes | 2016-07-13 | Memorandum of Understanding
Pipeline including CS | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Memorandum of Understanding | Yes | 2016-07-13 | Memorandum of Understanding
Pipeline including CS | TRA-N-980 | Interconnection Macedonia-Greece | MER JSC Skopje | Memorandum of understanding between DESFA S.A. and MER JSC Skopje | No | 2016-05-18
Pipeline including CS | TRA-N-965 | Interconnection Macedonia-Serbia | MER JSC Skopje | Memorandum of understanding between Macedonia and Serbia | No | 2016-05-18
Pipeline including CS | TRA-N-976 | Interconnection Macedonia-Bulgaria | MER JSC Skopje | Memorandum of understanding between Macedonia and Bulgaria | No | 2016-05-18
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Cyprus-Israel-Greece Trilateral Summit Declaration | Yes | 2016-01-28 | Agreement to "to strengthen the cooperation between our three countries in order to promote a trilateral partnership in different fields of common interest and to work together towards promoting peace, stability, security and prosperity in the Mediterran"
LNG Terminal | LNG-N-82 | LNG terminal Krk | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | CESEC MoU | Yes | 2015-07-10 | Memorandum of Understanding
Pipeline including CS | TRA-N-357 | NTS developments in North-East Romania | SNTGN Transgaz SA | Memorandum of Understanding | Yes | 2015-05-21 | Memorandum of understanding between the Ministry of Economy, Commerce and Business Environment in Romania and the Ministry of Economy from the Republic of Moldova related to preparing the conditions for the construction of the high pressure gas transmissi
Pipeline including CS | TRA-N-654 | Eastring - Bulgaria | Bulgartransgaz EAD | Declaration | No | 2015-05-21 | Governmental declaration
Pipeline including CS | TRA-N-628 | Eastring - Slovakia | eustream, a.s. (a joint stock company) | Declaration | Yes | 2015-05-21 | Governmental declaration
Pipeline including CS | TRA-N-656 | Eastring - Hungary | FGSZ Ltd. | Declaration | No | 2015-05-21 | Goverment declaration
Pipeline including CS | TRA-N-136 | Czech-Polish Gas Interconnector (CPI) | NET4GAS, s.r.o. | Memorandum of understanding | Yes | 2015-04-20 | On the cooperation in the natural gas sector aimed at implementation of the Czech Republic- Poland Interconnection Project
Pipeline including CS | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | REN-Gasodutos, S.A. | Madrid Declaration | Yes | 2015-03-04 | European Comission, Portugal, France and Spain
Pipeline including CS | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | REN-Gasodutos, S.A. | Madrid Declaration | Yes | 2015-03-04 | European Comission, Portugal, France and Spain
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Enagás Transporte, S.A.U. | Madrid Declaration | Yes | 2015-03-04 | Commission, France, Portugal and Spain sign High Level Group agreement to break energy barriers
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | GRTgaz and TIGF | Madrid Declaration | Yes | 2015-03-04 | Energy interconnection links summit
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Enagás Transporte, S.A.U. | Madrid Declaration | Yes | 2015-03-04 | Commission, France, Portugal and Spain sign High Level Group agreement to break energy barriers
Pipeline including CS | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | REN-Gasodutos, S.A. | Madrid Declaration | Yes | 2015-03-04 | European Comission, Portugal, France and Spain
Pipeline including CS | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | TIGF | Madrid Declaration | Yes | 2015-03-04 | Energy Interconnections Links Summit
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Enagás Transporte, S.A.U. | Madrid Declaration | Yes | 2015-03-04 | Commission, France, Portugal and Spain sign High Level Group agreement to break energy barriers
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Enagás Transporte, S.A.U. | Madrid Declaration | Yes | 2015-03-04 | Commission, France, Portugal and Spain sign High Level Group agreement to break energy barriers
Pipeline including CS | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd | Memorandum of Understanding | Yes | 2014-12-28 | Signed among Plinacro, Plinovodi and Gas Connect Austria
LNG Terminal | LNG-N-79 | Paldiski LNG Terminal | Balti Gaas plc | Agreement between PMs of Estonia and Finland | Yes | 2014-11-17 | Agreement in regards to the gas infrastructure in the countries.
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Plinovodi d.o.o. | Agreement between PMs of Estonia and Finland | Yes | 2014-11-17 | Agreement in regards to the gas infrastructure in the countries.
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | GAZ-SYSTEM S.A. | Agreement between the Government of the Republic of Poland and the Government of the Slovak Republic for cooperation on the implementation of the project of a gas pipeline connecting the Polish transmission system and Slovak transmission system. | Yes | 2014-06-11 | In Comments
Pipeline including CS | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Plinacro Ltd | Letter of Intent | Yes | 2014-05-22 | Signed between Plinacro and Plinovodi
Pipeline including CS | TRA-F-43 | Val de Saône project | GRTgaz | Cross border cost allocation | Yes | 2014-04-10 | Decision from CRE and CNMC on the request for cross order cost allocation between France and Spain for the project of common interest Val de Saône
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD | Memorandum of Understanding | Yes | 2014-03-28 | a Memorandum of Understanding between the Ministry of Economy and Energy of the Republic of Bulgaria and the Ministry of Energy and Natural Resources of the Republic of Turkey, concerning ITB project
LNG Terminal | LNG-N-79 | Paldiski LNG Terminal | Balti Gaas plc | Memorandum of Understanding | Yes | 2014-02-28 | MoU between Estonia and Finland and LNG project promoters
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Plinovodi d.o.o. | Memorandum of Understanding | Yes | 2014-02-28 | MoU between Estonia and Finland and LNG project promoters
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Agreement to extend the Memorandum of Understanding | Yes | 2014-02-25 | Signed between Plinacro and TAP
Pipeline including CS | TRA-F-190 | Poland - Slovakia interconnection | eustream,a.s. (a joint-stock company) | Agreement between the Government of the Slovak Republic and the Government of the Republic of Poland for cooperation on the implementation of the project of a gas pipeline connecting the Slovak transmission system and Polish transmission system | Yes | 2013-11-22 | Intergovernmental agreement
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | Host-government agreement between TAP and Greece | Yes | 2013-06-26 | The HGA is designed to fill legal, regulatory and fiscal caviats to mitigate commercial risks and thereby provide the necessary investor protection to ensure that the project is built and enable construction and operation in accordance with high standards
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | Host-government agreement between TAP and Albania | Yes | 2013-04-05 | The HGA is designed to fill legal, regulatory and fiscal caviats to mitigate commercial risks and thereby provide the necessary investor protection to ensure that the project is built and enable construction and operation in accordance with high standards
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | Inter-governmental Agreements (only applicable for import pipeline projects | Yes | 2013-02-13 | An IGA between Italy, Greece and Albania has formalized the state parties’ support for the TAP project, ensure cross-country harmonization of standards in order to facilitate the implementation of TAP and provide the necessary investor protection measure
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy | Memorandum of Understanding between Bulgaria and Serbia | Yes | 2012-12-14 | Memorandum of Understanding signed in Brussels between Bulgaria and Serbia in 2012
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Trans Adriatic Pipeline AG | Inter-ministerial agreement between Italy, Albania and Greece | Yes | 2012-09-27 | An inter-ministerial agreement between Italy, Albania and Greece is required under Italian law to commence the TPA exemption application process in Italy.
Pipeline including CS | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | SOCAR (The State Oil Company of the Azerbaijan Republic) | Intergovernmental Agreement between Turkey and Azerbaijan | Yes | 2012-06-26 | Intergovernmental Agreement (IGA) between the Government of the Republic of Turkey and the Government of the Republic of Azerbaijan Concerning the Trans Anatolian Natural Gas Pipeline System
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD | Joint Declaration of the Minister of Energy and Natural Resources of the Republic of Turkey and the Minister of Economy, Energy and Tourism of the Republic of Bulgaria on Energy Cooperation | Yes | 2012-03-20 | Declarationon Energy Cooperation
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Letter of Intent | Yes | 2011-04-06 | between Plinacro and BH Gas for all projects of interconnection
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Plinacro Ltd | Letter of Intent | Yes | 2011-04-06 | between Plinacro and BH Gas for all projects of interconnection
Pipeline including CS | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Plinacro Ltd | Letter of Intent | Yes | 2011-04-06 | between Plinacro and BH Gas for all projects of interconnection
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Memorandum of Understanding | Yes | 2011-02-05 | Signed between Plinacro and TAP
Pipeline including CS | TRA-N-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Memorandum of Understanding between Greece and Turkey | Yes | 2010-05-01
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy | Joint statement by Bulgaria and Serbia | Yes | 2010-03-05 | Joint statement signed in Brussels by Bulgaria and Serbia in 2010
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgartransgaz EAD | Memorandum of Understanding between the Ministry of Economy, Energy and Tourism of the Republic of Bulgaria and the Ministry of Energy and Natural Resources of the Republic of Turkey on Comprehensive Cooperation in the Field of Energy | Yes | 2010-01-29 | Memorandum of Understandingon Comprehensive Cooperation in the Field of Energy
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Plinovodi d.o.o. | Memorandum of Understanding (MOU) | Yes | 2009-11-27
Pipeline including CS | TRA-N-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Joint statement of the Italian Minister of Economic Development and the Turkish Minister of Energy and Natural Resources | Yes | 2009-11-01
Pipeline including CS | TRA-N-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Protocol of Cooperation between Italy and Azerbaijan | Yes | 2007-12-01
Pipeline including CS | TRA-N-12 | GALSI Pipeline Project | Galsi S.p.A. | Italy – Algeria Inter-Governmental Agreement for Galsi project | Yes | 2007-11-14 | Agreement between Italy and Algeria to promote and support the permitting, the construction and the commissioning of the Galsi Pipeline Project.
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Plinacro Ltd | Ministerial declaration | Yes | 2007-09-27 | signed by the Ministries of enegry of Albania, Montenegro and Croatia, from dezember 2008, Bosnia and Herzegovina signed as well
Pipeline including CS | TRA-N-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Italy‐Greece‐Turkey Intergovernmental Agreement | Yes | 2007-07-01
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Plinacro Ltd | Memorandum of understanding | Yes | 2006-06-26 | signed between Plinacro and BH Gas
Pipeline including CS | TRA-N-14 | Komotini-Thesprotia pipeline | DESFA S.A. | Intergovernmental Agreement between Greece and Italy for the implementation of the Interconnection Greece Italy. | Yes | 2005-11-04 | The Agreement was ratified by the Greek Parliament in 2006 (Law 3441/Government Gazette A’ 39/27.02.2006).
Pipeline including CS | TRA-N-10 | Poseidon Pipeline | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Italy‐Greece Intergovernmental Agreement | Yes | 2005-11-01
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Ministry of Energy | Memorandum of Understanding between Bulgaria and Serbia | Yes | 2005-04-08 | Memorandum of Understanding signed in Sofia between Bulgaria and Serbia in 2005
Pipeline including CS | TRA-F-1138 | South Caucasus Pipeline - (Future) Expansion - SCP-(F)X | SOCAR Midstream Operations LLC | Intergovernmental Agreement between Azerbaijan and Georgia | Yes | 2002-04-17

## Enablers
Enabler Projects
Enabler Project Type | Enabler Code | Enabler Project Name | Enabled Code | Enabled Project Name
Pipeline including CS | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde)
Pipeline including CS | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station)
Pipeline including CS | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde)
Pipeline including CS | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | TRA-N-320 | Carregado Compressor Station
Pipeline including CS | TRA-F-1028 | Albania - Kosovo Gas Pipeline | UGS-N-1229 | Underground Natural Gas Storage in Dumrea Area (UGS Dumrea)
Pipeline including CS | TRA-N-780 | Baltic Pipe project – onshore section in Denmark | TRA-N-394 | Norwegian tie-in to Danish upstream system
Pipeline including CS | TRA-F-895 | Balticconnector | TRA-F-915 | Enhancement of Estonia-Latvia interconnection
Pipeline including CS | TRA-F-895 | Balticconnector | LNG-N-1119 | Paldiski LNG
Pipeline including CS | TRA-F-895 | Balticconnector | TRA-N-1121 | TallinnLNG
Pipeline including CS | TRA-N-320 | Carregado Compressor Station | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station)
Pipeline including CS | TRA-N-320 | Carregado Compressor Station | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde)
Pipeline including CS | TRA-N-320 | Carregado Compressor Station | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border)
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod)
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo)
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec)
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia)
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS | TRA-N-1129 | Compressor Station Kipi Increment | TRA-N-14 | Komotini-Thesprotia pipeline
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod)
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-N-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo)
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec)
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar
Pipeline including CS | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | TRA-N-593 | Varna-Oryahovo gas pipeline
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak)
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec)
Pipeline including CS | TRA-F-340 | CS Wertingen | TRA-F-241 | MONACO section phase I (Burghausen-Finsing)
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor
Pipeline including CS | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor)
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project
Pipeline including CS | TRA-N-330 | EastMed Pipeline | TRA-N-10 | Poseidon Pipeline
Pipeline including CS | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | TRA-F-895 | Balticconnector
Storage Facility | UGS-N-374 | Enhancement of Incukalns UGS | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part)
Storage Facility | UGS-N-374 | Enhancement of Incukalns UGS | TRA-N-1181 | LNG terminal in Latvia with the connecting pipe
Pipeline including CS | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | UGS-N-374 | Enhancement of Incukalns UGS
Pipeline including CS | TRA-N-955 | GUD: Complete conversion to H-gas | TRA-N-951 | Embedding CS Folmhusen in H-Gas
Pipeline including CS | TRA-N-950 | Guitiriz - Lugo - Zamora pipeline | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion
Pipeline including CS | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system
Pipeline including CS | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | TRA-N-68 | Ionian Adriatic Pipeline
Pipeline including CS | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia)
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica
Pipeline including CS | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia)
LNG Terminal | LNG-N-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | TRA-N-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section
Pipeline including CS | TRA-N-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | LNG-N-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section
Pipeline including CS | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village
Pipeline including CS | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | UGS-N-138 | UGS Chiren Expansion
Pipeline including CS | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | TRA-N-593 | Varna-Oryahovo gas pipeline
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade
LNG Terminal | LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | LNG-N-297 | Mugardos LNG Terminal: Storage Extension
Pipeline including CS | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3
Pipeline including CS | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea
Pipeline including CS | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | TRA-N-357 | NTS developments in North-East Romania
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section)
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | TRA-N-621 | Poland - Ukraine Gas Interconnection (PL section)
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | TRA-N-273 | Poland - Czech Republic Gas Interconnection (PL section)
Pipeline including CS | TRA-N-394 | Norwegian tie-in to Danish upstream system | TRA-N-780 | Baltic Pipe project – onshore section in Denmark
Pipeline including CS | TRA-N-291 | NOWAL - Nord West Anbindungsleitung | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink)
Pipeline including CS | TRA-N-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section
Pipeline including CS | TRA-N-10 | Poseidon Pipeline | TRA-N-330 | EastMed Pipeline
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | TRA-N-654 | Eastring - Bulgaria
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | TRA-F-137 | Interconnection Bulgaria - Serbia
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | TRA-N-140 | Interconnection Turkey-Bulgaria
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | UGS-N-138 | UGS Chiren Expansion
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | TRA-N-593 | Varna-Oryahovo gas pipeline
Pipeline including CS | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage
Pipeline including CS | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | TRA-N-123 | Városföld CS
Pipeline including CS | TRA-N-339 | Trans-Caspian | TRA-N-53 | White Stream
Storage Facility | UGS-N-1229 | Underground Natural Gas Storage in Dumrea Area (UGS Dumrea) | TRA-F-1028 | Albania - Kosovo Gas Pipeline
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec)
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak)
Pipeline including CS | TRA-N-1267 | Upgrade Sülstorf station | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink)
Pipeline including CS | TRA-F-43 | Val de Saône project | TRA-F-45 | Reverse capacity from CH to FR at Oltingue
Pipeline including CS | TRA-F-43 | Val de Saône project | TRA-N-47 | Reverse capacity from France to Germany at Obergailbach
Pipeline including CS | TRA-N-593 | Varna-Oryahovo gas pipeline | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village
Pipeline including CS | TRA-N-593 | Varna-Oryahovo gas pipeline | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar
Pipeline including CS | TRA-N-123 | Városföld CS | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage
Pipeline including CS | TRA-N-123 | Városföld CS | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage
Pipeline including CS | TRA-N-53 | White Stream | TRA-N-339 | Trans-Caspian

## CBCA & CEF
CBCA and CEF
Type | Code | Project Name | Host Country | Promoter | PCI 3rd List Code | Previous PCI List | CBCA Decision | CBCA Decision Date | CBCA decision website | Benefiting Countries | Bearer Countries | CBCA Additional Comments | Applied for CEF | Grant for studies | Amount received for studies (mil. EUR) | Grant for works | Amount received for works (mil. EUR) | Intention to apply for CEF | Financial support for other programs | CEF Additional Comments
Pipeline including CS | TRA-F-43 | Val de Saône project | France | GRTgaz |  | PCI List 2015 |  |  | URL | France;#Spain | France |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | Yes |  |  | Yes
Pipeline including CS | TRA-F-45 | Reverse capacity from CH to FR at Oltingue | France | GRTgaz |  | PCI List 2013 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
LNG Terminal | LNG-F-147 | Revythoussa (2nd upgrade) | Greece | DESFA S.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | Yes
Pipeline including CS | TRA-F-208 | Reverse Flow TENP Germany | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | 5.01 (2018) | PCI List 2015 | Yes | 2014-05-12 | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1.232 | Yes | 8.665 |  | No
Pipeline including CS | TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Italy | Snam Rete Gas S.p.A. | 5.11 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | Yes
Pipeline including CS | TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | Turkey | SOCAR (The State Oil Company of the Azerbaijan Republic) | 7.1.1 (2018) | PCI List 2015 |  |  | URL |  |  | Our Project does not have CDCA desicion by NRA or ACER | (1) Yes, we have applied for CEF and we have received a decision | Yes | 10.327 | No |  | Yes, for studies only | No
Pipeline including CS | TRA-F-230 | Reverse Flow Transitgas Switzerland | Switzerland | FluxSwiss |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | Germany | bayernets GmbH |  | PCI List 2013 | Yes | 2014-04-10 | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Storage Facility | UGS-F-242 | Cornegliano UGS | Italy | ITAL Gas Storage |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-331 | Gascogne Midi | France | TIGF - GRTgaz |  | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-1138 | South Caucasus Pipeline - (Future) Expansion - SCP-(F)X | Azerbaijan | SOCAR Midstream Operations LLC | 7.1.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-F-1228 | Interconnection with UGS in Cornegliano Laudense | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-51 | Trans Adriatic Pipeline | Greece | Trans Adriatic Pipeline AG | 7.1.3 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 3314317 | No |  |  | No | Regarding CEF, TAP project requested EUR 14 018 347 in 2016, amount which was granted. In 2017, TAP requested EUR 3 314 317, amount which was not granted. EIB funding does not qualify as a 'funding programme'.
LNG Terminal | LNG-F-229 | Zeebrugge LNG Terminal - 5th Tank | Belgium | Fluxys LNG |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | Hungary | FGSZ Ltd. | 6.24.1.1 (2018) | PCI List 2015 | Yes | 2015-10-06 | URL | Hungary;#Romania |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2299500 | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Croatia | Plinacro Ltd | 6.5.5 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-340 | CS Wertingen | Germany | bayernets GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-752 | Capacity4Gas – DE/CZ | Czechia | NET4GAS, s.r.o. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-895 | Balticconnector | Estonia | Elering AS | 8.1.1 (2018) | PCI List 2015 | Yes | 2016-04-22 | URL | Finland;#Latvia | Estonia |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.77 | Yes | 98 |  | No
Pipeline including CS | TRA-F-902 | Capacity increase at IP Lanžhot entry | Slovakia | eustream,a.s. (a joint-stock company) |  |  |  |  | URL |  |  | Current technical capacity at the Czech side is 913,7 GWh/d. Incremental capacity on the Czech side based on Capacity increase at IP Lanžhot entry realization will be 333 GWh/d Current technical capacity at the Slovak side is 697 GWh/d. Incremental capacity on the Slovak side based on Capacity increase at IP Lanžhot entry realization will be 884 GWh/d It means that incremental capacity which should be taken into account for modelling is 549,7 GWh/d. | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Estonia | Elering AS | 8.2.2 (2018) | PCI List 2015 | Yes | 2016-04-22 | URL | Finland;#Latvia | Estonia |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | Yes | 18.6 |  | No
Pipeline including CS | TRA-F-928 | Balticconnector Finnish part | Finland | Baltic Connector Oy | 8.1.1 (2018) | PCI List 2015 | Yes | 2016-04-22 | URL | Finland;#Latvia | Estonia |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4.6 | Yes | 89.5 |  | No
Pipeline including CS | TRA-F-937 | Nord Stream 2 | Germany | Nord Stream 2 AG |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-941 | Metering and Regulating station at Nea Messimvria | Greece | DESFA S.A. | 7.1.3 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.486 | No |  |  | Yes
Pipeline including CS | TRA-F-954 | TAG Reverse Flow | Austria | Trans Austria Gasleitung GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-1193 | TAP interconnection | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-F-178 | Musel LNG terminal | Spain | Enagás Transporte, S.A.U. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-247 | North - South Gas Corridor in Western Poland | Poland | GAZ-SYSTEM S.A. | 6.2.11 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No |  |  | Yes
Pipeline including CS | TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | Romania | SNTGN Transgaz S.A. | 6.24.1.2 (2018) | PCI List 2015 | Yes | 2015-10-06 | URL | Hungary;#Romania | Hungary;#Romania |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1519342 | Yes | 179320000 |  | No
Pipeline including CS | TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | Bulgaria | ICGB a.d. | 6.8.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-F-918 | Capacity4Gas – CZ/SK | Czechia | NET4GAS, s.r.o. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Storage Facility | UGS-F-1045 | Bordolano Second phase | Italy | STOGIT S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-F-1241 | Interconnection with production in Gela | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
LNG Terminal | LNG-F-183 | Tenerife LNG Terminal | Spain | Gascan |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-F-190 | Poland - Slovakia interconnection | Slovakia | eustream,a.s. (a joint-stock company) | 6.2.1 (2018) | PCI List 2015 | Yes | 2014-11-28 | URL | Czechia;#Hungary;#Poland;#Slovakia;#Ukraine |  | It is expected that CAPEX and OPEX will be modified because of a decision (12/2017) not to contruct new compressor units at Veľké Kapušany but to technologically modify the existing compressor station at Veľké Kapušany. This will have a positive impact on CAPEX. However it will mean a slight increase of OPEX at eustream´s side. At this moment the project documents are being updated. It means that updated CAPEX and OPEX are not known. | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2544500 | Yes | 55232400 | No, we do not plan to apply | Yes
Pipeline including CS | TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | Poland | GAZ-SYSTEM S.A. | 8.05 (2018) | PCI List 2015 | Yes | 2014-08-11 | URL | Estonia;#Latvia;#Lithuania | Poland |  | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | Yes |  |  | Yes
Pipeline including CS | TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | 6.2.1 (2018) | PCI List 2015 | Yes | 2014-11-28 | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | Yes |  |  | Yes
Pipeline including CS | TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgaria | Bulgartransgaz EAD | 6.8.2 (2018) | PCI List 2015 |  |  | URL | Bulgaria | Bulgaria |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1032000 | Yes | 0 | Yes, for studies and works | Yes | During the 2017 CEF Energy Call for proposals Bulgartransgaz EAD submitted a project proposal for works. The proposal was not recommended for funding.
Pipeline including CS | TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | Lithuania | AB Amber Grid | 8.05 (2018) | PCI List 2015 | Yes | 2014-08-11 | URL |  | Estonia;#Latvia;#Lithuania |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2.5 | Yes | 57.9 |  | Yes
Pipeline including CS | TRA-F-137 | Interconnection Bulgaria - Serbia | Bulgaria | Ministry of Energy | 6.10 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-F-1028 | Albania - Kosovo Gas Pipeline | Albania | Min. of Infrastructure and Energy AL & Min. of Economic Development KO |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes | The Gas Master Plan of Albania: http://www.qbz.gov.al/Botime/Akteindividuale/Janar%202018/Fletore%2023/VKM%20nr.%2087,%20date%2014.2.2018.pdf The National General Territory Plan: http://www.qbz.gov.al/botime/fletore_zyrtare/2016/PDF-2016/248-2016.pdf
Pipeline including CS | TRA-F-1271 | Compressor Station Krummhoern | Germany | Open Grid Europe GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
LNG Terminal | LNG-F-272 | Upgrade of LNG terminal in Świnoujście | Poland | GAZ-SYSTEM S.A. | 8.07 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | No |  |  | No
Pipeline including CS | TRA-F-329 | ZEELINK | Germany | Open Grid Europe GmbH and Thyssengas GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
LNG Terminal | LNG-F-163 | Gran Canaria LNG Terminal | Spain | Gascan |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Storage Facility | UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Italy | STOGIT |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-291 | NOWAL - Nord West Anbindungsleitung | Germany | GASCADE Gastransport GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-12 | GALSI Pipeline Project | Italy | Galsi S.p.A. |  | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-N-82 | LNG terminal Krk | Croatia | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | 6.5.1 (2018) | PCI List 2015 |  |  | URL | Croatia;#Hungary | Croatia |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 6197000 | Yes | 101400000 | No decision yet taken | Yes
Pipeline including CS | TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Croatia | Plinacro Ltd | 6.5.1 (2018) | PCI List 2015 |  |  | URL | Croatia;#Hungary;#Ukraine |  |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | Yes | 16433500 |  | No
Pipeline including CS | TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | Romania | SNTGN Transgaz SA | 6.24.10.1 (2018) |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-357 | NTS developments in North-East Romania | Romania | SNTGN Transgaz SA |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | Germany | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | Romania | SNTGN Transgaz SA | 6.24.10.3 (2018) |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-1169 | Trans-Balkan Bi-directional Flow | Ukraine | PJSC "UKRTRANSGAZ" |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-1267 | Upgrade Sülstorf station | Germany | NGT GmbH / GUD GmbH & Co. KG / Fluxys D GmbH / ONTRAS GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | Romania | SNTGN Transgaz SA |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-N-32 | Project GO4LNG LNG terminal Gothenburg | Sweden | Swedegas AB | 8.06 (2018) | PCI List 2015 | Yes | 2015-10-01 | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | No |  |  | No
LNG Terminal | LNG-N-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Greece | Gastrade S.A. | 6.9.1 (2018) | PCI List 2015 |  |  | URL |  |  | CBCA is non applicable for the Project | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1755000 | No |  | Yes, for studies only | No
Pipeline including CS | TRA-N-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Greece | Gastrade S.A. | 6.9.1 (2018) | PCI List 2015 |  |  | URL |  |  | CBCA is non applicable for the Project | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1755000 | No |  | Yes, for studies only | No
Pipeline including CS | TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Croatia | Plinacro Ltd |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Croatia | Plinacro Ltd | 6.5.6 (2018) | PCI List 2015 |  |  | URL | Croatia;#Hungary;#Ukraine |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2250000 | Yes |  |  | No
Storage Facility | UGS-N-233 | Depomures | Romania | Engie Romania SA | 6.20.4 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | Spain | Reganosa |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | Romania | SNTGN Transgaz SA | 6.24.4.5 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Storage Facility | UGS-N-374 | Enhancement of Incukalns UGS | Latvia | JSC "Conexus Baltic Grid" | 8.2.4 (2018) | PCI List 2015 | Yes | 2014-04-30 | URL | Latvia;#Lithuania |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 150000 | No |  | Yes, for work only | No
Pipeline including CS | TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | Ukraine | PJSC UKRTRANSGAZ |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-621 | Poland - Ukraine Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | United Kingdom | GNI (UK) Limited | 5.1.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 925000 | No |  |  | No
Pipeline including CS | TRA-N-950 | Guitiriz - Lugo - Zamora pipeline | Spain | Reganosa |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-975 | Sardinia Gas Transportation Network | Italy | Società Gasdotti Italia |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1303 | IAEF - Vlora ccgt | Albania | Albgaz Sha |  |  |  |  | URL | Albania | Albania | We expect a positive decision any day by the National Regulatory Entity (ERE). | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-21 | Bidirectional Austrian-Czech Interconnector (BACI) | Austria | GAS CONNECT AUSTRIA GmbH | 6.04 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No | 0.022 | No, we do not plan to apply | Yes
Pipeline including CS | TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Croatia | Plinacro Ltd | 6.26.1.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4825000 | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | Czechia | NET4GAS, s.r.o. | 6.04 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.03 | No |  | No decision yet taken | Yes
LNG Terminal | LNG-N-198 | Porto Empedocle LNG | Italy | Nuove Energie S.r.l. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Croatia | Plinacro Ltd |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | Yes
Pipeline including CS | TRA-N-10 | Poseidon Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | 7.3.3 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
LNG Terminal | LNG-N-30 | Shannon LNG Terminal and Connecting Pipeline | Ireland | Shannon LNG Ltd | 5.03 (2018) | PCI List 2015 |  |  | URL |  |  | Shannon LNG did receive a CBCA decision in connection with the early build of the Shannon Pipeline. The CBCA involved agreement by the CRU in Ireland, Utility Regulator in Northern Ireland and Ofgem in the UK. | (3) No, we have not applied for CEF | No |  | No |  | Yes, for work only | No
Pipeline including CS | TRA-N-68 | Ionian Adriatic Pipeline | Croatia | Plinacro Ltd |  | PCI List 2013 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Slovenia | Plinovodi d.o.o. | 6.26.1.2 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Slovenia | Plinovodi d.o.o. | 6.23 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 344.5 | No |  |  | No
Pipeline including CS | TRA-N-123 | Városföld CS | Hungary | FGSZ Ltd. | 6.24.4.3 (2018) | PCI List 2015 | Yes | 2015-10-06 | URL | Hungary;#Romania |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2299500 | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-136 | Czech-Polish Gas Interconnector (CPI) | Czechia | NET4GAS, s.r.o. | 6.2.10 (2018) 6.2.12 (2018) | PCI List 2015 | Yes | 2014-10-17 | URL | Czechia;#Poland | Czechia;#Poland |  | (1) Yes, we have applied for CEF and we have received a decision;#(2) Yes, we have applied for CEF, but we have not received a decision yet | Yes | 1.196 | No |  | No decision yet taken | Yes | Decision of CEF grant for CS Břeclav has been taken. The Grant Agreement is now under development.
Pipeline including CS | TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Spain | Enagás Transporte, S.A.U. | 5.5.1 (2018) |  |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1.7 | No |  |  | No | In January 2016, Enagás Transporte SAU received a CEF-E grant for MidCat project to carry out the engineering studies of Martorell compressor station and the engineering studies of the pipeline from Figueras to the French border. These infrastructures are now included within STEP project. In January 2018, Enagás Transporte SAU received a CEF-E grant for studiers for permit granting process of STEP. INEA webpage on CEF-E grants for MidCat https://ec.europa.eu/inea/en/connecting-europe-facility/cef-energy/projects-by-country/spain/5.5-0054-esfr-s-m-15 List of actions selected for receiving financial assistance under the 2017 CEF Energy Call for Proposals (January 2018) https://ec.europa.eu/energy/sites/ener/files/documents/list_of_actions_selected_for_receiving_financial_assistance_under_the_2017_cef_energy_call_for_proposals.pdf
Pipeline including CS | TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | France | TIGF | 5.5.1 (2018) |  |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4.15 | Yes |  |  | No
Pipeline including CS | TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | Poland | GAZ-SYSTEM S.A. | 8.3.2 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No |  |  | Yes
Pipeline including CS | TRA-N-273 | Poland - Czech Republic Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | 6.2.10 (2018) | PCI List 2015 | Yes | 2014-06-24 | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No |  |  | No
Storage Facility | UGS-N-294 | Islandmagee Gas Storage Facility | United Kingdom | Islandmagee Storage Limited | 5.1.3 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4024000 | No |  |  | No
LNG Terminal | LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Spain | Reganosa |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-325 | Slovenian-Hungarian interconnector | Hungary | FGSZ Ltd. | 6.23 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | Yes |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | Austria | GAS CONNECT AUSTRIA GmbH | 6.26.1.4 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | Hungary | FGSZ Ltd. | 6.24.4.6 (2018) | PCI List 2015 | Yes | 2015-10-06 | URL | Hungary;#Romania |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 2299500 | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Slovenia | Plinovodi d.o.o. | 6.26.1.5 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Slovenia | Plinovodi d.o.o. | 6.26.6 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-394 | Norwegian tie-in to Danish upstream system | Denmark | Energinet.dk |  |  |  |  | URL | Denmark;#Poland;#Sweden |  | The Danish NRA (DERA) approved the CBCA on the 27 February 2018. The Polish NRA (URE) approved the CBCA on the 12 March 2018. The Danish decision can be found here: http://energitilsynet.dk/gas/afgoerelser/tilsynsafgoerelser/2018/godkendelse-af-omkostningsfordelingen-mellem-polen-og-danmark-for-baltic-pipe-projektet/ The Polish decision can be found here: https://bip.ure.gov.pl/bip/taryfy-i-inne-decyzje/inne-decyzje-informacj/3634,Inne-decyzje-informacje-sprawozdania-opublikowane-w-2018-r.html?search=3253 | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-423 | GCA Mosonmagyaróvár | Austria | GAS CONNECT AUSTRIA GmbH | 6.24.1.3 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | Bulgaria | Bulgartransgaz EAD | 6.25.4 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 920500 | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-593 | Varna-Oryahovo gas pipeline | Bulgaria | Bulgartransgaz EAD | 6.25.4 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 920500 | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgaria | Bulgartransgaz EAD | 6.25.4 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 920500 | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-780 | Baltic Pipe project – onshore section in Denmark | Denmark | Energinet.dk | 8.3.1 (2018) |  |  |  | URL | Denmark;#Poland;#Sweden |  | The Danish NRA (DERA) approved the CBCA on the 27 February 2018. The Polish NRA (URE) approved the CBCA on the 12 March 2018. The Danish decision can be found here: http://energitilsynet.dk/gas/afgoerelser/tilsynsafgoerelser/2018/godkendelse-af-omkostningsfordelingen-mellem-polen-og-danmark-for-baltic-pipe-projektet/ The Polish decision can be found here: https://bip.ure.gov.pl/bip/taryfy-i-inne-decyzje/inne-decyzje-informacj/3634,Inne-decyzje-informacje-sprawozdania-opublikowane-w-2018-r.html?search=3253 | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No |  |  | No
LNG Terminal | LNG-N-962 | Tallinn LNG | Estonia | Vopak E.O.S. AS / Vopak LNG Holdings B.V/ Port of Tallinn AS |  | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Italy | Società Gasdotti Italia |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Croatia | Plinacro Ltd | 6.26.1.3 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 3900000 | No |  |  | No
Pipeline including CS | TRA-N-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | Poland | GAZ-SYSTEM S.A. | 8.3.2 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No |  |  | No
Pipeline including CS | TRA-N-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Croatia | Plinacro Ltd |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Storage Facility | UGS-N-356 | Underground Gas Storage Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-628 | Eastring - Slovakia | Slovakia | eustream, a.s. (a joint stock company) | 6.25.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1000000 | No |  | Yes, for studies and works | Yes
Pipeline including CS | TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Croatia | Plinacro Ltd | 6.5.6 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-31 | Connection of Malta to the European Gas Network - Pipelines | Malta | Ministry For Energy & Water Management - Malta | 5.19 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4080000 | No |  | Yes, for studies and works | Yes
Storage Facility | UGS-N-138 | UGS Chiren Expansion | Bulgaria | Bulgartransgaz EAD | 6.20.2 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4030000 | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | France | GRTgaz and TIGF | 5.5.2 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 4.15 | No |  |  | No
Pipeline including CS | TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | Portugal | REN-Gasodutos, S.A. | 5.4.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 505925 | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-320 | Carregado Compressor Station | Portugal | REN-Gasodutos, S.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Spain | Enagás Transporte, S.A.U. | 5.5.2 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1.5 | No |  |  | No | In January 2016, Enagás Transporte SAU received a CEF-E grant for MidCat project to carry out the engineering studies of Martorell compressor station and the engineering studies of the pipeline from Figueras to the French border. These infrastructures are now included within STEP project. In January 2018, Enagás Transporte SAU received a CEF-E grant for studiers for permit granting process of STEP. INEA webpage on CEF-E grants for MidCat https://ec.europa.eu/inea/en/connecting-europe-facility/cef-energy/projects-by-country/spain/5.5-0054-esfr-s-m-15 List of actions selected for receiving financial assistance under the 2017 CEF Energy Call for Proposals (January 2018) https://ec.europa.eu/energy/sites/ener/files/documents/list_of_actions_selected_for_receiving_financial_assistance_under_the_2017_cef_energy_call_for_proposals.pdf
Pipeline including CS | TRA-N-645 | HU-UA reverse flow (Ukrainian section) | Ukraine | PJSC Ukrtransgaz |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-955 | GUD: Complete conversion to H-gas | Germany | Gasunie Deutschland Transport Services GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | Germany | ONTRAS Gastransport GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1200 | Expansion MS Hetlingen | Germany | Gasunie Deutschland Transport Service GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1253 | Trans-Balkan Bi-directional Flow (Moldavia phase) | Moldavia | Moldovatransgaz LLC |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
LNG Terminal | LNG-N-50 | Gate terminal phase 3 | Netherlands | Gate |  | PCI List 2013 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-128 | Compressor Station Kipi | Greece | DESFA S.A. | 6.8.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-192 | Entry capacity expansion GATE terminal | Netherlands | Gasunie Transport Services B.V. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | Lithuania | AB Amber Grid | 8.2.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | No |  |  | No
Pipeline including CS | TRA-N-809 | Additional East-West transport | Germany | Gasunie Deutschland Transport Services GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-882 | Transferring L-gas infrastructure to H-gas | Netherlands | Gasunie Transport Services B.V. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-951 | Embedding CS Folmhusen in H-Gas | Germany | Gasunie Deutschland Transport Services GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-980 | Interconnection Macedonia-Greece | former Yugoslav Republic of Macedonia | MER JSC Skopje |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1064 | Moffat Physical Reverse Flow | United Kingdom | National Grid Gas plc | 5.1.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | Greece | DESFA S.A. | 6.9.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-N-1146 | Cyprus Gas2EU | Cyprus | Ministry of Energy, Commerce, Industry and Tourism | 7.05 (2018) | PCI List 2015 |  |  | URL | Cyprus;#Greece | Cyprus |  | (1) Yes, we have applied for CEF and we have received a decision | No |  | Yes | 101000000 |  | Yes | www.Cynergy-project.eu
Pipeline including CS | TRA-N-1194 | Sardinia Methanization | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1197 | Expansion of the gas infrastructure between BG-TR and BG-RS borders | Bulgaria | Bulgartransgaz EAD |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1268 | Romania-Serbia Interconnection | Romania | SNTGN Tranzgaz SA |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | United Kingdom | Premier Transmission Limited | 5.1.2 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
LNG Terminal | LNG-N-225 | Montoir LNG Terminal Expansion | France | Elengy |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
LNG Terminal | LNG-N-227 | Fos Cavaou LNG Terminal Expansion | France | Fosmax LNG |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-N-339 | Trans-Caspian | Turkmenistan | W-Stream Caspian Pipeline Company Ltd | 7.1.1 (2018) | PCI List 2015 |  |  | URL |  |  | TCP 1st and 2n string are not located in any of the EU-MS nor do they impact any of the EU-MS respectively Contracting Parties to the Energy Community directly. | (1) Yes, we have applied for CEF and we have received a decision | Yes | 1.87 | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | Latvia | JSC "Conexus Baltic Grid" | 8.2.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 175000 | No |  | Yes, for studies and works | No | The feasibility study that just started shall be finished by the end of September 2018. Depending on the results of the study further steps will be decided (e.g. study according to EIA Directive, works, etc.)
LNG Terminal | LNG-N-912 | Skulte LNG | Latvia | AS Skulte LNG Terminal |  |  |  |  | URL | Estonia;#Finland;#Latvia;#Lithuania | Estonia;#Finland;#Latvia |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-965 | Interconnection Macedonia-Serbia | former Yugoslav Republic of Macedonia | MER JSC Skopje |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-967 | Nea-Messimvria to FYRoM pipeline | Greece | DESFA S.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-N-976 | Interconnection Macedonia-Bulgaria | former Yugoslav Republic of Macedonia | MER JSC Skopje |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
LNG Terminal | LNG-N-1198 | LNG Terminal Brunsbuettel | Germany | Gasunie Deutschland Transport Service GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1199 | LNG Terminal Brunsbuettel - Grid Integration | Germany | Gasunie Deutschland Transport Service GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1276 | Compressor station at Nea Messimvria (3rd unit) | Greece | DESFA S.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-47 | Reverse capacity from France to Germany at Obergailbach | France | GRTgaz |  | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0 | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-53 | White Stream | Georgia | White Stream Ltd |  | PCI List 2013 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
Pipeline including CS | TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Slovenia | Plinovodi d.o.o. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Slovenia | Plinovodi d.o.o. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgaria | Bulgartransgaz EAD |  | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 142620 | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-245 | North - South Gas Corridor in Eastern Poland | Poland | GAZ-SYSTEM S.A. | 6.2.2 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | Yes
Pipeline including CS | TRA-N-500 | L/H Conversion Belgium | Belgium | Fluxys Belgium | 5.21 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Hungary | Magyar Gáz Tranzit Zrt. | 6.2.13 (2018) |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Hungary | Magyar Gáz Tranzit Zrt. | 6.2.13 (2018) |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-831 | Vecsés-Városföld gas transit pipeline | Hungary | Magyar Gáz Tranzit Zrt. | 6.2.14 (2018) |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
LNG Terminal | LNG-N-947 | FSRU Polish Baltic Sea Coast | Poland | GAZ-SYSTEM S.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | Yes |  |  | No
Pipeline including CS | TRA-N-971 | Compressor station at Nea Messimvria | Greece | DESFA S.A. | 7.1.3 (2018) |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | Poland | GAZ-SYSTEM S.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1227 | Gorizia plant upgrade | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-N-1231 | Inisfree LNG | Ireland | NextDecade LNG |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | Slovakia | eustream,a.s. (a joint-stock company) |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-1254 | CS Elten | Germany | Open Grid Europe GmbH and Thyssengas GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-1265 | Biomethane productions interconnection | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1278 | Compressor station at Ambelia | Greece | DESFA S.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-71 | Physical Reverse Flow on South North Pipeline | Ireland | Gas Networks Ireland |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-224 | Gaspipeline Brod - Zenica | Bosnia Herzegovina | BH-Gas d.o.o. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No | Having in mind that BiH is not MS, but Energy Community Contracting Party, BH-Gas is not in possition to apply to CEF. Once if this criterium will be changed, we will use this opportunity. Project was listed at PECI 2013 and it is submitted for PECI 2018.
Pipeline including CS | TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | France | GRTgaz |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | France | GRTgaz |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Spain | Reganosa |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-354 | Interconnection with Slovenia | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Storage Facility | UGS-N-385 | South Kavala Underground Gas Storage facility | Greece | Hellenic Republic Asset anagement Fund |  | PCI List 2013 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-654 | Eastring - Bulgaria | Bulgaria | Bulgartransgaz EAD | 6.25.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-655 | Eastring - Romania | Romania | SNTGN Transgaz SA | 6.25.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-656 | Eastring - Hungary | Hungary | FGSZ Ltd. | 6.25.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-N-742 | Zeebrugge LNG Terminal - 3rd Jetty | Belgium | Fluxys LNG |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-755 | CS Rimpar | Germany | GRTgaz Deutschland GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-851 | Southern Interconnection pipeline BiH/CRO | Bosnia Herzegovina | BH-GAS d.o.o. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | Yes
Pipeline including CS | TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | Romania | SNTGN Transgaz SA | 6.24.10.2 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | Greece | DESFA S.A. | 6.20.3 (2018) |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-14 | Komotini-Thesprotia pipeline | Greece | DESFA S.A. |  | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 0.322 | No |  |  | No
Pipeline including CS | TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Spain | Enagás Transporte, S.A.U. | 5.4.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Storage Facility | UGS-N-371 | Sarmasel undeground gas storage in Romania | Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | 6.20.6 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 550000 | No |  | Yes, for studies and works | No | We have applied for CEF grant for studies but it was not approved,
LNG Terminal | LNG-N-824 | LNG Terminal in Klaipeda | Lithuania | AB Klaipėdos Nafta |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for work only | No
Pipeline including CS | TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Germany | Gastransport Nord GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1129 | Compressor Station Kipi Increment | Greece | DESFA S.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Storage Facility | UGS-N-1229 | Underground Natural Gas Storage in Dumrea Area (UGS Dumrea) | Albania | Ministry of Infrastructure and Energy of Albania and Albgaz sh.a. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes | The Gas Master Plan is approved with the DoCM no. 87, dated on 14.02.2018. In this study a detailed assessment is conluded related to this project. UGS Dumrea is consider as very important project regarding the benefits on the security of supply of Albanian and neighbour countries.
Pipeline including CS | TRA-N-7 | Development for new import from the South (Adriatica Line) | Italy | Snam Rete Gas S.p.A. | 7.3.4 (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | Yes
LNG Terminal | LNG-N-79 | Paldiski LNG Terminal | Estonia | Balti Gaas plc |  | PCI List 2015 |  |  | URL | Estonia;#Finland |  | No net cost bearers were identified | (1) Yes, we have applied for CEF and we have received a decision | Yes | 136715600 | Yes | 136715600 |  | No | The CEF funding application was declined due to unclear situation with the temporary solution in Klaipeda and lack of clarity regarding the permanent solution.
Pipeline including CS | TRA-N-330 | EastMed Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | 7.3.1 (2018) | PCI List 2015 |  |  | URL |  |  |  | (1) Yes, we have applied for CEF and we have received a decision | Yes | 3650000 | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-429 | Adaptation L- gas - H-gas | France | GRTgaz and Storengy | 5.21 (2018) |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-808 | Transport of gas volumes to the Netherlands | Germany | Gasunie Deutschland Transport Services GmbH |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-873 | Additional capacity at OSZ from Germany to the Netherlands | Netherlands | Gasunie Transport Services B.V. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-1091 | Metering and Regulating station at Megalopoli | Greece | DESFA S.A. | 7.3.1 (2018) |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1195 | Matagiola - Massafra pipeline | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-1246 | Greece - Italy interconnection | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
LNG Terminal | LNG-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | Romania | AGRI LNG Project Company SRL (RO) |  | PCI List 2013 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | Yes, for studies and works | No
Pipeline including CS | TRA-N-910 | West Interconnection BiH/CRO | Bosnia Herzegovina | BH-Gas d.o.o. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Storage Facility | UGS-N-914 | UGS Damasławek | Poland | GAZ-SYSTEM S.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-17 | System Enhancements - Eustream | Slovakia | eustream, a.s. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No, we do not plan to apply | No
Pipeline including CS | TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Croatia | Plinacro Ltd |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Croatia | Plinacro Ltd |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | Portugal | REN-Gasodutos, S.A. | 5.4.2. (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | Portugal | REN-Gasodutos, S.A. | 5.4.2. (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Spain | Enagás Transporte, S.A.U. | 5.4.2. (2018) | PCI List 2015 |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  |  | No
Pipeline including CS | TRA-N-8 | Import developments from North-East | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No
Pipeline including CS | TRA-N-9 | Additional Southern developments | Italy | Snam Rete Gas S.p.A. |  |  |  |  | URL |  |  |  | (3) No, we have not applied for CEF | No |  | No |  | No decision yet taken | No

## National Development Plan Info
NDP Information
Code | Project Name | Country | Promoter | Maturity Status | PCI 3rd List | PCI 3rd List Code | PCI Priority Corridors | Is Part of a NDP | NDP Number | NDP Name Or Reason for non-NDP inclusion | NDP Website | NDP Release Date
TRA-N-10 | Poseidon Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Advanced | Yes | 7.3.3 (2018) | SGC | Yes | n.a. | Piano decennale di sviluppo delle reti di trasporto di gas naturale 2017-2026 (pag. 55, 56, 98) | URL | 2017-11-30
TRA-N-12 | GALSI Pipeline Project | Italy | Galsi S.p.A. | Advanced | No |  |  | Yes | n.a. | SNAM NDP 2017-2026 (page 98) | URL | 2017-11-30
TRA-N-21 | Bidirectional Austrian-Czech Interconnector (BACI) | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | Yes | 6.04 (2018) | NSIE | Yes | GCA 2015/01a | NDP 2018-2027 | URL | 2018-01-19
LNG-N-30 | Shannon LNG Terminal and Connecting Pipeline | Ireland | Shannon LNG Ltd | Advanced | Yes | 5.03 (2018) | NSIW | Yes | 3.3 | Gas Networks Ireland 2017 Network Development Plan | URL | 2017-12-15
TRA-N-31 | Connection of Malta to the European Gas Network - Pipelines | Malta | Ministry For Energy & Water Management - Malta | Advanced | Yes | 5.19 (2018) | NSIW | Yes | Section 4.3.2 | Malta National Reform Programme April 2017 | URL | 2017-04-30
TRA-N-66 | Interconnection Croatia -Bosnia and Herzegovina (Slobodnica- Bosanski Brod) | Croatia | Plinacro Ltd | Advanced | No |  |  | Yes | 1.15 | 2018-2027 | URL | 2017-12-15
TRA-N-68 | Ionian Adriatic Pipeline | Croatia | Plinacro Ltd | Advanced | No |  |  | Yes | 1.12, 1.25-1.27, 5.5 | 2018-2027 | URL | 2017-12-15
TRA-N-70 | Interconnection Croatia/Serbia (Slobdnica-Sotin-Bačko Novo Selo) | Croatia | Plinacro Ltd | Advanced | No |  |  | Yes | 1.30, 1.31 | 2018-2027 | URL | 2017-12-15
TRA-N-75 | LNG evacuation pipeline Zlobin-Bosiljevo-Sisak-Kozarac | Croatia | Plinacro Ltd | Advanced | Yes | 6.5.6 (2018) | NSIE | Yes | 1.19, 1.20, 1.21 | 2018-2027 | URL | 2017-12-15
LNG-N-82 | LNG terminal Krk | Croatia | LNG Hrvatska d.o.o. za poslovanje ukapljenim prirodnim plinom | Advanced | Yes | 6.5.1 (2018) | NSIE | Yes | LNG terminal on the island of Krk | DESETOGODISNJI PLAN RAZVOJA PLINSKOG TRANSPORTNOG SUSTAVA REPUBLIKE HRVATSKE 2018. - 2027. | URL | 2017-11-01
TRA-N-86 | Interconnection Croatia/Slovenia (Lučko - Zabok - Rogatec) | Croatia | Plinacro Ltd | Advanced | Yes | 6.26.1.1 (2018) | NSIE | Yes | 1.9, 1.10, 1.11 | 2018-2027 | URL | 2017-12-15
TRA-N-90 | LNG evacuation pipeline Omišalj - Zlobin (Croatia) | Croatia | Plinacro Ltd | Advanced | Yes | 6.5.1 (2018) | NSIE | Yes | 1.18 | 2018-2027 | URL | 2017-12-15
TRA-N-123 | Városföld CS | Hungary | FGSZ Ltd. | Advanced | Yes | 6.24.4.3 (2018) | NSIE | Yes | 12.2. | Hungarian TYNDP 2017 | URL | 2017-12-28
TRA-N-133 | Bidirectional Austrian Czech Interconnection (BACI) | Czechia | NET4GAS, s.r.o. | Advanced | Yes | 6.04 (2018) | NSIE | Yes | TRA-N-133 | CZ NDP 2016-2025 (approved) | URL | 2015-10-31
TRA-N-136 | Czech-Polish Gas Interconnector (CPI) | Czechia | NET4GAS, s.r.o. | Advanced | Yes | 6.2.10 (2018) 6.2.12 (2018) | NSIE | Yes | TRA-N-136 | CZ NDP 2016-2025 (approved) | URL | 2015-10-31
UGS-N-138 | UGS Chiren Expansion | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.20.2 (2018) | NSIE | Yes | Section 5.3 (5.3.1) | 2017-2026 Ten-year network development plan of BTG | URL | 2017-04-10
TRA-N-139 | Interconnection of the NTS with the DTS and reverse flow at Isaccea | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.24.10.1 (2018) | NSIE | Yes | 7.3 | The National Gas Transmission System Development Plan 2017-2026 | URL | 2017-06-22
TRA-N-161 | South Transit East Pyrenees (STEP) - ENAGAS | Spain | Enagás Transporte, S.A.U. | Advanced | Yes | 5.5.1 (2018) | NSIW | Yes | No code in the NDP | Conexión internacional con Francia por Cataluña | URL | 2008-05-01
LNG-N-198 | Porto Empedocle LNG | Italy | Nuove Energie S.r.l. | Advanced | No |  |  | Yes | RN_12 | Piano decennale di sviluppo SNAM 2017-2026 | URL | 2017-11-30
TRA-N-252 | South Transit East Pyrenees (STEP) - TIGF | France | TIGF | Advanced | Yes | 5.5.1 (2018) | NSIW | Yes | No number | 2017 TIGF NDP | URL
TRA-N-256 | Iberian-French corridor: Eastern Axis-Midcat Project | France | GRTgaz and TIGF | Advanced | Yes | 5.5.2 (2018) | NSIW | Yes | Augmentation des capacités d’interconnexion entre la France et l’Espagne | GRTgaz and TIGF development plans 2017 | URL | 2017-11-27
TRA-N-271 | Poland - Denmark interconnection (Baltic Pipe) - offshore section | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 8.3.2 (2018) | BEMIP | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-N-273 | Poland - Czech Republic Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 6.2.10 (2018) | NSIE | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-N-283 | 3rd IP between Portugal and Spain (pipeline Celorico-Spanish border) | Portugal | REN-Gasodutos, S.A. | Advanced | Yes | 5.4.1 (2018) | NSIW | Yes | - | PDIRGN 2017 | URL
TRA-N-291 | NOWAL - Nord West Anbindungsleitung | Germany | GASCADE Gastransport GmbH | Advanced | No |  |  | Yes | (already completed: 083-07, 409-01), 410-01 (older version compared to current draft NDP) | Netzentwicklungsplan Gas 2016-2026 | URL | 2017-10-16
UGS-N-294 | Islandmagee Gas Storage Facility | United Kingdom | Islandmagee Storage Limited | Advanced | Yes | 5.1.3 (2018) | NSIW | Yes | n.a. | Northern Ireland Gas Capacity Statement | URL
TRA-N-302 | Interconnection Croatia-Bosnia and Herzegovina (South) | Croatia | Plinacro Ltd | Advanced | No |  |  | Yes | 1.13 | 2018-2027 | URL | 2017-12-15
TRA-N-320 | Carregado Compressor Station | Portugal | REN-Gasodutos, S.A. | Advanced | No |  |  | Yes | - | PDIRGN 2017 | URL
TRA-N-325 | Slovenian-Hungarian interconnector | Hungary | FGSZ Ltd. | Advanced | Yes | 6.23 (2018) | NSIE | Yes | 12.12. | Hungarian TYNDP 2017 | URL | 2017-12-28
UGS-N-356 | Underground Gas Storage Velke Kapusany | Slovakia | NAFTA a.s. (joint stock company) | Advanced | No |  |  | Yes | chapter 3.3 | Ten-Year Network Development Plan of the transmission system of the company Eustream | URL | 2017-11-30
TRA-N-357 | NTS developments in North-East Romania | Romania | SNTGN Transgaz SA | Advanced | No |  |  | Yes | 7.4 | The National Gas Transmission System Development Plan 2017 - 2026 | URL | 2017-06-22
TRA-N-361 | GCA 2015/08: Entry/Exit Murfeld | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | Yes | 6.26.1.4 (2018) | NSIE | Yes | GCA 2015/08 | NDP 2018 - 2027 | URL | 2018-01-19
TRA-N-362 | Development on the Romanian territory of the Southern Transmission Corridor | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.24.4.5 (2018) | NSIE | Yes | 7.2 | The National Gas Transmission System Development Plan 2017-2026 | URL | 2017-06-22
TRA-N-377 | Romanian-Hungarian reverse flow Hungarian section 2nd stage | Hungary | FGSZ Ltd. | Advanced | Yes | 6.24.4.6 (2018) | NSIE | Yes | 12.1. | Hungarian TYNDP 2017 | URL | 2017-12-28
TRA-N-423 | GCA Mosonmagyaróvár | Austria | GAS CONNECT AUSTRIA GmbH | Advanced | Yes | 6.24.1.3 (2018) | NSIE | Yes | GCA 2015/05 | NDP 2018 - 2027 | URL | 2018-01-19
TRA-N-500 | L/H Conversion Belgium | Belgium | Fluxys Belgium | Advanced | Yes | 5.21 (2018) | NSIW | Yes | L/H Conversion | Ten-Year Indicative Investment Programme Fluxys Belgium & Fluxys LNG 2017-2026 | URL
TRA-N-592 | Looping CS Valchi Dol - Line valve Novi Iskar | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.25.4 (2018) | NSIE | Yes | Section 5.1. (5.1.1) | 2017-2026 Ten-year network development plan of BTG | URL | 2017-04-10
TRA-N-593 | Varna-Oryahovo gas pipeline | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.25.4 (2018) | NSIE | Yes | Section 5.1. (5.1.1) | 2017-2026 Ten-year network development plan of BTG | URL | 2017-04-10
TRA-N-594 | Construction of a Looping CS Provadia – Rupcha village | Bulgaria | Bulgartransgaz EAD | Advanced | Yes | 6.25.4 (2018) | NSIE | Yes | Section 5.1. (5.1.1) | 2017-2026 Ten-year network development plan of BTG | URL | 2017-04-10
TRA-N-621 | Poland - Ukraine Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | Advanced | No |  |  | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-N-628 | Eastring - Slovakia | Slovakia | eustream, a.s. (a joint stock company) | Advanced | Yes | 6.25.1 (2018) | NSIE | Yes | 4.1.1.3. Eastring | National Development Plan 2018-2027 | URL | 2017-11-30
TRA-N-727 | Iberian‐French corridor: Eastern Axis ‐ Midcat Project | Spain | Enagás Transporte, S.A.U. | Advanced | Yes | 5.5.2 (2018) | NSIW | Yes | No code in the NDP | Conexión internacional con Francia por Cataluña | URL | 2008-05-01
TRA-N-829 | PCI 5.1.1 Physical Reverse Flow at Moffat interconnection point (IE/UK) | United Kingdom | GNI (UK) Limited | Advanced | Yes | 5.1.1 (2018) | NSIW | Yes | PCI 5.1.1 | GNI, Network Development Plan 2016 | URL | 2018-12-15
TRA-N-950 | Guitiriz - Lugo - Zamora pipeline | Spain | Reganosa | Advanced | No |  |  | Yes | N/A. | PLANIFICACION ELECTRICIDAD Y GAS 2008-2016 | URL | 2008-05-01
LNG-N-962 | Tallinn LNG | Estonia | Vopak E.O.S. AS / Vopak LNG Holdings B.V/ Port of Tallinn AS | Advanced | No |  |  | Yes | Paragraph 3 point 7 | Eesti Gaasi Ülekandevõrgu arengukava 2018-2027. | URL | 2018-03-03
TRA-N-964 | New NTS developments for taking over gas from the Black Sea shore | Romania | SNTGN Transgaz SA | Advanced | Yes | 6.24.10.3 (2018) | NSIE | Yes | 7.6 | The National Gas Transmission System Development Plan 2017-2026 | URL | 2017-06-22
TRA-N-974 | LARINO - RECANATI Adriatic coast backbone | Italy | Società Gasdotti Italia | Advanced | No |  |  | Yes | Dorsale Larino Recanati | Piano Decennale di sviluppo delle reti di trasporto gas naturale 2017-2026 | URL
TRA-N-975 | Sardinia Gas Transportation Network | Italy | Società Gasdotti Italia | Advanced | No |  |  | Yes | Metanizzazione della regione Sardegna | Piano decennale di sviluppo delle reti di trasporto gas naturale 2017-2026 | URL | 2017-10-31
TRA-N-1057 | Compressor stations 2 and 3 at the Croatian gas tranmission system | Croatia | Plinacro Ltd | Advanced | Yes | 6.26.1.3 (2018) | NSIE | Yes | 5.3 and 5.4 | 2018-2027 | URL | 2017-12-15
TRA-N-1058 | LNG Evacuation Pipeline Kozarac-Slobodnica | Croatia | Plinacro Ltd | Advanced | Yes | 6.5.6 (2018) | NSIE | Yes | 1.32 | 2018-2027 | URL | 2017-12-15
TRA-N-1173 | Poland - Denmark interconnection (Baltic Pipe) - onshore section in Poland | Poland | GAZ-SYSTEM S.A. | Advanced | Yes | 8.3.2 (2018) | BEMIP | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
UGS-N-1229 | Underground Natural Gas Storage in Dumrea Area (UGS Dumrea) | Albania | Ministry of Infrastructure and Energy of Albania and Albgaz sh.a. | Advanced | No |  |  | Yes | Map no. 3.27; page no. 145 | National General Territory Plan of Albania DoCM no. 881, dated 14.012.2016 | URL | 2016-12-14
TRA-N-1268 | Romania-Serbia Interconnection | Romania | SNTGN Tranzgaz SA | Advanced | No |  |  | Yes | 7.7 | THE NATIONAL GAS TRANSMISSION SYSTEM DEVELOPMENT PLAN 2017-2026 | URL | 2017-06-22
TRA-N-1277 | Upgrading GMS Isaccea 1 and GMS Negru Voda 1 | Romania | SNTGN Transgaz SA | Advanced | No |  |  | Yes | 7.8 | The National Gas Transmission System development Plan 2017 - 2026 | URL | 2017-06-22
LNG-N-32 | Project GO4LNG LNG terminal Gothenburg | Sweden | Swedegas AB | Advanced | Yes | 8.06 (2018) | BEMIP | No | N/A | Not applicable for Sweden. There is no NDP yet. There will be one and then this project will be included but as for today there are no plan in Sweden. | URL
LNG-N-62 | LNG terminal in northern Greece / Alexandroupolis - LNG Section | Greece | Gastrade S.A. | Advanced | Yes | 6.9.1 (2018) | NSIE | No | N/A | The Project is not included in the NDP because it is an Independent Natural Gas System not developed or operated by the NTSO (DESFA). The Project will be included in the NDP of the NTSO once the application for ARCA is formally submitted by the Project promoter to DESFA (planned within 2017). | URL
TRA-N-63 | LNG terminal in northern Greece / Alexandroupolis - Pipeline Section | Greece | Gastrade S.A. | Advanced | Yes | 6.9.1 (2018) | NSIE | No | N/A | The Project is not included in the NDP because it is an Independent Natural Gas System not developed or operated by the NTSO (DESFA). The Project will be included in the NDP of the NTSO once the application for ARCA is formally submitted by the Project promoter to DESFA (planned within 2017). | URL
UGS-N-233 | Depomures | Romania | Engie Romania SA | Advanced | Yes | 6.20.4 (2018) | NSIE | No | N/A | As far as we are aware, currently there is no comprehensive system wide national development plan, only one regarding the gas transmission infrastructure put together by the TSO. Nevertheless, the operator submitted a 5-year investment plan to Romanian NRA in 2015, which is updated annualy. | URL
LNG-N-296 | Mugardos LNG Terminal: 2nd Jetty | Spain | Reganosa | Advanced | No |  |  | No | N/A | The last aproved Spanish NDP ended in 2016. The Royal Decree-Law 13/2012 cancel any award procedures of new regasification plants in Spain. | URL
LNG-N-297 | Mugardos LNG Terminal: Storage Extension | Spain | Reganosa | Advanced | No |  |  | No | N/A | The last aproved Spanish NDP ended in 2016. The Royal Decree-Law 13/2012 cancel any award procedures of new regasification plants in Spain. | URL
TRA-N-339 | Trans-Caspian | Turkmenistan | W-Stream Caspian Pipeline Company Ltd | Advanced | Yes | 7.1.1 (2018) | SGC | No | N/A | Countries outside EU do not have established practices similar to EU MSs for the NDPs. As for EU MSs, Germany has included the White Stream project, a continuation of the TCP project: http://www.fnb-gas.de/files/2015_07_27_nep_gas_2016_szenariorahmen.pdf | URL
UGS-N-374 | Enhancement of Incukalns UGS | Latvia | JSC "Conexus Baltic Grid" | Advanced | Yes | 8.2.4 (2018) | BEMIP | No | N/A | National developmeny plan for 2014-2020 does not specify particular projects, however, under Activity "Energy efficiency and energy production" item "7. Development of enery infrastructure networks" may include the project. | URL
TRA-N-382 | Enhancement of Latvia-Lithuania interconnection (Latvian part) | Latvia | JSC "Conexus Baltic Grid" | Advanced | Yes | 8.2.1 (2018) | BEMIP | No | N/A | National Development Plan for 2014-2020 does not specify particular projects. Under activity "Energy efficiency and energy production" title "7.Development of energy infrastructure networks" may include project of enhancement of Latvia-Lithuania interconnection | URL
TRA-N-394 | Norwegian tie-in to Danish upstream system | Denmark | Energinet.dk | Advanced | No |  |  | No | N/A | This is an upstream project from the North Sea (Norway) to a Danish onshore system. The project is vital for the Baltic-Pipe project (gas pipeline between Denmark and Poland). The project will be included in future national plans in connection when possibly including the Baltic Pipe. | URL
TRA-N-561 | Poland-Ukraine Interconnector (Ukrainian section) | Ukraine | PJSC UKRTRANSGAZ | Advanced | No |  |  | No | N/A |  | URL
TRA-N-763 | EUGAL - Europaeische Gasanbindungsleitung (European Gaslink) | Germany | GASCADE GmbH / Fluxys Deutschland GmbH / GUD GmbH&Co.KG / ONTRAS GmbH | Advanced | No |  |  | No | N/A | Capacities for this project will ultimately be allocated by auctioning in 2017. At the moment, it is assumed that these auction results will be included as an identified capacity requirement in the process for the NDP 2018. - Parts are included (Vierow 412-01) (www.more-capacity.eu/en) | URL
TRA-N-780 | Baltic Pipe project – onshore section in Denmark | Denmark | Energinet.dk | Advanced | Yes | 8.3.1 (2018) | BEMIP | No | N/A | Presently a feasibility study for the Baltic Pipe is carried out in cooperation between Gaz-System (Polish TSO) and Energinet.dk. The study will be finalized by end of 2016. If the study recommends a capacity of Baltic Pipe well above 3 bcm/y , this reinforcement project will be included in NDP. | URL
TRA-N-809 | Additional East-West transport | Germany | Gasunie Deutschland Transport Services GmbH | Advanced | No |  |  | No | N/A | Project idea. The inclusion in the NDP is planned at a later time. | URL | 2018-04-01
TRA-N-814 | Upgrade for IP Deutschneudorf et al. for More Capacity | Germany | ONTRAS Gastransport GmbH | Advanced | No |  |  | No | N/A | The project is not yet part of the recent German NDP 2016. The German NRA by decree of 11th December 2015 had ordered the German TSOs to only modell a 42 % coverage of the expected additional national demand from North East in the scenario Q2 including Nord Stream 2, but no further flows at IPs. | URL | 2018-04-01
LNG-N-1146 | Cyprus Gas2EU | Cyprus | Ministry of Energy, Commerce, Industry and Tourism | Advanced | Yes | 7.05 (2018) | SGC | No | N/A | Cuurently there is no TSO Gas in Cyprus | URL
TRA-N-1267 | Upgrade Sülstorf station | Germany | NGT GmbH / GUD GmbH & Co. KG / Fluxys D GmbH / ONTRAS GmbH | Advanced | No |  |  | No | N/A |  | URL
TRA-F-43 | Val de Saône project | France | GRTgaz | FID | No |  |  | Yes | Fusion des zones | Plan décennal de développement du réseau de GRTgaz 2017-2026 | URL | 2017-11-29
TRA-F-45 | Reverse capacity from CH to FR at Oltingue | France | GRTgaz | FID | No |  |  | Yes | Création de capacités d’entrée à partir de la Suisse | Plan de développement du réseau de transport de GRTgaz 2017-2026 | URL | 2017-11-27
TRA-F-137 | Interconnection Bulgaria - Serbia | Bulgaria | Ministry of Energy | FID | Yes | 6.10 (2018) | NSIE | Yes | Sectin 5.2 (5.2.3) | 2017-2026 Ten-year network development plan of BTG | URL | 2017-04-10
LNG-F-147 | Revythoussa (2nd upgrade) | Greece | DESFA S.A. | FID | No |  |  | Yes | 2.2.1.7 | Development Plan NNGS 2016-2025 | URL
LNG-F-163 | Gran Canaria LNG Terminal | Spain | Gascan | FID | No |  |  | Yes | No code in the NDP | Planta de regasificación de Gran Canaria | URL | 2008-05-01
LNG-F-178 | Musel LNG terminal | Spain | Enagás Transporte, S.A.U. | FID | No |  |  | Yes | No code in the NDP | planta de regasificación de El Musel | URL | 2008-05-01
LNG-F-183 | Tenerife LNG Terminal | Spain | Gascan | FID | No |  |  | Yes | No code in the NDP | Planta de regasificacion de Tenerife | URL | 2008-05-01
TRA-F-190 | Poland - Slovakia interconnection | Slovakia | eustream,a.s. (a joint-stock company) | FID | Yes | 6.2.1 (2018) | NSIE | Yes | 4.1.1.3.-PL-SK | National Development Plan 2018-2027 | URL | 2017-11-30
TRA-F-208 | Reverse Flow TENP Germany | Germany | Fluxys TENP GmbH & Open Grid Europe GmbH | FID | Yes | 5.01 (2018) | NSIW | Yes | 305-02 | Netzentwicklungsplan Gas 2016-2026 | URL | 2017-10-16
TRA-F-212 | Gas Interconnection Poland-Lithuania (GIPL) - PL section | Poland | GAZ-SYSTEM S.A. | FID | Yes | 8.05 (2018) | BEMIP | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-F-214 | Support to the North West market and bidirectional cross-border flows | Italy | Snam Rete Gas S.p.A. | FID | Yes | 5.11 (2018) | NSIW | Yes | RN_01 | Snam Rete Gas TYNDP 2017-2026 | URL | 2017-11-30
LNG-F-229 | Zeebrugge LNG Terminal - 5th Tank | Belgium | Fluxys LNG | FID | No |  |  | Yes | Zeebrugge LNG Terminal - 5th Tank | Ten-Year Indicative Investment Programme Fluxys Belgium & Fluxys LNG 2017-2026 | URL
TRA-F-241 | MONACO section phase I (Burghausen-Finsing) | Germany | bayernets GmbH | FID | No |  |  | Yes | 030-02a, 030-02b | Netzentwicklungsplan Gas 2018-2028 | URL | 2018-04-01
UGS-F-242 | Cornegliano UGS | Italy | ITAL Gas Storage | FID | No |  |  | Yes | RN_10 | Ten-year development plan of the natural gas transmission network 2017–2026 | URL | 2017-10-02
TRA-F-247 | North - South Gas Corridor in Western Poland | Poland | GAZ-SYSTEM S.A. | FID | Yes | 6.2.11 (2018) | NSIE | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
UGS-F-260 | System Enhancements - Stogit - on-shore gas fields | Italy | STOGIT | FID | No |  |  | Yes | NA | Snam Rete Gas TYNDP 2017-2026 | URL
LNG-F-272 | Upgrade of LNG terminal in Świnoujście | Poland | GAZ-SYSTEM S.A. | FID | Yes | 8.07 (2018) | BEMIP | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-F-275 | Poland - Slovakia Gas Interconnection (PL section) | Poland | GAZ-SYSTEM S.A. | FID | Yes | 6.2.1 (2018) | NSIE | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-F-286 | Romanian-Hungarian reverse flow Hungarian section 1st stage | Hungary | FGSZ Ltd. | FID | Yes | 6.24.1.1 (2018) | NSIE | Yes | 12.1. | Hungarian TYNDP 2016 | URL | 2016-12-21
TRA-F-298 | Rehabilitation, Modernization and Expansion of the NTS | Bulgaria | Bulgartransgaz EAD | FID | Yes | 6.8.2 (2018) | NSIE | Yes | Section 5.5. | 2017-2026 Ten-year network development plan of BTG | URL | 2017-04-10
TRA-F-329 | ZEELINK | Germany | Open Grid Europe GmbH and Thyssengas GmbH | FID | No |  |  | Yes | 204-02a, 205-02a, 416/02, | Netzentwicklungsplan 2016 (German NDP 2016) and consultation document German NDP 2018 | URL | 2017-10-16
TRA-F-331 | Gascogne Midi | France | TIGF - GRTgaz | FID | No |  |  | Yes | No number | 2015 NDP of GRTgaz and TIGF | URL
TRA-F-334 | Compressor station 1 at the Croatian gas transmission system | Croatia | Plinacro Ltd | FID | Yes | 6.5.5 (2018) | NSIE | Yes | 5.1 | 2018-2027 | URL | 2017-12-15
TRA-F-340 | CS Wertingen | Germany | bayernets GmbH | FID | No |  |  | Yes | 036-04 | Netzentwicklungsplan Gas 2018-2028 | URL | 2018-04-01
TRA-F-341 | Gas Interconnection Poland-Lithuania (GIPL) (Lithuania's section) | Lithuania | AB Amber Grid | FID | Yes | 8.05 (2018) | BEMIP | Yes | n/a | Network Development Plan 2017-2026 | URL | 2018-01-18
TRA-F-358 | Development on the Romanian territory of the NTS (BG–RO-HU-AT Corridor) | Romania | SNTGN Transgaz S.A. | FID | Yes | 6.24.1.2 (2018) | NSIE | Yes | 7.1 | Development Plan for the National GTS 2017-2026 | URL | 2017-06-22
TRA-F-378 | Interconnector Greece-Bulgaria (IGB Project) | Bulgaria | ICGB a.d. | FID | Yes | 6.8.1 (2018) | NSIE | Yes | not applicable | Included in both the TYNDPs of Greece and Bulgaria | URL
TRA-F-752 | Capacity4Gas – DE/CZ | Czechia | NET4GAS, s.r.o. | FID | No |  |  | Yes | TRA-F-752 | CZ NDP 2018-2027 (currently under approval process) | URL | 2017-10-31
TRA-F-895 | Balticconnector | Estonia | Elering AS | FID | Yes | 8.1.1 (2018) | BEMIP | Yes | paragraph 3.3 | EESTI GAASIÜLEKANDEVÕRGU ARENGUKAVA 2018‐2027 | URL | 2018-03-03
TRA-F-902 | Capacity increase at IP Lanžhot entry | Slovakia | eustream,a.s. (a joint-stock company) | FID | No |  |  | Yes | 4.1.1.3. Lanžhot | National Development Plan 2018-2027 | URL | 2017-11-30
TRA-F-915 | Enhancement of Estonia-Latvia interconnection | Estonia | Elering AS | FID | Yes | 8.2.2 (2018) | BEMIP | Yes | paragraph 3.3 | EESTI GAASIÜLEKANDEVÕRGU ARENGUKAVA 2018‐2027 | URL | 2018-03-03
TRA-F-918 | Capacity4Gas – CZ/SK | Czechia | NET4GAS, s.r.o. | FID | No |  |  | Yes | TRA-F-918 | CZ NDP 2018-2027 (currently under approval process) | URL | 2017-10-31
TRA-F-941 | Metering and Regulating station at Nea Messimvria | Greece | DESFA S.A. | FID | Yes | 7.1.3 (2018) | SGC | Yes | 2.2.1.5 | Development Plan NNGS 2016-2025 | URL | 2017-01-27
TRA-F-954 | TAG Reverse Flow | Austria | Trans Austria Gasleitung GmbH | FID | No |  |  | Yes | TAG 2016-01 | Coordinated Network Development Plan 2018-2027 | URL | 2018-01-19
TRA-F-1028 | Albania - Kosovo Gas Pipeline | Albania | Min. of Infrastructure and Energy AL & Min. of Economic Development KO | FID | No |  |  | Yes | Map no. 3.27, page 145 | General National Territory Plan of Albania | URL | 2016-12-14
UGS-F-1045 | Bordolano Second phase | Italy | STOGIT S.p.A. | FID | No |  |  | Yes | NA | Snam Rete Gas TYNDP 2017/2026 | URL | 2017-11-30
TRA-F-1193 | TAP interconnection | Italy | Snam Rete Gas S.p.A. | FID | No |  |  | Yes | RN_02 | Snam Rete Gas TYNDP 2017-2026 | URL | 2017-11-30
TRA-F-1228 | Interconnection with UGS in Cornegliano Laudense | Italy | Snam Rete Gas S.p.A. | FID | No |  |  | Yes | RN_10 | TYNDP 2017-2026 | URL | 2017-11-30
TRA-F-1271 | Compressor Station Krummhoern | Germany | Open Grid Europe GmbH | FID | No |  |  | Yes | 414-01 an 415-01 | Netzentwicklungsplan Gas 2016 (German NDP 2016) and draft NDP 2018 | URL | 2017-10-16
TRA-F-51 | Trans Adriatic Pipeline | Greece | Trans Adriatic Pipeline AG | FID | Yes | 7.1.3 (2018) | SGC | No | N/A | The TAP project is being developed on a stand-alone basis, independent from the national transmission systems of Greece, Albania and Italy. | URL
TRA-F-221 | TANAP - Trans Anatolian Natural Gas Pipeline Project | Turkey | SOCAR (The State Oil Company of the Azerbaijan Republic) | FID | Yes | 7.1.1 (2018) | SGC | No | N/A | TANAP Project is not directly constructed by Turkish Government whereas it is executed by a private legal entity. However, there are referrals to TANAP Project in National Development Plans of Turkey since TANAP has a strategic importance. | URL
TRA-F-230 | Reverse Flow Transitgas Switzerland | Switzerland | FluxSwiss | FID | No |  |  | No | N/A | No public NDP. | URL
TRA-F-928 | Balticconnector Finnish part | Finland | Baltic Connector Oy | FID | Yes | 8.1.1 (2018) | BEMIP | No | N/A | The national Natural Gas Market legislation does not set system operators any obligation to draw up and publish a NDP. | URL
TRA-F-937 | Nord Stream 2 | Germany | Nord Stream 2 AG | FID | No |  |  | No | N/A | Nord Stream 2 is to be included in the German Net Development Plan 2016 (currently under discussion). | URL
TRA-F-1138 | South Caucasus Pipeline - (Future) Expansion - SCP-(F)X | Azerbaijan | SOCAR Midstream Operations LLC | FID | Yes | 7.1.1 (2018) | SGC | No | N/A | South Caucasus Pipeline Future Expansion project to be developed based on investment decision of consortium consisting from international companies and after approval of Azerbaijan Government, which consider energy infrastructure projects as an investment in projects containing strategic interest. | URL
TRA-F-1241 | Interconnection with production in Gela | Italy | Snam Rete Gas S.p.A. | FID | No |  |  | No | N/A |  | URL
TRA-N-7 | Development for new import from the South (Adriatica Line) | Italy | Snam Rete Gas S.p.A. | Less-Advanced | Yes | 7.3.4 (2018) | SGC | Yes | RN_04 | Snam Rete Gas TYNDP 2017-2026 | URL | 2017-11-30
TRA-N-8 | Import developments from North-East | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | Yes | RN_06 | Snam Rete Gas TYNDP 2017-2026 | URL | 2017-11-30
TRA-N-9 | Additional Southern developments | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | Yes | RN_07 | Snam Rete Gas TYNDP 2017-2026 | URL
TRA-N-14 | Komotini-Thesprotia pipeline | Greece | DESFA S.A. | Less-Advanced | No |  |  | Yes | 2.2.1.6 | Development Plan NNGS 2016-2025 | URL
TRA-N-17 | System Enhancements - Eustream | Slovakia | eustream, a.s. | Less-Advanced | No |  |  | Yes | 4.2.1 | National Development Plan 2018-2027 | URL | 2017-11-30
TRA-N-27 | Physical reverse flow from NI to GB and IE via SNIP pipeline | United Kingdom | Premier Transmission Limited | Less-Advanced | Yes | 5.1.2 (2018) | NSIW | Yes | n.a. | Northern Ireland Gas Capacity Statement | URL | 2017-10-26
TRA-N-47 | Reverse capacity from France to Germany at Obergailbach | France | GRTgaz | Less-Advanced | No |  |  | Yes | na | Plan décennal de développement du réseau de transport de GRTgaz 2017-2026 | URL | 2017-11-27
LNG-N-50 | Gate terminal phase 3 | Netherlands | Gate | Less-Advanced | No |  |  | Yes | unknown see GTS | GTS | URL | 2018-03-01
TRA-N-71 | Physical Reverse Flow on South North Pipeline | Ireland | Gas Networks Ireland | Less-Advanced | No |  |  | Yes | N/A | Gaslink, Network development Plan 2013 | URL
LNG-N-79 | Paldiski LNG Terminal | Estonia | Balti Gaas plc | Less-Advanced | No |  |  | Yes | - | Estonian transmission system development plan for 2018-2027 | URL | 2018-03-03
TRA-N-92 | CS Ajdovščina, 1st phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | No |  |  | Yes | C1 | TYNDP for the period 2018-2027 | URL | 2017-10-09
TRA-N-94 | CS Kidričevo, 2nd phase of upgrade | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.1.2 (2018) | NSIE | Yes | C5 | TYNDP for the period 2018-2027 | URL | 2017-10-09
TRA-N-108 | M3 pipeline reconstruction from CS Ajdovščina to Šempeter/Gorizia | Slovenia | Plinovodi d.o.o. | Less-Advanced | No |  |  | Yes | C2 | TYNDP for the period 2018-2027 | URL | 2017-10-09
TRA-N-112 | R15/1 Pince - Lendava - Kidričevo | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.23 (2018) | NSIE | Yes | C3 | TYNDP for the period 2018-2027 | URL | 2017-10-09
TRA-N-128 | Compressor Station Kipi | Greece | DESFA S.A. | Less-Advanced | Yes | 6.8.1 (2018) | NSIE | Yes | 2.2.1.3 | Development Plan NNGS 2016-2025 | URL
TRA-N-140 | Interconnection Turkey-Bulgaria | Bulgaria | Bulgartransgaz EAD | Less-Advanced | No |  |  | Yes | ITB | 2017-2026 Ten-year network development plan of BTG | URL | 2017-04-10
TRA-N-192 | Entry capacity expansion GATE terminal | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  |  | Yes | 6.5.2 | Netwerk Ontwikkelingsplan 2017 | URL
TRA-N-224 | Gaspipeline Brod - Zenica | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | No |  |  | Yes | PTG1 | SPP-Strategic plan and programme of FBiH | URL | 2009-09-30
LNG-N-225 | Montoir LNG Terminal Expansion | France | Elengy | Less-Advanced | No |  |  | Yes | Montoir Extension | GRTgaz Ten Year Development plan 2015-2024 | URL | 2017-11-27
LNG-N-227 | Fos Cavaou LNG Terminal Expansion | France | Fosmax LNG | Less-Advanced | No |  |  | Yes | Fos Cavaou Extension | GRTgaz Ten Year Development plan 2015-2024 | URL
TRA-N-245 | North - South Gas Corridor in Eastern Poland | Poland | GAZ-SYSTEM S.A. | Less-Advanced | Yes | 6.2.2 (2018) | NSIE | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-N-258 | Developments for Montoir LNG terminal 2.5 bcm expansion | France | GRTgaz | Less-Advanced | No |  |  | Yes | Augmentation des capacités d’entrée à partir du terminal de Montoir de 10 à 12,5 Gm³/an | Plan décennal de développement du réseau de transport de GRTgaz 2017-2026 | URL | 2017-11-27
TRA-N-269 | Developments for Fosmax (Cavaou) LNG 8.25 bcm expansion | France | GRTgaz | Less-Advanced | No |  |  | Yes | Extension du terminal de Fos Cavaou à 16,5 Gm³/an | Plan décennal de développement du réseau de transport de GRTgaz 2017-2026 | URL | 2017-11-27
TRA-N-284 | 3rd IP between Portugal and Spain (Compressor Station) | Portugal | REN-Gasodutos, S.A. | Less-Advanced | Yes | 5.4.2. (2018) | NSIW | Yes | - | PDIRGN 2017 | URL
TRA-N-285 | 3rd IP between Portugal and Spain (pipeline Cantanhede-Mangualde) | Portugal | REN-Gasodutos, S.A. | Less-Advanced | Yes | 5.4.2. (2018) | NSIW | Yes | - | PDIRGN 2017 | URL
LNG-N-295 | Mugardos LNG Terminal: Send-out Increase | Spain | Reganosa | Less-Advanced | No |  |  | Yes | No Number- Name: Ampliación Planta de Reganosa. Ampliación de Emisión a 825,600 Nm3/h | PLANIFICACION ELECTRICIDAD Y GAS 2008-2016 | URL | 2008-05-01
TRA-N-303 | Interconnection Croatia-Bosnia and Herzegovina (west) | Croatia | Plinacro Ltd | Less-Advanced | No |  |  | Yes | 1.35 and 1.36 | 2018-2027 | URL | 2018-12-15
TRA-N-336 | Interconnection Croatia/Slovenia (Umag-Koper) | Croatia | Plinacro Ltd | Less-Advanced | No |  |  | Yes | 1.37 | 2018-2027 | URL | 2017-12-15
TRA-N-342 | Enhancement of Latvia-Lithuania interconnection (Lithuania's part) | Lithuania | AB Amber Grid | Less-Advanced | Yes | 8.2.1 (2018) | BEMIP | Yes | n/a | Network Development Plan 2017-2026 | URL | 2018-01-18
TRA-N-354 | Interconnection with Slovenia | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | Yes | RN_03 | Snam Rete Gas TYNDP 2017-2026 | URL | 2017-11-30
TRA-N-389 | Upgrade of Murfeld/Ceršak interconnection (M1/3 Interconnection Ceršak) | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.1.5 (2018) | NSIE | Yes | C4 | TYNDP for the period 2018-2027 | URL | 2017-10-09
TRA-N-390 | Upgrade of Rogatec interconnection (M1A/1 Interconnection Rogatec) | Slovenia | Plinovodi d.o.o. | Less-Advanced | Yes | 6.26.6 (2018) | NSIE | Yes | C12 | TYNDP for the period 2018-2027 | URL | 2017-10-09
TRA-N-429 | Adaptation L- gas - H-gas | France | GRTgaz and Storengy | Less-Advanced | Yes | 5.21 (2018) | NSIW | Yes | Plan de conversion du gaz B en gaz H | Plan décennal de développement du réseau de GRTgaz 2017-2026 | URL | 2017-11-27
TRA-N-524 | Enhancement of Transmission Capacity of Slovak-Hungarian interconnector | Hungary | Magyar Gáz Tranzit Zrt. | Less-Advanced | Yes | 6.2.13 (2018) | NSIE | Yes | TRA-N-524 (new nr will be received once project is approved) | National Development Plan- MGT 10 Year Development Plan | URL
TRA-N-636 | Development of Transmission Capacity at Slovak-Hungarian interconnector | Hungary | Magyar Gáz Tranzit Zrt. | Less-Advanced | Yes | 6.2.13 (2018) | NSIE | Yes | TRA-N-636 | National Development Plan - MGT 10 Year Development Plan | URL
TRA-N-654 | Eastring - Bulgaria | Bulgaria | Bulgartransgaz EAD | Less-Advanced | Yes | 6.25.1 (2018) | NSIE | Yes | Section 5.1(5.1,2) | 2017-2026 Ten-year network development plan of BTG | URL | 2017-04-10
TRA-N-656 | Eastring - Hungary | Hungary | FGSZ Ltd. | Less-Advanced | Yes | 6.25.1 (2018) | NSIE | Yes | 12.13. | National Development Plan 2017 | URL | 2017-12-28
LNG-N-742 | Zeebrugge LNG Terminal - 3rd Jetty | Belgium | Fluxys LNG | Less-Advanced | No |  |  | Yes | Zeebrugge LNG Terminal - 3rd Jetty | Ten-Year Indicative Investment Programme Fluxys Belgium & Fluxys LNG 2017-2026 | URL
TRA-N-755 | CS Rimpar | Germany | GRTgaz Deutschland GmbH | Less-Advanced | No |  |  | Yes | 312-01 | Netzentwicklungsplan Gas 2016 and consulation document Netzentwicklungsplan Gas 2018 | URL | 2017-10-16
TRA-N-831 | Vecsés-Városföld gas transit pipeline | Hungary | Magyar Gáz Tranzit Zrt. | Less-Advanced | Yes | 6.2.14 (2018) | NSIE | Yes | TRA-N-831 | National Development Plan - MGT 10 Year Development Plan | URL
TRA-N-851 | Southern Interconnection pipeline BiH/CRO | Bosnia Herzegovina | BH-GAS d.o.o. | Less-Advanced | No |  |  | Yes | PTG2 | SPP-Strategic plan and programme of FBiH | URL | 2009-09-30
TRA-N-873 | Additional capacity at OSZ from Germany to the Netherlands | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  |  | Yes | 6.5.4. | Netwerk Ontwikkelingsplan 2017 | URL
TRA-N-882 | Transferring L-gas infrastructure to H-gas | Netherlands | Gasunie Transport Services B.V. | Less-Advanced | No |  |  | Yes | 6.5.1 | Netwerk Ontwikkelingsplan 2017 | URL
TRA-N-910 | West Interconnection BiH/CRO | Bosnia Herzegovina | BH-Gas d.o.o. | Less-Advanced | No |  |  | Yes | PTG4 | SPP-Strategic plan and programme of FBiH | URL | 2009-09-30
UGS-N-914 | UGS Damasławek | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  |  | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
LNG-N-947 | FSRU Polish Baltic Sea Coast | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  |  | Yes | N/A | National Ten-Year Transmission System Development Plan 2018-2027 | URL
TRA-N-949 | Oude(NL)-Bunde(DE) GTG H-Gas | Germany | Gastransport Nord GmbH | Less-Advanced | No |  |  | Yes | 432-01 | Netzentwicklungsplan Entwurf 2016-2026 | URL | 2017-10-16
TRA-N-951 | Embedding CS Folmhusen in H-Gas | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  |  | Yes | ID 300-02 | NEP Gas 2015; NEP Gas 2016-2026 | URL | 2017-10-16
TRA-N-955 | GUD: Complete conversion to H-gas | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  |  | Yes | ID 221-01 ID; ID 222-02; ID 223-01 | NEP Gas 2014; NEP Gas 2015; NEP Gas 2016-2026 | URL | 2017-10-17
TRA-N-959 | Further enlargement of the BG—RO—HU—AT transmission corridor (BRUA) phase 3 | Romania | SNTGN Transgaz SA | Less-Advanced | Yes | 6.24.10.2 (2018) | NSIE | Yes | 7.5 | The National Gas Transmission System Development Plan 2017-2026 | URL | 2017-06-22
TRA-N-965 | Interconnection Macedonia-Serbia | former Yugoslav Republic of Macedonia | MER JSC Skopje | Less-Advanced | No |  |  | Yes | N/A | Work Program of the Government of R. Macedonia | URL
TRA-N-967 | Nea-Messimvria to FYRoM pipeline | Greece | DESFA S.A. | Less-Advanced | No |  |  | Yes | 2.1.2.2 | Draft NDP 2017-2026 | URL
TRA-N-976 | Interconnection Macedonia-Bulgaria | former Yugoslav Republic of Macedonia | MER JSC Skopje | Less-Advanced | No |  |  | Yes | N/A | Work Program of the Government of R.Macedonia | URL
TRA-N-980 | Interconnection Macedonia-Greece | former Yugoslav Republic of Macedonia | MER JSC Skopje | Less-Advanced | No |  |  | Yes | N/A | Work Program of the Government of R.Macedonia | URL
TRA-N-1129 | Compressor Station Kipi Increment | Greece | DESFA S.A. | Less-Advanced | No |  |  | Yes | 2.2.1.3 | Development Plan NNGS 2016-2025 | URL
TRA-N-1194 | Sardinia Methanization | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | Yes | RN_09 | Snam Rete Gas TYNDP 2017-2026 | URL | 2017-11-30
TRA-N-1195 | Matagiola - Massafra pipeline | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | Yes | RN_05 | Snam Rete Gas TYNDP 2017-2026 | URL | 2017-11-30
LNG-N-1231 | Inisfree LNG | Ireland | NextDecade LNG | Less-Advanced | No |  |  | Yes | CER17278 | Gas Networks Ireland's 2017 Network Development Plan; approved by the Commission for Regulation of Utilities on Dec. 15, 2017 (CRU/17/340) | URL
TRA-N-1235 | Firm transmission capacity increase at the IP Veľké Zlievce | Slovakia | eustream,a.s. (a joint-stock company) | Less-Advanced | No |  |  | Yes | 4.1.1.3 Firm transmission capacity increase at the IP Veľké Zlievce | National Development Plan 2018 - 2027 | URL | 2017-11-30
TRA-N-1254 | CS Elten | Germany | Open Grid Europe GmbH and Thyssengas GmbH | Less-Advanced | No |  |  | Yes | 422/01 | Netzentwicklungsplan 2016 (German NDP 2016) and consultation document German NDP 2018 | URL | 2017-10-16
TRA-N-1276 | Compressor station at Nea Messimvria (3rd unit) | Greece | DESFA S.A. | Less-Advanced | No |  |  | Yes | 2.1.2.9 | Draft Development Plan 2017-2026 | URL
TRA-N-1278 | Compressor station at Ambelia | Greece | DESFA S.A. | Less-Advanced | No |  |  | Yes | 2.1.2.3 | Draft Development Plan 2017-2026 | URL
TRA-N-1303 | IAEF - Vlora ccgt | Albania | Albgaz Sha | Less-Advanced | No |  |  | Yes | PiP1 | Plani 10 Vjecar i Zhvillimit | URL | 2018-02-15
TRA-N-53 | White Stream | Georgia | White Stream Ltd | Less-Advanced | No |  |  | No | N/A | Countries outside EU do not have established practices similar to EU MSs for the NDPs. As for EU MSs, Germany has included the White Stream project, a continuation of the TCP project: http://www.fnb-gas.de/files/2015_07_27_nep_gas_2016_szenariorahmen.pdf | URL
TRA-N-168 | Interconnection ES-PT (3rd IP) - 1st phase | Spain | Enagás Transporte, S.A.U. | Less-Advanced | Yes | 5.4.1 (2018) | NSIW | No | N/A | The project was not included in the last NDP that was published in 2008. The project was identified later on, and was selected as PCI by the European Commission in 2013 and in 2015. Additionally, this project is being considered in the High Level Group on Interconnections for South-West Europe. | URL
TRA-N-330 | EastMed Pipeline | Greece | Natural Gas Submarine Interconnector Greece-Italy Poseidon S.A | Less-Advanced | Yes | 7.3.1 (2018) | SGC | No | N/A | EastMed pipeline is not included in the Greek NDP, as the project is considered an Indipendent Natural gas System. In Cyprus there is no NND as the country does not have any gas TSO. | URL
UGS-N-371 | Sarmasel undeground gas storage in Romania | Romania | Societatea Naţională de Gaze Naturale ROMGAZ S.A. | Less-Advanced | Yes | 6.20.6 (2018) | NSIE | No | N/A | S.N.G.N. ROMGAZ S.A., the project promotor, is not a TSO, therefore it is not mandatory to have a TYNDP, as Transgaz does. There is no NDP at country level. | URL
LNG-N-376 | Azerbaijan, Georgia, Romania Interconnector - AGRI | Romania | AGRI LNG Project Company SRL (RO) | Less-Advanced | No |  |  | No | N/A | AGRI is not a Transmission System Operator, so it is not necessary for its project to be part of a National Development Plan. | URL
UGS-N-385 | South Kavala Underground Gas Storage facility | Greece | Hellenic Republic Asset anagement Fund | Less-Advanced | No |  |  | No | N/A | The Project Promoter is not a Transmission System Operator and as such does not have the obligation to submit a National Development Plan. | URL
TRA-N-645 | HU-UA reverse flow (Ukrainian section) | Ukraine | PJSC Ukrtransgaz | Less-Advanced | No |  |  | No | N/A |  | URL
TRA-N-655 | Eastring - Romania | Romania | SNTGN Transgaz SA | Less-Advanced | Yes | 6.25.1 (2018) | NSIE | No | N/A | For the moment, the project lacks sufficient descriptive elements in order for it to be included in the National Gas Transmission System Development Plan. | URL
TRA-N-729 | Interconnection ES-PT (3rd IP) - 2nd phase | Spain | Enagás Transporte, S.A.U. | Less-Advanced | Yes | 5.4.2. (2018) | NSIW | No | N/A | The project was not included in the last NDP that was published in 2008. The project was identified later on, and was selected as PCI by the European Commission in 2013 and in 2015. Additionally, this project is being considered in the High Level Group on Interconnections for South-West Europe. | URL
TRA-N-808 | Transport of gas volumes to the Netherlands | Germany | Gasunie Deutschland Transport Services GmbH | Less-Advanced | No |  |  | No | N/A | Decision of BNetzA (Tenor 3d) regarding the NEP 2016: The H-Gas balance related to variant Q2 of the NEP 2016 shows an add. demand of 42% in the region "North-East". Any other add. demands which are not covered by binding bookings are not taken into account on IPs (neither entry nor exit). | URL | 2018-04-01
LNG-N-824 | LNG Terminal in Klaipeda | Lithuania | AB Klaipėdos Nafta | Less-Advanced | No |  |  | No | N/A | NDP covers only TSO investments. LNG terminal is not a part of TSO network, therefore NDP does not include LNG terminal projects. LNG projects are covered by TYNDP at EU level, not at the national level. | URL
LNG-N-912 | Skulte LNG | Latvia | AS Skulte LNG Terminal | Less-Advanced | No |  |  | No | N/A | Project will be included in NDP by end of 2017 after completion of Environmental Impact Assessment process. | URL
TRA-N-971 | Compressor station at Nea Messimvria | Greece | DESFA S.A. | Less-Advanced | Yes | 7.1.3 (2018) | SGC | No | N/A | The project is currently in the maturing phase and will be included in the Development Plan at a later stage. | URL
TRA-N-1064 | Moffat Physical Reverse Flow | United Kingdom | National Grid Gas plc | Less-Advanced | Yes | 5.1.1 (2018) | NSIW | No | N/A | This project is not part of our network development plan as we do not view it as a network development issue but rather we view it as a connection issue. It is for Gaslink to make the investment decision on this project. | URL
TRA-N-1090 | Metering and Regulating Station at Alexandroupoli | Greece | DESFA S.A. | Less-Advanced | Yes | 6.9.1 | NSIE | No | N/A | This project is not included in the National Development Plan because no application has been made, by the promoter of the LNG terminal in Northern Greece, for the connection of this project to the Greek gas transmission system. | URL
TRA-N-1091 | Metering and Regulating station at Megalopoli | Greece | DESFA S.A. | Less-Advanced | Yes | 7.3.1 (2018) | SGC | No | N/A | This project is not included in the National Development Plan because no application has been made, by the promoter of the East-Med pipeline, for the connection of this project to the Greek gas transmission system. | URL
TRA-N-1092 | Metering and Regulating Station at UGS South Kavala | Greece | DESFA S.A. | Less-Advanced | Yes | 6.20.3 (2018) | NSIE | No | N/A | This project is not included in the National Development Plan because no application has been made, by the promoter of the UGS in South Kavala, for the connection of this project to the Greek gas transmission system. | URL
TRA-N-1169 | Trans-Balkan Bi-directional Flow | Ukraine | PJSC "UKRTRANSGAZ" | Less-Advanced | No |  |  | No | N/A |  | URL
TRA-N-1197 | Expansion of the gas infrastructure between BG-TR and BG-RS borders | Bulgaria | Bulgartransgaz EAD | Less-Advanced | No |  |  | No | N/A |  | URL
LNG-N-1198 | LNG Terminal Brunsbuettel | Germany | Gasunie Deutschland Transport Service GmbH | Less-Advanced | No |  |  | No | N/A |  | URL
TRA-N-1199 | LNG Terminal Brunsbuettel - Grid Integration | Germany | Gasunie Deutschland Transport Service GmbH | Less-Advanced | No |  |  | No | N/A |  | URL | 2018-04-01
TRA-N-1200 | Expansion MS Hetlingen | Germany | Gasunie Deutschland Transport Service GmbH | Less-Advanced | No |  |  | No | N/A |  | URL
TRA-N-1202 | GCP GAZ-SYSTEM/ONTRAS - incremental capacity project | Poland | GAZ-SYSTEM S.A. | Less-Advanced | No |  |  | No | N/A |  | URL
TRA-N-1227 | Gorizia plant upgrade | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | No | N/A |  | URL
TRA-N-1246 | Greece - Italy interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | No | N/A |  | URL
TRA-N-1253 | Trans-Balkan Bi-directional Flow (Moldavia phase) | Moldavia | Moldovatransgaz LLC | Less-Advanced | No |  |  | No | N/A |  | URL
TRA-N-1265 | Biomethane productions interconnection | Italy | Snam Rete Gas S.p.A. | Less-Advanced | No |  |  | No | N/A |  | URL